## Feb 00
Period | 4/1/2000-4/30/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
4348 Construction Equipment | 3507.43
|  | 113.62 | 9715 Bard PC stuff | 2.1.7.11.2.2
|  | 1457 | 9715 1/15/00 ENG | 2.1.7.11.2.1
|  | 874.2 | 9715 1/29/00 ENG | 2.1.7.11.2.1
|  | 504.74 | 9725 1/15/00 ENG | 2.1.7.11.2.1
|  | 557.87 | 9725 1/29/00 ENG | 2.1.7.11.2.1
3507.43
Subtotal | 3507.43
Total Direct Cost | 3507.43
Indirect Cost | 0
Total Cost | 3507.43
Less Payments Previously Requested | 0
Please Remit This Amount | 3507.43
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG | 3393.81
|  | 2.1.7.11.2.2 | FEE M&S | 113.62
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | Total | 3507.43
|  |  | Check | 0

## Mar 00 cor
Period | 4/1/2000-4/30/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1020 Graduate Assistant | 2164.33
|  | 2164.33 | Hongbo ???? | 2.1.7.1.1.3.1
3321 Travel - Domestic | 2401.73
|  | 440 | Baden 2/26/00 reimbursement | 2.1.1.8.6.9
|  | 148.96 | Skuja 2/26/00 reimbursement | 2.1.1.8.6.9
|  | 598.77 | Skuja 2/26/00 reimbursement | 2.1.1.8.6.9
|  | 326 | ??? Delta 3/3/00 | 2.1.1.8.6.9
|  | 305 | ??? Delta 3/3/00 | 2.1.1.8.6.9
|  | 245 | ??? Delta 3/3/00 | 2.1.1.8.6.9
|  | 338 | Kunori 3/11/00 reimbursement | 2.1.1.8.6.9
2401.73
SUBTOTAL (for overhead) | 4566.06
9998 Indirect Costs | 2191.7088
|  | 1038.8784 | 1020 Graduate Assistant | 2.1.7.1.1.3.1
|  | 1152.8304 | 3321 Travel - Domestic | 2.1.1.8.6.9
2191.7088
SUBTOTAL | 6757.7688
Equipment | 10558.38
|  | 2427.04 | 9715 2/12/00 ENG | 2.1.7.11.2.1
|  | 2009.46 | 9715 2/26/00 ENG | 2.1.7.11.2.1
|  | 876.65 | 9725 2/12/00 ENG | 2.1.7.11.2.1
|  | 2276.41 | 9725 2/26/00 ENG | 2.1.7.11.2.1
|  | 383.75 | 9715 2/28/2000 Creative Baum Marshall | 2.1.7.11.2.2
|  | 26.24 | Baden 3/16/00 COMPUSA | 2.1.7.1.1.2
|  | 120.94 | Baden 3/16/00 SONY VAIO | 2.1.7.1.1.2
|  | 177 | Baden 3/16/00 VITA (VME books) | 2.1.7.1.1.2
|  | 2260.89 | Baden 3/16/00 SONY VAIO (see July 00) | 2.1.7.1.1.2
10558.38
Subtotal | 10558.38
Total Cost | 17316.1488
Less Payments Previously Requested | 0
Please Remit This Amount | 17316.1488
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel | 3554.5604
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report | 2585.07
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG | 3203.2084
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG | 7589.56
|  | 2.1.7.11.2.2 | FEE M&S | 383.75
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | Total | 17316.1488
|  |  | Check | 0

## Mar 00
Period | 4/1/2000-4/30/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1020 Graduate Assistant | 2164.33
|  | 2164.33 | Hongbo ???? | 2.1.7.1.1.3.1
3952 Other (M&S) | 2585.07
|  | 26.24 | Baden 3/16/00 COMPUSA | 2.1.7.1.1.2
|  | 120.94 | Baden 3/16/00 SONY VAIO | 2.1.7.1.1.2
|  | 177 | Baden 3/16/00 VITA (VME books) | 2.1.7.1.1.2
|  | 2260.89 | Baden 3/16/00 SONY VAIO (see July 00) | 2.1.7.1.1.2
2585.07
3321 Travel - Domestic | 2401.73
|  | 440 | Baden 2/26/00 reimbursement | 2.1.1.8.6.9
|  | 148.96 | Skuja 2/26/00 reimbursement | 2.1.1.8.6.9
|  | 598.77 | Skuja 2/26/00 reimbursement | 2.1.1.8.6.9
|  | 326 | ??? Delta 3/3/00 | 2.1.1.8.6.9
|  | 305 | ??? Delta 3/3/00 | 2.1.1.8.6.9
|  | 245 | ??? Delta 3/3/00 | 2.1.1.8.6.9
|  | 338 | Kunori 3/11/00 reimbursement | 2.1.1.8.6.9
2401.73
SUBTOTAL (for overhead) | 7151.13
9998 Indirect Costs | 3432.5424
|  | 1038.8784 | 1020 Graduate Assistant | 2.1.7.1.1.3.1
|  | 1240.8336 | 3952 Other (M&S) | 2.1.7.1.1.2
|  | 1152.8304 | 3321 Travel - Domestic | 2.1.1.8.6.9
3432.5424
SUBTOTAL | 10583.6724
Equipment | 7973.31
|  | 2427.04 | 9715 2/12/00 ENG | 2.1.7.11.2.1
|  | 2009.46 | 9715 2/26/00 ENG | 2.1.7.11.2.1
|  | 876.65 | 9725 2/12/00 ENG | 2.1.7.11.2.1
|  | 2276.41 | 9725 2/26/00 ENG | 2.1.7.11.2.1
|  | 383.75 | 9715 2/28/2000 Creative Baum Marshall | 2.1.7.11.2.2
7973.31
Subtotal | 7973.31
Total Cost | 18556.9824
Less Payments Previously Requested | 0
Please Remit This Amount | 18556.9824
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel | 3554.5604
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report | 3825.9036
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG | 3203.2084
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG | 7589.56
|  | 2.1.7.11.2.2 | FEE M&S | 383.75
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | Total | 18556.9824
|  |  | Check | 0

## April 00
Period | 4/1/2000-4/30/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1020 Graduate Assistants | 1236.76
|  | 618.38 | Hongbo 9/9 | 2.1.7.1.1.3.1
|  | 618.38 | Hongbo 9/23 | 2.1.7.1.1.3.1
|  | 1236.76 | TOTAL
3922+4045 M&S etc | 969.9
|  | 900 |  | 2.1.7.1.1.1
|  | 69.9 |  | 2.1.7.1.1.1
969.9
3321 Travel - Domestic | 272.86
|  | 129.15 | Skuja 4/8 | 2.1.1.8.6.9
|  | 143.71 | Skuja 4/22 | 2.1.1.8.6.9
272.86
SUBTOTAL (for overhead) | 2479.52
9998 Indirect Costs | 1190.1696
|  | 593.6448 | 1020 Graduate Assistants | 2.1.7.1.1.3.1
|  | 465.552 | 3922+4045 M&S etc | 2.1.7.1.1.1
|  | 130.9728 | 3321 Travel - Domestic | 2.1.1.8.6.9
1190.1696
SUBTOTAL | 3669.6896
Equipment | 9963.52
|  | 202.16 | 9715 3/14-4/07/00 | 2.1.7.11.1.1
|  | 2170.33 | 9715 3/11/00 ENG | 2.1.7.11.1.1
|  | 1457 | 9715 3/25/00 ENG | 2.1.7.11.1.1
|  | 3583.43 | 9725 3/11/00 ENG | 2.1.7.11.1.1
|  | 1738.35 | 9725 3/25/00 ENG | 2.1.7.11.1.1
|  | 812.25 | 9725 4/7/00 Touart Advancec Circuits | 2.1.7.11.1.1
9963.52
Subtotal | 9963.52
Total Cost | 13633.2096
Less Payments Previously Requested | 0
Please Remit This Amount | 13633.2096
2.1.1.8.6.9 | 403.8328
2.1.7.1.1.3.1 | 1830.4048
2.1.7.11.1.1 | 11398.972
13633.2096

## May 00
Period | 5/1/2000-5/31/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1020 Graduate Assistants | 1236.76
|  | 618.38 | Hongbo 5/6 | 2.1.7.1.1.2 | 2.1.7.1.1.3.1
|  | 618.38 | Hongbo 5/20 | 2.1.7.1.1.2 | 2.1.7.1.1.3.1
|  | 1236.76 | TOTAL
3914+3922+3952+4045 M&S | 732.94
|  | 57.94 | Baden Amazon.com | 2.1.7.1.1.1 | 2.1.7.1.1.3.2
|  | 600 | Baden Synplicity | 2.1.7.1.1.1 | 2.1.7.1.1.3.2
|  | 75 | Baden ???? | 2.1.7.1.1.1 | 2.1.7.1.1.3.2
|  | 732.94 | TOTAL
3321 Travel - Domestic | 195.07
|  | 195.07 | Skuja 5/6 | 2.1.1.8.6.9
3360 Travel - Foreign | 1124.84
|  | 611.65 | Skuja 5/5 | 2.1.1.8.6.9
|  | 513.19 | Skuja 5/5 | 2.1.1.8.6.9
|  | 1124.84 | TOTAL
SUBTOTAL (for overhead) | 3289.61
9998 Indirect Costs | 1579.0128
|  | 593.6448 | 1020 Graduate Assistants | 2.1.7.1.1.2 | 2.1.7.1.1.3.1
|  | 351.8112 | 3914+3922+3952+4045 M&S | 2.1.7.1.1.1 | 2.1.7.1.1.3.1
|  | 93.6336 | 3321 Travel - Domestic | 2.1.1.8.6.9
|  | 539.9232 | 3360 Travel - Foreign | 2.1.1.8.6.9
1579.0128
Subtotal | 4868.6228
Equipment | 10834.4
|  | 247.5 | 9715 Touart Vitesse | 2.1.7.11.1.2
|  | 1587.53 | 9715 Labor 4/8/00 | 2.1.7.11.2.1
|  | 1966.31 | 9715 Labor 4/22/00 | 2.1.7.11.2.1
|  | 1736.3 | 9715 Baum DAWN VME 5/5/00 | 2.1.7.11.1.5
|  | 41.9 | 9715 " shipping | 2.1.7.11.1.5
|  | 3089.78 | 9725 Labor 4/8/00 | 2.1.7.11.2.1
|  | 2165.08 | 9725 Labor 4/22/00 | 2.1.7.11.2.1
10834.4
Subtotal | 10834.4
Total Cost | 15703.0228
Less Payments Previously Requested | 0
Please Remit This Amount | 15703.0228
2.1.1.8.6.9 | 1953.4668
2.1.7.1.1.1
2.1.7.1.1.2 | 1830.4048
2.1.7.1.1.3.1 | 1084.7512
2.1.7.1.1.3.2
2.1.7.11.1.2 | 247.5
2.1.7.11.1.5 | 1778.2
2.1.7.11.2.1 | 8808.7
15703.0228

## Jun 00
Period | 6/1/2000-6/32/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty 12 Months | 8978.18
|  | 7095.66 | Tullio ??? | 2.1.7.13.1
|  | 1882.52 | Tullio 6/30 | 2.1.7.13.1
|  | 8978.18 | TOTAL
1020 Graduate Assistants | 1810.97
|  | 618.38 | Hongbo 6/3 | 2.1.7.1.1.3.1
|  | 618.38 | Hongbo 6/17 | 2.1.7.1.1.3.1
|  | 574.21 | Hongbo 6/30 | 2.1.7.1.1.3.1
|  | 1810.97 | TOTAL
2725 Social Security | 144.02
|  | 144.02 | Tullio FICA | 2.1.7.1.1.3.1
3952 Other (M&S) | 1872.61
|  | 1724.98 | Baden Sony notebook (replacement) | 2.1.7.11.1.5
|  | 147.63 | memory for above | 2.1.7.11.1.5
|  | 1872.61 | TOTAL
3360 Travel - Foreign | 4342.63
|  | 10 | TRAVELON | 2.1.1.8.6.9
|  | 1138.76 | Skuja 6/2 | 2.1.1.8.6.9
|  | 933.71 | Baden 6/3 | 2.1.1.8.6.9
|  | 1207.07 | Skuja 6/3 | 2.1.1.8.6.9
|  | 605.92 | Skuja 6/19 | 2.1.1.8.6.9
|  | 10 | TRAVELON | 2.1.1.8.6.9
|  | -555.92 | Skuja 6/19 credit? | 2.1.1.8.6.9
|  | 993.09 | Skuja 6/19 | 2.1.1.8.6.9
|  | 4342.63 | TOTAL
SUBTOTAL (for overhead) | 17148.41
9998 Indirect Costs | 8231.2368
|  | 4309.5264 | 1012 Faculty 12 Months | 2.1.7.13.1
|  | 869.2656 | 1020 Graduate Assistants | 2.1.7.1.1.3.1
|  | 69.1296 | 2725 Social Security | 2.1.7.13.1
|  | 898.8528 | 3952 Other (M&S) | 2.1.7.11.1.5
|  | 2084.4624 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 8231.2368 | TOTAL
Subtotal | 25379.6468
4046 Equipment no overhead | 2904
|  | 2904 | DELL ???? | 2.1.7.11.2.2
4348 Construction Equipment | 11079.01
|  | 5.89 | 9715 Touart DKY | 2.1.7.11.1.2
|  | 1948.52 | 9715 5/6/00 ENG | 2.1.7.11.1.1
|  | 1748.4 | 9715 5/20/00 ENG | 2.1.7.11.1.1
|  | 733.68 | 9725 5/6/00 ENG | 2.1.7.11.1.1
|  | 796 | 9725 5/20/00 ENG | 2.1.7.11.1.1
|  | 1042.55 | 9725 Touart misc for universal tester | 2.1.7.11.1.2
|  | 1828.91 | 9715 6/3/00 ENG | 2.1.7.1.1.3.1
|  | 398 | 9725 6/3/00 ENG | 2.1.7.1.1.3.1
|  | 2577.06 | 9725 6/17/00 ENG | 2.1.7.1.1.3.1
11079.01
Total Cost | 39362.6568
Less Payments Previously Requested | 0
Please Remit This Amount | 39362.6568
2.1.1.8.6.9 | 6427.0924
2.1.7.11.1.5 | 2771.4628
2.1.7.1.1.3.1 | 7628.2256
2.1.7.11.1.1 | 5226.6
2.1.7.11.1.2 | 1048.44
2.1.7.13.1 | 13356.836
2.1.7.11.2.2 | 2904
39362.6568

## July 00
Period | 7/1/2000-7/31/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty 12 Months | 2178.09
|  | -1882.52 | Correction for 6/17 Tullio | 2.1.7.13.1
|  | 2027.73 | Tullio 7/1/00 | 2.1.7.13.1
|  | 2032.88 | Tullio 7/15/00 | 2.1.7.13.1
|  | 2178.09 | TOTAL
1020 Graduate Assistants | 664.36
|  | -574.21 | Correction for 6/17 Hongbo | 2.1.7.1.1.3.1
|  | 618.5 | Hongbo 7/1/00 | 2.1.7.1.1.3.1
|  | 620.07 | Hongbo 7/15/00 | 2.1.7.1.1.3.1
|  | 664.36 | TOTAL
2710+2711+2725 Benefits | 129.18
|  | 119.24 | Tullio 7/1/00 | 2.1.7.13.1
|  | 119.24 | Tullio 7/15/00 | 2.1.7.13.1
|  | 17.36 | Hongbo 7/1/00 | 2.1.7.1.1.3.1
|  | 17.36 | Hongbo 7/15/00 | 2.1.7.1.1.3.1
|  | -144.02 | Correction for 6/17 Tullio TIAA? | 2.1.7.13.1
|  | 129.18 | TOTAL
3952 Supplies & Materials | -2585.07
|  | -26.24 | Correction from 3952 Mar-00 overhead charge | 2.1.7.1.1.2
|  | -120.94 | " | 2.1.7.1.1.2
|  | -177 | " | 2.1.7.1.1.2
|  | -2260.89 | " | 2.1.7.1.1.2
|  | -2585.07 | TOTAL
SUBTOTAL (for overhead) | 386.56
9998 Indirect Cost | 1426.3824
|  | 1045.4832 | 1012 Faculty 12 Months | 2.1.7.13.1
|  | 318.8928 | 1020 Graduate Assistants | 2.1.7.1.1.3.1
|  | 62.0064 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 1426.3824 | TOTAL
Total Direct+Indirect | 1812.9424
4061 Supplies non-overhead | 2585.07
|  | 26.24 | Move 3952 Mar-00 to non-overhead equip | 2.1.7.1.1.2
|  | 120.94 | " | 2.1.7.1.1.2
|  | 177 | " | 2.1.7.1.1.2
|  | 2260.89 | " | 2.1.7.1.1.2
|  | 2585.07 | TOTAL
4348 Equipment | 33.25
|  | 33.25 | 9725 McQueen software | 2.1.7.1.1.2
Subtotal | 2618.32
Total Cost | 4431.2624
Less Payments Previously Requested | 0
Please Remit This Amount | 4431.2624
2.1.7.1.1.2 | 33.25
2.1.7.1.1.3.1 | 1017.9728
2.1.7.13.1 | 3380.0396
4431.2624

## Aug 00
Period | 8/1/2000-8/31/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty 12 Months | 6098.64
|  | 2032.88 | Tullio 7/29/00 | 2.1.7.13.1
|  | 2032.88 | Tullio 8/12/00 | 2.1.7.13.1
|  | 2032.88 | Tullio 8/26/00 | 2.1.7.13.1
|  | 6098.64 | TOTAL
1020 Graduate Assistants | 1860.21
|  | 620.07 | 7/29 Hongbo | 2.1.7.1.1.3.1
|  | 620.07 | 8/12 Hongbo | 2.1.7.1.1.3.1
|  | 620.07 | 8/26 Hongbo | 2.1.7.1.1.3.1
|  | 1860.21 | TOTAL
2710+2711+2725 Benefits | 273.2
|  | 119.24 | Tullio 7/1/00 | 2.1.7.13.1
|  | 119.24 | Tullio 7/15/00 | 2.1.7.13.1
|  | 17.36 | Hongbo 7/1/00 | 2.1.7.1.1.3.1
|  | 17.36 | Hongbo 7/15/00 | 2.1.7.1.1.3.1
|  | 273.2 | TOTAL
3360 Travel - Foreign | 1286.25
|  | 1286.25 | Skuja 7/29 | 2.1.1.8.6.9
3728 Freight & Delivery | 52.5
|  | 15.6 | 8/2 UPS | 2.1.7.11.2.2
|  | 36.9 | 8/2 UPS | 2.1.7.11.2.2
|  | 52.5 | TOTAL
SUBTOTAL (for overhead) | 9570.8
9998 Indirect Cost | 4593.984
|  | 2927.3472 | 1012 Faculty 12 Months | 2.1.7.13.1
|  | 892.9008 | 1020 Graduate Assistants | 2.1.7.1.1.3.1
|  | 131.136 | 2710+2711+2725 Benefits | 2.1.7.1.1.3.1
|  | 617.4 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 25.2 | 3728 Freight & Delivery | 2.1.7.11.2.2
|  | 4593.984 | TOTAL
Total Direct+Indirect | 14164.784
4348 Equipment | 5337.07
|  | 489.1 | 9715 7/29/00 ENG | 2.1.7.1.1.4.2 | 2.1.7.1.1.3.2
|  | 2315.76 | 9725 7/1/00 ENG | 2.1.7.11.2.1
|  | 2436.61 | 9725 7/15/00 ENG | 2.1.7.1.1.3.1
|  | 90.3 | 9725 7/29/00 ENG | 2.1.7.1.1.3.1
|  | 3.7 | 9715 | 2.1.7.1.1.3.2
|  | 1.6 | 9725 | 2.1.7.1.1.3.2
|  | 5337.07 | Total
Subtotal | 5337.07
Total Cost | 19501.854
Less Payments Previously Requested | 0
Please Remit This Amount | 19501.854
2.1.1.8.6.9 | 1903.65
2.1.7.1.1.4.2 | 494.4
2.1.7.1.1.3.1 | 5445.8768
2.1.7.11.2.1 | 2315.76
2.1.7.11.2.2 | 77.7
2.1.7.13.1 | 9264.4672
19501.854

## Sept 00
Period | 9/1/2000-9/30/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4065.76
|  | 2032.88 | Tullio 9/9 | 2.1.7.13.1
|  | 2032.88 | Tullio 9/23 | 2.1.7.13.1
|  | 4065.76 | TOTAL
1020 Graduate Assistants | 1240.14
|  | 620.07 | Hongbo 9/9 | 2.1.7.1.1.3.1
|  | 620.07 | Hongbo 9/23 | 2.1.7.1.1.3.1
|  | 1240.14 | TOTAL
2710+2711+2725 Benefits | 657.46
|  | 192.13 | Tullio TIAA 9/9 | 2.1.7.13.1
|  | 192.13 | Tullio TIAA 10/21 | 2.1.7.13.1
|  | 119.24 | Tullio+Honbo Health Ins 9/9 | 2.1.7.1.1.3.1
|  | 119.24 | Tullio+Honbo Health Ins 10/21 | 2.1.7.1.1.3.1
|  | 17.36 | Tullio Retiree Health Ins 9/9 | 2.1.7.13.1
|  | 17.36 | Tullio Retiree Health Ins 10/21 | 2.1.7.13.1
|  | 657.46 | TOTAL
3321 Travel - Domestic | 413.59
|  | 194.28 | Skuja 9/9 | 2.1.1.8.6.9
|  | 219.31 | Skuja 9/23 | 2.1.1.8.6.9
413.59
SUBTOTAL (for overhead) | 6376.95
9998 Indirect Cost | 3060.936
|  | 1951.5648 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 595.2672 | 1020 Graduate Assistants | 2.1.7.1.1.3.1
|  | 315.5808 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 198.5232 | 3321 Travel - Domestic | 2.1.1.8.6.9
|  | 3060.936 | TOTAL
Total Direct+Indirect | 9437.886
4348 Construction Equipment | 5004.52
|  | 653.04 | 9715 8/26/00 ENG | 2.1.7.11.1.1
|  | 1469.6 | 9725 8/26/00 ENG | 2.1.7.1.1.3.1
|  | 1474 | 9725 9/7/2000 Creative Electronics | 2.1.7.1.1.3.2
|  | 1407.88 | 9725 9/12-9/22/00 FPGA etc for HTR demo | 2.1.7.11.2.2
5004.52
Subtotal | 5004.52
Total Cost | 14442.406
Less Payments Previously Requested | 0
Please Remit This Amount | 14442.406
2.1.1.8.6.9 | 612.1132
2.1.7.1.1.3.1 | 3543.4872
2.1.7.1.1.3.2 | 1474
2.1.7.11.1.1 | 653.04
2.1.7.11.2.2 | 1407.88
2.1.7.13.1 | 6751.8856
14442.406

## Oct 00
Period | 10/1/2000-10/31/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4065.76
|  | 2032.88 | Tullio 10/7 | 2.1.7.13.1
|  | 2032.88 | Tullio 10/21 | 2.1.7.13.1
|  | 4065.76 | TOTAL
1020 Graduate Assistants | 1240.14
|  | 620.07 | Hongbo 10/7 | 2.1.7.1.1.3.1
|  | 620.07 | Hongbo 10/21 | 2.1.7.1.1.3.1
|  | 1240.14 | TOTAL
2710+2711+2725 Benefits | 657.46
|  | 192.13 | Tullio TIAA 10/7 | 2.1.7.13.1
|  | 192.13 | Tullio TIAA 10/21 | 2.1.7.13.1
|  | 119.24 | Tullio+Honbo Health Ins 10/7 | 2.1.7.1.1.3.1
|  | 119.24 | Tullio+Honbo Health Ins 10/21 | 2.1.7.1.1.3.1
|  | 17.36 | Tullio Retiree Health Ins 10/7 | 2.1.7.13.1
|  | 17.36 | Tullio Retiree Health Ins 10/21 | 2.1.7.13.1
|  | 657.46 | TOTAL
3952 Other Supplies | 640
|  | 640 | ALDEC licenses | 2.1.7.11.1.2
3321 Travel - Domestic | 0
3360 Travel - Foreign | 1402.19
|  | 1402.19 | Tullio to CERN 10/2000 | 2.1.1.8.6.9
SUBTOTAL (for overhead) | 8005.55
9998 Indirect Cost | 3842.664
|  | 1951.5648 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 595.2672 | 1020 Graduate Assistants | 2.1.7.13.1
|  | 315.5808 | 2710+2711+2725 Benefits | 2.1.7.1.1.3.1
|  | 307.2 | 3952 Other Supplies | 2.1.7.1.1.3.1
|  | 673.0512 | 3360 Travel - Foreign | 2.1.1.8.6.9
3842.664
Total Direct+Indirect | 11848.214
3734 Subcontracts>$25k | 20241.08
|  | 3529.41 | CPU 5/11/00 6000CHF | 2.1.1.5.1.5
|  | 3511.76 | Monitor 5/11/00 5970 CHF | 2.1.1.5.1.5
|  | 218.24 | Hostel (Baden) 5/22/00 CERN | 2.1.1.8.6.9
|  | 2352.94 | 4000 CHF DaSilva | 2.1.7.13.1
|  | 2395.21 | 4000 CHF DaSilva | 2.1.7.13.1
|  | 4790.42 | 8000 CHF DaSilva | 2.1.7.13.1
|  | 2395.2 | 4000 CHF DaSilva | 2.1.7.13.1
|  | 1047.9 | LHC Module + TTCrx test board | 2.1.7.11.1.5
20241.08
Equipment | 293.34
|  | 293.34 | parts for FEE | 2.1.7.11.2.2
Subtotal | 20534.42
Total Cost | 32382.634
Less Payments Previously Requested | 0
Please Remit This Amount | 32382.634
2.1.1.5.1.5 | 7041.17
2.1.1.8.6.9 | 2293.4812
2.1.7.1.1.3.1 | 2101.4008
2.1.7.11.1.2 | 640
2.1.7.11.1.5 | 1047.9
2.1.7.11.2.2 | 293.34
2.1.7.13.1 | 18965.342
32382.634

## Nov 00
Period | 11/1/2000-11/30/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4089
|  | 2032.88 | Tullio 11/4 | 2.1.7.13.1
|  | 2056.12 | Tullio 11/18 | 2.1.7.13.1
|  | 4089 | TOTAL
1020 Graduate Assistants | 1240.14
|  | 620.07 | Hongbo 11/4 | 2.1.7.1.1.3.1
|  | 620.07 | Hongbo 11/18 | 2.1.7.1.1.3.1
|  | 1240.14 | TOTAL
2710+2711+2725 Benefits | 665.14
|  | 192.13 | Tullio TIAA 11/4 | 2.1.7.13.1
|  | 199.81 | Tullio TIAA 11/18 | 2.1.7.13.1
|  | 119.24 | Tullio+Honbo Health Ins 11/4 | 2.1.7.1.1.3.1
|  | 119.24 | Tullio+Honbo Health Ins 11/18 | 2.1.7.1.1.3.1
|  | 17.36 | Tullio Retiree Health Ins 11/4 | 2.1.7.13.1
|  | 17.36 | Tullio Retiree Health Ins 11/8 | 2.1.7.13.1
|  | 665.14 | TOTAL
3321 Travel - Domestic | 2288.26
|  | 469.21 | Baden 11/4 reimbursement | 2.1.1.8.6.9
|  | 225.37 | Grassi 11/4 remibursement | 2.1.1.8.6.9
|  | 479.18 | Skuja 11/4 reimbursement | 2.1.1.8.6.9
|  | 10 | 11/03 TRAVELON | 2.1.1.8.6.9
|  | 175.5 | 10/12 Southwest SKUJA | 2.1.1.8.6.9
|  | 261 | 10/12 Soutwest BADEN | 2.1.1.8.6.9
|  | 261 | 10/12 Soutwest GRASSI | 2.1.1.8.6.9
|  | 10 | 11/3 OMEGA | 2.1.1.8.6.9
|  | 173 | 10/30 Southwest KUNORI | 2.1.1.8.6.9
|  | 214 | 11/21 Southwest SKUJA | 2.1.1.8.6.9
|  | 10 | 12/1 OMEGA | 2.1.1.8.6.9
2288.26
3360 Travel - Foreign | 2936.92
|  | 1003.71 | 11/18 SKUJA reimbursement | 2.1.1.8.6.9
|  | 1783.21 | 10/22 SKUJA Barcelona | 2.1.1.8.6.9
|  | 150 | 12/1 TCRD12 | 2.1.1.8.6.9
2936.92
SUBTOTAL (for overhead) | 11219.46
9998 Indirect Cost | 5385.3408
|  | 1962.72 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 595.2672 | 1020 Graduate Assistants | 2.1.7.13.1
|  | 319.2672 | 2710+2711+2725 Benefits | 2.1.7.1.1.3.1
|  | 1098.3648 | 3321 Travel - Domestic | 2.1.1.8.6.9
|  | 1409.7216 | 3360 Travel - Foreign | 2.1.1.8.6.9
5385.3408
Total Direct+Indirect | 16604.8008
4348 Construction Equipment | 5651.42
|  | 2459.5 | 9715 11/4 optical parts | 2.1.7.1.1.5.2 | 2.1.7.11.2.2
|  | 33 | 9715 surcharge for above | 2.1.7.11.2.2
|  | 2099.86 | 9725 11/09 HTR stuff | 2.1.7.1.1.3.1
|  | 1059.06 | 9725 11/14 VME stuff | 2.1.7.11.1.1
5651.42
Subtotal | 5651.42
Total Cost | 22256.2208
Less Payments Previously Requested | 0
Please Remit This Amount | 22256.2208
2.1.1.8.6.9 | 7733.2664
2.1.7.1.1.3.1 | 3897.7472
2.1.7.11.1.1 | 1059.06
2.1.7.1.1.5.2 | 2492.5
2.1.7.11.2.2
2.1.7.13.1 | 7073.6472
22256.2208

## Dec 00
Period | 11/1/2000-11/30/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4228.4
|  | 2114.2 | Tullio 12/2 | 2.1.7.13.1
|  | 2114.2 | Tullio 12/16 | 2.1.7.13.1
|  | 4228.4 | TOTAL
2710+2711+2725 Benefits | 672.82
|  | 199.81 | Tullio TIAA 12/2 | 2.1.7.13.1
|  | 199.81 | Tullio TIAA 12/16 | 2.1.7.13.1
|  | 119.24 | Tullio Health Ins 12/2 | 2.1.7.1.1.3.1
|  | 119.24 | Tullio Health Ins 12/16 | 2.1.7.1.1.3.1
|  | 17.36 | Tullio Retiree Health Ins 12/2 | 2.1.7.13.1
|  | 17.36 | Tullio Retiree Health Ins 12/16 | 2.1.7.13.1
|  | 672.82 | TOTAL
3321 Travel - Domestic | 1068.64
|  | 489.54 | Skuja 12/2 reimbursement | 2.1.1.8.6.9
|  | 579.1 | Skuja 12/16 remibursement | 2.1.1.8.6.9
1068.64
SUBTOTAL (for overhead) | 5969.86
9998 Indirect Cost | 2865.5328
|  | 2029.632 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 322.9536 | 2710+2711+2725 Benefits | 2.1.7.1.1.3.1
|  | 512.9472 | 3321 Travel - Domestic | 2.1.1.8.6.9
2865.5328
Total Direct+Indirect | 8835.3928
4348 Construction Equipment | 20372.52
|  | 136.06 | 9715 9/23/00 ENG | 2.1.7.1.1.3.1
|  | 7424.78 | 9725 9/9/00 and 9/23/00 ENG | 2.1.7.1.1.3.1
|  | 625.84 | 9715 10/7/00 ENG | 2.1.7.11.2.1
|  | 7189.94 | 9725 10/7/00 and 10/21/00 ENG | 2.1.7.11.2.1
|  | 3875.1 | 9715 VME CPU | 2.1.7.1.1.4.2 | 2.1.7.1.1.3.2
|  | 1120.8 | 9725 Misc WYLE | 2.1.7.11.2.2
20372.52
Subtotal | 20372.52
Total Cost | 29207.9128
Less Payments Previously Requested | 0
Please Remit This Amount | 29207.9128
2.1.1.8.6.9 | 1581.5872
2.1.7.1.1.3.1 | 8122.2736
2.1.7.1.1.4.2 | 3875.1
2.1.7.11.2.1 | 7815.78
2.1.7.11.2.2 | 1120.8
2.1.7.13.1 | 6692.372
29207.9128

## Jan 01
Period | 1/1/2001-1/31/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 6342.6
|  | 2114.2 | Tullio 12/30 | 2.1.7.13.1
|  | 2114.2 | Tullio 1/13 | 2.1.7.13.1
|  | 2114.2 | Tullio 1/27 | 2.1.7.13.1
|  | 6342.6 | TOTAL
2705+2710+2711+2725 Benefits | 924.05
|  | 199.81 | Tullio TIAA 12/30 | 2.1.7.13.1
|  | 199.81 | Tullio TIAA 1/13 | 2.1.7.13.1
|  | 199.81 | Tullio TIAA 1/27 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 1/13 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 1/27 | 2.1.7.13.1
|  | 20.63 | Tullio Retiree Health Ins 12/2 | 2.1.7.13.1
|  | 20.63 | Tullio Retiree Health Ins 12/16 | 2.1.7.13.1
|  | 924.05 | TOTAL
3321 Travel - Domestic | 690.5
|  | 415 | American Airlines 2/2 | 2.1.1.8.6.9
|  | 10 | Omega World 2/2 | 2.1.1.8.6.9
|  | 265.5 | Southwest Airlines 2/2 | 2.1.1.8.6.9
690.5
3360 Travel - Foreign | 808.98
|  | 10 | Omega World 2/2 | 2.1.1.8.6.9
|  | 798.98 | United Airlines | 2.1.1.8.6.9
808.98
3728 Freight & Delivery | 68.55
|  | 31.97 | UPS 1/2 | 2.1.7.11.1.5
|  | 36.58 | UPS 1/2 | 2.1.7.11.1.5
68.55
SUBTOTAL (for overhead) | 8834.68
9998 Indirect Cost | 4240.6464
|  | 3044.448 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 443.544 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 331.44 | 3321 Travel - Domestic | 2.1.1.8.6.9
|  | 388.3104 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 32.904 | 3724+3728 | 2.1.7.11.1.5
4240.6464
Total Direct+Indirect | 13075.3264
4348 Construction Equipment | 32285.27
|  | 975.42 | Misc for FEE/HTR 12/21 + surcharge | 2.1.7.1.1.1 | 2.1.7.1.1.3.1
|  | 12394.37 | 9725 11/4, 11/18, 12/2 ENG | 2.1.7.12.1
|  | 6067.04 | 9725 12/30 ENG | 2.1.7.12.1
|  | 1210.61 | Limo connectors + surcharge 1/11 | 2.1.7.11.1.2
|  | 161.03 | caps + surcharge BREDEN 1/08 | 2.1.7.11.1.2
|  | 4488.28 | 9725 1/13 ENG | 2.1.7.1.1.4.2 | 2.1.7.11.1.1
|  | 136.68 | 9725 1/27 MDG | 2.1.7.11.1.1
|  | 6851.84 | 9725 1/27 ENG | 2.1.7.11.1.1
32285.27
Subtotal | 32285.27
Total Cost | 45360.5964
Less Payments Previously Requested | 0
Please Remit This Amount | 45360.5964
|  | 2.1.1.8.6.9 | Travel | 2219.2304
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG | 975.42
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.11.1.1 | Universal Tester ENG | 13055.56
|  | 2.1.7.11.1.2 | Universal Tester M&S | 1371.64
|  | 2.1.7.11.1.5 | TTC Setup | 101.454
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.1.1.4.2 | PrototypeM&S | 4488.28
|  | 2.1.7.12.1 | Demonstrator Integration | 12394.37
|  | 2.1.7.13.1 | Integration | 10754.642
45360.5964
Note on F48: Drew Baden: changed sep 01 due to overruns in this WBS

## Feb 01
Period | 2/1/2001-2/28/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4228.4
|  | 2114.2 | Tullio 2/10 | 2.1.7.13.1
|  | 2114.2 | Tullio 2/24 | 2.1.7.13.1
|  | 4228.4 | TOTAL
2705+2710+2711+2725 Benefits | 724.24
|  | 199.81 | Tullio TIAA 2/10 | 2.1.7.13.1
|  | 199.81 | Tullio TIAA 2/24 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 2/10 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 2/24 | 2.1.7.13.1
|  | 20.63 | Tullio Retiree Health Ins 12/2 | 2.1.7.13.1
|  | 20.63 | Tullio Retiree Health Ins 12/16 | 2.1.7.13.1
|  | 724.24 | TOTAL
3321 Travel - Domestic | 1495.53
|  | 337.2 | Skuja 2/10 | 2.1.1.8.6.9
|  | 345.71 | Skuja 2/10 | 2.1.1.8.6.9
|  | 259.62 | Baden 2/24 | 2.1.1.8.6.9
|  | 155.25 | Grassi 2/24 | 2.1.1.8.6.9
|  | 397.75 | Skuja 2/24 | 2.1.1.8.6.9
1495.53
3360 Travel - Foreign | 2329.84
|  | 943.84 | Baden 2/10 | 2.1.1.8.6.9
|  | 1386 | Grassi 2/10 | 2.1.1.8.6.9
2329.84
3724+3728 | 272.05
|  | 340.6 | CERN | 2.1.7.11.1.5
|  | -31.97 | Credit from UPS | 2.1.7.11.1.5
|  | -36.58 | Credit from UPS | 2.1.7.11.1.5
272.05
SUBTOTAL (for overhead) | 9050.06
9998 Indirect Cost | 4344.0288
|  | 2029.632 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 347.6352 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 717.8544 | 3321 Travel - Domestic | 2.1.1.8.6.9
|  | 1118.3232 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 130.584 | 3724+3728 | 2.1.7.11.1.5
4344.0288
Total Direct+Indirect | 13394.0888
4348 Construction Equipment | 19406.62
|  | 1842.27 | Misc for FEE/HTR | 2.1.7.1.1.3.2
|  | 5399.06 | 9725 2/10/01 ENG | 2.1.7.11.1.1
|  | 5684.03 | Misc for FEE/HTR | 2.1.7.11.2.2
|  | 6481.26 | 9725 2/24/01 ENG | 2.1.7.11.2.1
19406.62
38813.24
Subtotal | 19406.62
Total Cost | 32800.7088
Less Payments Previously Requested | 0
Please Remit This Amount | 32800.7088
|  | 2.1.1.8.6.9 | Travel | 5661.5476
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG | 5684.03
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S | 1842.27
|  | 2.1.7.11.1.1 | Universal Tester ENG | 5399.06
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup | 402.634
|  | 2.1.7.11.2.1 | FEE ENG | 6481.26
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.13.1 | Integration | 7329.9072
32800.7088

## Mar 01
Period | 3/1/2001-3/31/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 1748.12
|  | 2114.2 | Tullio 3/10 | 2.1.7.13.1
|  | 2114.2 | Tullio 3/24 | 2.1.7.13.1
|  | -620.07 | HongBo 3/7 credit | 2.1.7.1.1.3.1
|  | -620.07 | HongBo 3/7 credit | 2.1.7.1.1.3.1
|  | -620.07 | HongBo 3/7 credit | 2.1.7.1.1.3.1
|  | -620.07 | HongBo 3/7 credit | 2.1.7.1.1.3.1
|  | 1748.12 | TOTAL
2705+2710+2711+2725 Benefits | 724.24
|  | 199.81 | Tullio TIAA 3/10 | 2.1.7.13.1
|  | 199.81 | Tullio TIAA 3/24 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 3/10 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 3/24 | 2.1.7.13.1
|  | 20.63 | Tullio Retiree Health Ins 3/10 | 2.1.7.13.1
|  | 20.63 | Tullio Retiree Health Ins 3/24 | 2.1.7.13.1
|  | 724.24 | TOTAL
3321 Travel - Domestic | 3220.36
|  | 474.5 | Kunori 3/10 | 2.1.1.8.6.9
|  | 150.26 | Skuja 3/10 | 2.1.1.8.6.9
|  | 1271.5 | Northwest Airlines 3/2 | 2.1.1.8.6.9
|  | 10 | Omega World 3/2 | 2.1.1.8.6.9
|  | 544.5 | American Airlines 3/2 | 2.1.1.8.6.9
|  | 10 | Travel-ON 3/2 | 2.1.1.8.6.9
|  | 369.8 | Continental Airlines 3/2 | 2.1.1.8.6.9
|  | 10 | Travel-ON 3/2 | 2.1.1.8.6.9
|  | 369.8 | Continental Airlines 3/2 | 2.1.1.8.6.9
|  | 10 | Travel-ON 3/2 | 2.1.1.8.6.9
3220.36
3360 Travel - Foreign | 3164.57
|  | 673.67 | Grassi 3/24 | 2.1.1.8.6.9
|  | 868.13 | Skuja 3/24 | 2.1.1.8.6.9
|  | 724.08 | American Airlines 3/2 | 2.1.1.8.6.9
|  | 10 | Travel-ON 3/2 | 2.1.1.8.6.9
|  | 10 | Omega World 3/2 | 2.1.1.8.6.9
|  | 878.69 | United Airlines 3/2 | 2.1.1.8.6.9
3164.57
SUBTOTAL (for overhead) | 8857.29
9998 Indirect Cost | 4251.4992
|  | 839.0976 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 347.6352 | 2710+2711+2725 Benefits | 2.1.7.12.1
|  | 1545.7728 | 3321 Travel - Domestic | 2.1.1.8.6.9
|  | 1518.9936 | 3360 Travel - Foreign | 2.1.1.8.6.9
4251.4992
Total Direct+Indirect | 13108.7892
4348 Construction Equipment | 11449.94
|  | 2.31 | Misc for FEE/HTR 3/2 | 2.1.7.1.1.3.2
|  | 7360.48 | 9725 2/24 ENG | 2.1.7.12.1
|  | 4087.15 | 9725 3/10 ENG | 2.1.7.11.2.1
11449.94
Subtotal | 11449.94
Total Cost | 24558.7292
Less Payments Previously Requested | 0
Please Remit This Amount | 24558.7292
|  | 2.1.1.8.6.9 | Travel | 9449.6964
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG | -2480.28
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S | 2.31
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG | 4087.15
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration | 7708.1152
|  | 2.1.7.13.1 | Integration | 5791.7376
24558.7292

## Apr 01
Period | 4/1/2001-4/30/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4228.4
|  | 2114.2 | Tullio 4/7 | 2.1.7.13.1
|  | 2114.2 | Tullio 4/21 | 2.1.7.13.1
|  | 4228.4 | TOTAL
2705+2710+2711 Benefits | 724.24
|  | 199.81 | Tullio TIAA 4/7 | 2.1.7.13.1
|  | 199.81 | Tullio TIAA 4/21 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 4/7 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 4/21 | 2.1.7.13.1
|  | 20.63 | Tullio Retiree Health Ins 4/7 | 2.1.7.13.1
|  | 20.63 | Tullio Retiree Health Ins 4/21 | 2.1.7.13.1
|  | 724.24 | TOTAL
3321 Travel - Domestic | 1505.05
|  | 238.5 | Tullio 4/21 | 2.1.1.8.6.9
|  | 673.18 | Skuja 4/21 | 2.1.1.8.6.9
|  | 10 | Omega World 4/7 | 2.1.1.8.6.9
|  | 192.01 | US Airways 4/7 | 2.1.1.8.6.9
|  | 10 | Omega World 4/7 | 2.1.1.8.6.9
|  | 381.36 | US Airways 4/7 | 2.1.1.8.6.9
1505.05
3360 Travel - Foreign | 959.41
|  | 387.2 | Kunori 4/7 | 2.1.1.8.6.9
|  | 562.21 | Delta 4/7 | 2.1.1.8.6.9
|  | 10 | Travel-ON 4/7 | 2.1.1.8.6.9
959.41
3914 Purchases | 46.83
|  | 46.83 | Arrow, Hamilton 4/18 | 2.1.7.1.1.3.2
3724 General | 4006.33
|  | 4006.33 | SKUJA 4/11 CERN S-LINK cards | 2.1.7.11.1.5
SUBTOTAL (for overhead) | 11470.26
9998 Indirect Cost | 5505.7248
|  | 2029.632 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 347.6352 | 2710+2711+2725 Benefits | 2.1.7.1.1.4.1 | 2.1.7.12.1
|  | 722.424 | 3321 Travel - Domestic | 2.1.1.8.6.9 | 1182.9408
|  | 460.5168 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 22.4784 | 3914 Purchases | 2.1.7.1.1.3.2
|  | 1923.0384 | 3724 General | 2.1.7.11.1.5
5505.7248
Total Direct+Indirect | 16975.9848
4348 Construction Equipment | 15084.46
|  | 2512.18 | Misc for FEE/HTR | 2.1.7.1.1.3.2
|  | 4988.12 | 9725 4/7 ENG | 2.1.7.1.1.4.1 | 2.1.7.12.1
|  | 7584.16 | 9725 4/21 ENG | 2.1.7.11.2.1
15084.46
Subtotal | 15084.46
Total Cost | 32060.4448
Less Payments Previously Requested | 0
Please Remit This Amount | 32060.4448
|  | 2.1.1.8.6.9 | Travel | 3647.4008
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S | 2581.4884
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG | 5335.7552
|  | 2.1.7.1.1.4.2 | PrototypeM&S | 5929.3684
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG | 7584.16
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 6982.272
|  |  |  | 32060.4448 | 0

## May 01
Period | 5/1/2001-5/31/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4228.4
|  | 2114.2 | Tullio 5/5 | 2.1.7.13.1
|  | 2114.2 | Tullio 5/19 | 2.1.7.13.1
|  | 4228.4 | TOTAL
2705+2710+2711 Benefits | 724.24
|  | 199.81 | Tullio TIAA 5/5 | 2.1.7.13.1
|  | 199.81 | Tullio TIAA 5/19 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 5/5 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 5/19 | 2.1.7.13.1
|  | 20.63 | Tullio Retiree Health Ins 5/5 | 2.1.7.13.1
|  | 20.63 | Tullio Retiree Health Ins 5/19 | 2.1.7.13.1
|  | 724.24 | TOTAL
3321 Travel - Domestic | 1958.63
|  | 593.82 | Baden 5/5 | 2.1.1.8.6.9
|  | 157.45 | Skuja 5/5 | 2.1.1.8.6.9
|  | 10 | Omega World 5/5 | 2.1.1.8.6.9
|  | 100 | Skuja 5/5 | 2.1.1.8.6.9
|  | 97.6 | Skuja 5/5 | 2.1.1.8.6.9
|  | 160.41 | Skuja 5/19 | 2.1.1.8.6.9
|  | 199.6 | Baden 5/19 | 2.1.1.8.6.9
|  | 279.22 | US Airways 5/5 | 2.1.1.8.6.9
|  | 360.53 | US Airways 5/5 | 2.1.1.8.6.9
1958.63
3360 Travel - Foreign | 4769.68
|  | 807.41 | American Airlines 5/5 | 2.1.1.8.6.9
|  | 1757.55 | American Airlines 5/5 | 2.1.1.8.6.9
|  | 2184.72 | United Airlines 6/1 | 2.1.1.8.6.9
|  | 10 | Travel-ON 5/5 | 2.1.1.8.6.9
|  | 10 | Travel-ON 5/5 | 2.1.1.8.6.9
4769.68
3914 Purchases | -1053.33
|  | -1053.33 | Credit | 2.1.7.1.1.3.2
3724 General | 9893.44
|  | 2677.36 | SKUJA 5/8 CERN computer for Sarma | 2.1.1.5.1.5
|  | 7216.08 | SKUJA 5/29 CERN (credit next month) | 2.1.1.5.1.5
9893.44
SUBTOTAL (for overhead) | 20521.06
9998 Indirect Cost | 9850.1088
|  | 2029.632 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 347.6352 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 940.1424 | 3321 Travel - Domestic | 2.1.1.8.6.9
|  | -505.5984 | Credit | 2.1.7.1.1.3.2
|  | 2289.4464 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 4748.8512 | 3724 General
9850.1088
Total Direct+Indirect | 30371.1688
4348 Construction Equipment | 11584.01
|  | 896.55 | Misc for FEE/HTR | 2.1.7.1.1.3.2
|  | 6986.6 | 9725 4/7 ENG | 2.1.7.11.1.1
|  | 3700.86 | 9725 4/21 ENG | 2.1.7.11.1.1
11584.01
Subtotal | 11584.01
Total Cost | 41955.1788
Less Payments Previously Requested | 0
Please Remit This Amount | 41955.1788
|  | 2.1.1.8.6.9 | Travel | 9957.8988
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S | -662.3784
|  | 2.1.7.11.1.1 | Universal Tester ENG | 10687.46
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 7329.9072
|  | 2.1.1.5.1.5 | Computing in building 186 | 14642.2912
|  |  |  | 41955.1788 | 0

## Jun 01
Period | 6/1/2001-6/30/2000
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 6342.6
|  | 2114.2 | Tullio 6/2 | 2.1.7.13.1 | 7940.7328
|  | 2114.2 | Tullio 6/16 | 2.1.7.13.1
|  | 2114.2 | Tullio 5/30 | 2.1.7.13.1
|  | 6342.6 | TOTAL
2705+2710+2711 Benefits | 524.43
|  | 199.81 | Tullio TIAA 6/2 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 6/2 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 6/16 | 2.1.7.13.1
|  | 20.63 | Tullio Retiree Health Ins 6/2 | 2.1.7.13.1
|  | 20.63 | Tullio Retiree Health Ins 6/16 | 2.1.7.13.1
|  | 524.43 | TOTAL
2075 Student (Other) | 1360
|  | 1360 | Anil for firmware | 2.1.7.1.1.4.1
1020 Graduate Assistants | -4341.92
|  | -631.83 | WANG 6/11 | 2.1.7.1.1.3.1
|  | -3710.09 | WANG 6/11 | 2.1.7.1.1.3.1
-4341.92
3321 Travel - Domestic | 781.61
|  | 112 | Grassi 6/2 | 2.1.1.8.6.9
|  | 228.31 | Skuja 6/2 | 2.1.1.8.6.9
|  | 89.13 | Skuja 6/2 | 2.1.1.8.6.9
|  | 222.67 | Skuja 6/16 | 2.1.1.8.6.9
|  | 129.5 | Skuja 6/16 | 2.1.1.8.6.9
781.61
3360 Travel - Foreign | 3293.96
|  | 315.7 | Kunori 6/2 | 2.1.1.8.6.9
|  | 2978.26 | United Airlines 6/27 | 2.1.1.8.6.9
3293.96
3724 General | -7216.08
|  | -7216.08 | SKUJA 6/20 CERN | 2.1.1.5.1.5
-7216.08
SUBTOTAL (for overhead) | 744.6
9998 Indirect Cost | 357.408
|  | 3044.448 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 251.7264 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | -2084.1216 | 1020 Graduate Assistants | 2.1.7.1.1.3.1
|  | 652.8 | 2075 Student (Other) | 2.1.7.1.1.4.1
|  | 375.1728 | 3321 Travel - Domestic | 2.1.1.8.6.9
|  | 1581.1008 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | -3463.7184 | 3724 General | 2.1.1.5.1.5
357.408
Total Direct+Indirect | 1102.008
4348 Construction Equipment | 23394.45
|  | 5981.96 | Misc for FEE/HTR | 2.1.7.1.1.3.2
|  | 9493.06 | 9725 6/2 ENG | 2.1.7.11.1.1
|  | 7833.26 | 9725 6/16 ENG | 2.1.7.11.1.1
|  | 86.17 | Misc for FEE/HTR | 2.1.7.1.1.3.2
23394.45
Subtotal | 23394.45
Total Cost | 24496.458
Less Payments Previously Requested | 0
Please Remit This Amount | 24496.458
|  | 2.1.1.5.1.5 | Computing in building 186 | -10679.7984
|  | 2.1.1.8.6.9 | Travel | 6031.8436
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG | -6426.0416
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S | 6068.13
|  | 2.1.7.11.1.1 | Universal Tester ENG | 17326.32
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG | 2012.8
|  | 2.1.7.1.1.4.2 | Prototype M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 10163.2044
|  |  |  | 24496.458 | 0

## Jul 01
Period | 7/1/2001-7/31/2001
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4376.38
|  | 2188.19 | Tullio 7/14 | 2.1.7.13.1
|  | 2188.19 | Tullio 7/28 | 2.1.7.13.1
|  | 4376.38 | TOTAL
2705+2710+2711 Benefits | 325.1
|  | 141.68 | Tullio Health Ins 7/14 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 7/28 | 2.1.7.13.1
|  | 20.87 | Tullio Retiree Health Ins 7/14 | 2.1.7.13.1
|  | 20.87 | Tullio Retiree Health Ins 7/28 | 2.1.7.13.1
|  | 325.1 | TOTAL
2075 Student (Other) | 2720
|  | 1360 | Anil 7/14
|  | 1360 | Anil 7/28
|  | 2720 | TOTAL | 2.1.7.1.1.4.1
3311 In-State Travel | 36
|  | 36 | MO Pool usechg 7/30
3321 Travel - Domestic | 149
|  | 149 | Grassi 7/28 | 2.1.1.8.6.9
149
3360 Travel - Foreign | 4731.97
|  | 1119.73 | Kunori 7/14 | 2.1.1.8.6.9
|  | 2480.37 | Skuja 7/14 | 2.1.1.8.6.9
|  | 1121.87 | American Airlines 8/3 | 2.1.1.8.6.9
|  | 10 | Omega | 2.1.1.8.6.9
4731.97
SUBTOTAL (for overhead) | 12338.45
9998 Indirect Cost | 5922.456
|  | 2100.6624 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 156.048 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 1305.6 | 2075 Student (Other) | 2.1.7.1.1.4.1
|  | 17.28 | 3311 In-State Travel | 2.1.1.8.6.9
|  | 71.52 | 3321 Travel - Domestic | 2.1.1.8.6.9
|  | 2271.3456 | 3360 Travel - Foreign | 2.1.1.8.6.9
5922.456
Total Direct+Indirect | 18260.906
4348 Construction Equipment | 14781.03
|  | 3008.09 | 9725 6/30 ENG | 2.1.7.1.1.4.1
|  | 2025.13 | 9725 7/14 ENG+MACHINE SHOP | 2.1.7.1.1.4.1
|  | 3411.5 | 9725 7/28 ENG | 2.1.7.1.1.4.1
|  | 6315.81 | FEE/HTR CR charges | 2.1.7.1.1.4.2
|  | 20.5 | Misc FEE/HTR | 2.1.7.1.1.4.2
14781.03
Subtotal | 14781.03
Total Cost | 33041.936
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel | 7277.1156
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG | 12470.32
|  | 2.1.7.1.1.4.2 | PrototypeM&S | 6336.31
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 6958.1904
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 33041.936
|  |  | Check | 0

## Aug 01
Period | 8/1/2001-8/31/2001
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4376.38
|  | 2188.19 | Tullio 8/11 | 2.1.7.13.1
|  | 2188.19 | Tullio 8/25 | 2.1.7.13.1
|  | 4376.38 | TOTAL
2705+2710+2711 Benefits | 408.49
|  | 141.68 | Tullio Health Ins 8/11 | 2.1.7.13.1
|  | 225.07 | Tullio Health Ins 8/25 | 2.1.7.13.1
|  | 20.87 | Tullio Retiree Health Ins 8/11 | 2.1.7.13.1
|  | 20.87 | Tullio Retiree Health Ins 8/25 | 2.1.7.13.1
|  | 408.49 | TOTAL
2075 Student (Other) | 2720
|  | 1360 | Anil 8/11 | 2.1.7.1.1.4.1
|  | 1360 | Anil 8/25 | 2.1.7.1.1.4.1
|  | 2720 | TOTAL
3360 Travel - Foreign | 1325.72
|  | 1060.47 | Skuja 8/25 | 2.1.1.8.6.9
|  | 265.25 | Skuja 8/25 | 2.1.1.8.6.9
1325.72
3724 General | 10759.63
|  | 8086.74 | mistake, credit given 9/01 | 2.1.1.5.1.5
|  | 2672.89 | mistake, credit given 9/01 | 2.1.1.5.1.5
10759.63
SUBTOTAL (for overhead) | 19590.22
9998 Indirect Cost | 9403.3056
|  | 2100.6624 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 196.0752 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 5164.6224 | 3724 General | 2.1.1.5.1.5
|  | 1305.6 | 2075 Student (Other) | 2.1.7.1.1.4.1
|  | 636.3456 | 3360 Travel - Foreign | 2.1.1.8.6.9
9403.3056
Total Direct+Indirect | 28993.5256
4348 Construction Equipment | 20845.63
|  | 1346.81 | TI Eval board + books + misc | 2.1.7.1.1.4.2
|  | 1355 | HTR demo boards | 2.1.7.1.1.4.2
|  | 615.7 | Misc FEE/HTR | 2.1.7.1.1.4.1
|  | 10.04 | EDM work from MDG | 2.1.7.1.1.4.1
|  | 206 | 9725 8/11 MDG | 2.1.7.1.1.4.1
|  | 8987.78 | 9725 8/11 EDG | 2.1.7.1.1.4.1
|  | 8324.3 | 9725 9/8 EDG | 2.1.7.1.1.4.1
20845.63
Subtotal | 20845.63
Total Cost | 49839.1556
|  | 2.1.1.5.1.5 | Computing in building 186 | 15924.2524
|  | 2.1.1.8.6.9 | Travel | 1962.0656
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S | 2701.81
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG | 22169.42
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 7081.6076
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 49839.1556
|  |  | Check | 0

## Sep 01
Period | 9/1/2001-9/30/2001
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4376.38
|  | 2188.19 | Tullio 9/8 | 2.1.7.13.1
|  | 2188.19 | Tullio 9/22 | 2.1.7.13.1
|  | 4376.38 | TOTAL
2705+2710+2711 Benefits | 822.09
|  | 206.8 | Tullio 9/8 TIAA Optional | 2.1.7.13.1
|  | 206.8 | Tullio 9/22 TIAA Optional | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 9/22 | 2.1.7.13.1
|  | 225.07 | Tullio Health Ins 9/8 | 2.1.7.13.1
|  | 20.87 | Tullio Retiree Health Ins 9/8 | 2.1.7.13.1
|  | 20.87 | Tullio Retiree Health Ins 9/22 | 2.1.7.13.1
|  | 822.09 | TOTAL
1020 Graduate Assistants | 1816.71
|  | 1211.14 | Adarsh 9/8 | 2.1.7.1.1.4.1
|  | 605.57 | Adarsh 9/22 | 2.1.7.1.1.4.1
|  | 1816.71 | TOTAL
2075 Student (Other) | 680
|  | 680 | Anil 9/8 | 2.1.7.1.1.4.1
|  | 680 | TOTAL
2775 Tuition Waiver GA | 2890
|  | 2890 | FALL01 Tuition Waiver Adarsh | 2.1.7.1.1.2 | 2.1.7.11.1.1 | 2.1.7.12.1
3321 Travel - Out-of-State | 230.3
|  | 230.3 | Skuja 9/8 | 2.1.1.8.6.9
3360 Travel - Foreign | 4.5
|  | 4.5 | United Airlines? | 2.1.1.8.6.9
4.5
3724 General | -10759.63
|  | -8086.74 | mistake, credit given 9/01 | 2.1.1.5.1.5
|  | -2672.89 | mistake, credit given 9/01 | 2.1.1.5.1.5
-10759.63
3728 Freight & Delivery | 23.9
|  | 23.9 | Breden 9/20 | 2.1.7.1.1.4.2
SUBTOTAL (for overhead) | 84.25
9998 Indirect Cost | -1346.76
|  | 2100.6624 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 394.6032 | 2710+2711+2725 Benefits | 2.1.7.13.1 | 1
|  | 872.0208 | 1020 Graduate Assistants | 2.1.7.1.1.4.1
|  | 326.4 | 2075 Student (Other) | 2.1.7.1.1.4.1
|  | 11.472 | 3728 Freight & Delivery | 2.1.7.1.1.4.2
|  | 110.544 | 3321 Travel - Out-of-State | 2.1.1.8.6.9 | 1
|  | 2.16 | 3360 Travel - Foreign | 2.1.1.8.6.9 | 1
|  | -5164.6224 | 3724 General | 2.1.1.5.1.5
|  | -1346.76 | Total
Total Direct+Indirect | -1262.51
4348 Construction Equipment | 1073.56
|  | 1073.56 | Books + HTR board assembly | 2.1.7.1.1.4.2
1073.56
Subtotal | 1073.56
Total Cost | -188.95
|  | 2.1.1.5.1.5 | Computing in building 186 | -15924.2524
|  | 2.1.1.8.6.9 | Travel | 347.504
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report | 351.2752 | 2890
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG | 3695.1308
|  | 2.1.7.1.1.4.2 | PrototypeM&S | 1108.932
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG | 376.988 | 2890 | 2161.7368
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration | 2161.7368
|  | 2.1.7.13.1 | Integration | 7693.7356
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | -188.95
|  |  | Check | -3.638e-12

## Oct 01
Period | 10/1/2001-10/31/2001
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4376.38
|  | 2188.19 | Tullio 10/6 | 2.1.7.13.1
|  | 2188.19 | Tullio 10/20 | 2.1.7.13.1
|  | 4376.38 | TOTAL
2705+2710+2711 Benefits | 738.7
|  | 206.8 | Tullio 10/6 TIAA Optional | 2.1.7.13.1
|  | 206.8 | Tullio 10/20 TIAA Optional | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 10/6 | 2.1.7.13.1
|  | 141.68 | Tullio Health Ins 10/20 | 2.1.7.13.1
|  | 20.87 | Tullio Retiree Health Ins 10/6 | 2.1.7.13.1
|  | 20.87 | Tullio Retiree Health Ins 10/20 | 2.1.7.13.1
|  | 738.7 | TOTAL
1020 Graduate Assistants | 1211.14
|  | 605.57 | Adarsh 10/6 | 2.1.7.1.1.4.1
|  | 605.57 | Adarsh 10/6 | 2.1.7.1.1.4.1
|  | 1211.14 | TOTAL
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 0
0
3360 Travel - Foreign | 1960.39
|  | 995.25 | TULLIO 10/20 | 2.1.1.8.6.9
|  | 10 | OMEGA
955.14
1960.39
3724 General | 0
0
3728 Freight & Delivery | 30.6
|  | 30.6 | UPS Breden 10/24 | 2.1.7.1.1.4.2
SUBTOTAL (for overhead) | 8317.21
9998 Indirect Cost | 3992.2608
|  | 2100.6624 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 354.576 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 581.3472 | 1020 Graduate Assistants | 2.1.7.1.1.4.1
|  | 0 | 2075 Student (Other)
|  | 14.688 | 3728 Freight & Delivery | 2.1.7.1.1.4.2
|  | 0 | 3321 Travel - Out-of-State
|  | 940.9872 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 0 | 3724 General | 2.1.1.5.1.5
|  | 3992.2608 | Total
Total Direct+Indirect | 12309.4708
4348 Construction Equipment | 33460.32
|  | 11271.1 | 9725 9/22 ENG | 2.1.7.1.1.4.1
|  | 220.3 | 10/5 misc for prototype | 2.1.7.1.1.4.2
|  | 4244.76 | 972510/6 ENG | 2.1.7.1.1.4.1
|  | 7490.47 | 9725 9/8 ENG | 2.1.7.1.1.4.1
|  | 10233.69 | 9724 10/20 ENG | 2.1.7.1.1.4.1
33460.32
Subtotal | 33460.32
Total Cost | 45769.7908
|  | 2.1.1.5.1.5 | Computing in building 186 | 0
|  | 2.1.1.8.6.9 | Travel | 2901.3772
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report |  | 0
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG | 35032.5072
|  | 2.1.7.1.1.4.2 | PrototypeM&S | 265.588
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG |  | 2890 | 2890
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 7570.3184
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 45769.7908
|  |  | Check | 0

## Nov 01
Period | 11/1/2001-11/30/2001
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4376.38
|  | 2188.19 | Tullio 11/3 | 2.1.7.13.1
|  | 2188.19 | Tullio 11/17 | 2.1.7.13.1
|  | 4376.38 | TOTAL
2705+2710+2711 Benefits | 996.54
|  | 206.8 | Tullio 11/3 TIAA Optional | 2.1.7.13.1
|  | 206.8 | Tullio 11/17 TIAA Optional | 2.1.7.13.1
|  | 270.6 | Tullio Health Ins 11/3 | 2.1.7.13.1
|  | 270.6 | Tullio Health Ins 11/17 | 2.1.7.13.1
|  | 20.87 | Tullio Retiree Health Ins 11/3 | 2.1.7.13.1
|  | 20.87 | Tullio Retiree Health Ins 11/17 | 2.1.7.13.1
|  | 996.54 | TOTAL
1020 Graduate Assistants | 1211.14
|  | 605.57 | Adarsh 11/3 | 2.1.7.1.1.4.1
|  | 605.57 | Adarsh 11/17 | 2.1.7.1.1.4.1
|  | 1211.14 | TOTAL
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 312.56
|  | 312.56 | Grassi 11/17 | 2.1.1.8.6.9
3360 Travel - Foreign | 0
0
3724 General | 0
0
3728 Freight & Delivery | 0
0
3952 Other Supply/Matl | 195.66
|  | 93.98 | Amazon/Baden PCR | 2.1.7.1.1.5.2
|  | 46.45 | Dell/Baden PCR | 2.1.7.1.1.5.2
|  | 55.23 | UMBookStore/Baden PCR | 2.1.7.1.1.5.2
195.66
SUBTOTAL (for overhead) | 7092.28
9998 Indirect Cost | 3404.2944
|  | 2100.6624 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 478.3392 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 581.3472 | 1020 Graduate Assistants | 2.1.7.1.1.4.1
|  | 0 | 2075 Student (Other)
|  | 0 | 3728 Freight & Delivery
|  | 150.0288 | 3321 Travel - Out-of-State | 2.1.1.8.6.9
|  | 0 | 3360 Travel - Foreign
|  | 93.9168 | 3952 Other Supply/Matl | 2.1.1.5.1.5
|  | 3404.2944 | Total
Total Direct+Indirect | 10496.5744
4348 Construction Equipment | 15316.35
|  | 7070.8 | 9725 11/3 ENG | 2.1.7.1.1.4.1
|  | 5899.3 | 9725 11/17 ENG | 2.1.7.1.1.5.1
|  | 2297.19 | HTR prototype parts | 2.1.7.1.1.4.2
|  | 49.06 | HTR prototype parts | 2.1.7.1.1.4.2
15316.35
Subtotal | 15316.35
Total Cost | 25812.9244
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel | 462.5888
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG | 8863.2872
|  | 2.1.7.1.1.4.2 | PrototypeM&S | 2635.8268
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG | 5899.3
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG |  | 2890 | 2890
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 7951.9216
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 25812.9244
|  |  | Check | 0

## Dec 01
Period | 12/1/2001-12/31/2001
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4376.38
|  | 2188.19 | Tullio 12/1 | 2.1.7.13.1
|  | 2188.19 | Tullio 12/15 | 2.1.7.13.1
|  | 4376.38 | TOTAL
2705+2710+2711 Benefits | 1119.94
|  | 206.8 | Tullio 12/1 TIAA Optional | 2.1.7.13.1
|  | 206.8 | Tullio 12/15 TIAA Optional | 2.1.7.13.1
|  | 270.6 | Tullio Health Ins 12/1 | 2.1.7.13.1
|  | 378.16 | Tullio Health Ins 12/15 | 2.1.7.13.1
|  | 20.87 | Tullio Retiree Health Ins 12/1 | 2.1.7.13.1
|  | 36.71 | Tullio Retiree Health Ins 12/15 | 2.1.7.13.1
|  | 1119.94 | TOTAL
1020 Graduate Assistants | 1211.14
|  | 605.57 | Adarsh 12/1 | 2.1.7.1.1.5.1
|  | 605.57 | Adarsh 12/15 | 2.1.7.1.1.5.1
|  | 1211.14 | TOTAL
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 536.18
|  | 200.18 | USAirways 12/7 | 2.1.1.8.6.9
|  | 324 | TCRD12 12/7 | 2.1.1.8.6.9
|  | 12 | Omega 12/7 | 2.1.1.8.6.9
536.18
3360 Travel - Foreign | 1933.15
|  | 1933.15 | Skuja 12/1 | 2.1.1.8.6.9
3724 General | 0
0
3728 Freight & Delivery | 0
0
SUBTOTAL (for overhead) | 9176.79
9998 Indirect Cost | 4404.8592
|  | 2100.6624 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 537.5712 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 581.3472 | 1020 Graduate Assistants | 2.1.7.1.1.5.1
|  | 0 | 2075 Student (Other)
|  | 0 | 3728 Freight & Delivery
|  | 257.3664 | 3321 Travel - Out-of-State | 2.1.1.8.6.9
|  | 927.912 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 4404.8592 | Total
Total Direct+Indirect | 13581.6492
4060 Computers-Admin | 2892.7
|  | 2892.7 | Rack mounted dual PC for Tully | 2.1.1.5.1.5
4348 Construction Equipment | 18494.07
|  | 5588.64 | 9725 12/1 ENG | 2.1.7.1.1.5.1
|  | 6583.8 | 9725 12/15 ENG | 2.1.7.1.1.5.1
|  | 6321.63 | HTR prototype parts, boards, etc. | 2.1.7.1.1.5.2
18494.07
Subtotal | 21386.77
Total Cost | 34968.4192
|  | 2.1.1.5.1.5 | Computing in building 186 | 2892.7
|  | 2.1.1.8.6.9 | Travel | 3654.6084
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG | 13964.9272
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S | 6321.63
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG |  | 2890 | 2890
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 8134.5536
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 34968.4192
|  |  | Check | 0

## Jan 02
Period | 1/1/2002-1/31/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 6727.13
|  | 2188.19 | Tullio 12/29 | 2.1.7.13.1
|  | 2263.22 | Tullio 1/12 | 2.1.7.13.1
|  | 2275.72 | Tullio 1/26 | 2.1.7.13.1
|  | 6727.13 | TOTAL
2705+2710+2711 Benefits | 1517.24
|  | 206.8 | Tullio 12/29 TIAA Optional | 2.1.7.13.1
|  | 215.07 | Tullio 1/12 TIAA Optional | 2.1.7.13.1
|  | 215.07 | Tullio 1/29 TIAA Optional | 2.1.7.13.1
|  | 402.42 | Tullio Health Ins 1/12 | 2.1.7.13.1
|  | 402.42 | Tullio Health Ins 1/29 | 2.1.7.13.1
|  | 37.73 | Tullio Retiree 1/12 | 2.1.7.13.1
|  | 37.73 | Tullio Retiree 1/26 | 2.1.7.13.1
|  | 1517.24 | TOTAL
1020 Graduate Assistants | 1816.71
|  | 605.57 | Adarsh 12/29 | 2.1.7.1.1.3.1
|  | 605.57 | Adarsh 1/12 | 2.1.7.1.1.3.1
|  | 605.57 | Adarsh 1/26 | 2.1.7.1.1.3.1
|  | 1816.71 | TOTAL
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 273
|  | 261 | Delta Airlines 2/1 | 2.1.1.8.6.9
|  | 12 | Omega 2/1 | 2.1.1.8.6.9
273
3360 Travel - Foreign | 1413.21
|  | 1001.08 | Baden 12/29 | 2.1.1.8.6.9
|  | 10 | Travel-ON | 2.1.1.8.6.9
|  | 402.13 | UAL 1/4 | 2.1.1.8.6.9
1413.21
3724 General | 0
0
3728 Freight & Delivery | 0
0
SUBTOTAL (for overhead) | 11747.29
9998 Indirect Cost | 5638.6992
|  | 3229.0224 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 728.2752 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 872.0208 | 1020 Graduate Assistants | 2.1.7.1.1.5.1
|  | 0 | 2075 Student (Other)
|  | 0 | 3728 Freight & Delivery
|  | 131.04 | 3321 Travel - Out-of-State | 2.1.1.8.6.9
|  | 678.3408 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 5638.6992 | Total
Total Direct+Indirect | 17385.9892
4060 Computers-Admin | 0
0
4348 Construction Equipment | 22155.5
|  | 3255.7 | 9725 12/29 ENG | 2.1.7.9.1
|  | 6945.17 | 9725 1/12 ENG | 2.1.7.1.1.3.1
|  | 6869.68 | 9725 1/26 ENG | 2.1.7.1.1.5.2
|  | 2256 | Stratos Rx (24) | 2.1.7.1.1.5.2
|  | 1800 | HTR prototype CR | 2.1.7.1.1.5.2
|  | 656 | Agilent scope parts | 2.1.7.1.1.5.2
|  | 195 | CMS computer memory | 2.1.7.11.1.2
|  | 177.95 | freight and shipping | 2.1.7.1.1.5.2
22155.5
Subtotal | 22155.5
Total Cost | 39541.4892
|  | 2.1.1.5.1.5 | Computing in building 186 | 0
|  | 2.1.1.8.6.9 | Travel | 2495.5908
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG | 8761.88
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG | 7741.7008
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S | 4889.95
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration | 3255.7
|  | 2.1.7.11.1.1 | Universal Tester ENG |  | 2890 | 2890
|  | 2.1.7.11.1.2 | Universal Tester M&S | 195
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 12201.6676
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 39541.4892
|  |  | Check | 0

## Feb 02
Period | 2/1/2002-2/28/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4551.44
|  | 2275.72 | Tullio 2/09 | 2.1.7.13.1
|  | 2275.72 | Tullio 2/23 | 2.1.7.13.1
|  | 4551.44 | TOTAL
2705+2710+2711 Benefits | 1310.44
|  | 215.07 | Tullio 2/9 TIAA Optional | 2.1.7.13.1
|  | 215.07 | Tullio 2/23 TIAA Optional | 2.1.7.13.1
|  | 402.42 | Tullio Health Ins 2/9 | 2.1.7.13.1
|  | 402.42 | Tullio Health Ins 2/23 | 2.1.7.13.1
|  | 37.73 | Tullio Retiree 2/9 | 2.1.7.13.1
|  | 37.73 | Tullio Retiree 2/23 | 2.1.7.13.1
|  | 1310.44 | TOTAL
1020 Graduate Assistants | 1211.14
|  | 605.57 | Adarsh 2/9 | 2.1.7.1.1.6.2
|  | 605.57 | Adarsh 2/23 | 2.1.7.1.1.6.2
|  | 1211.14 | TOTAL
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 2023
|  | 2023 | Ardash tuition waver | 2.1.7.1.1.6.2
3321 Travel - Out-of-State | 1927.63
|  | 1083.05 | Tullio 2/23 | 2.1.1.8.6.9
|  | 844.58 | Skuja 2/23 | 2.1.1.8.6.9
1927.63
3360 Travel - Foreign | 0
0
3724 General | 1863.39
|  | 1863.39 | CERN daSilva | 2.1.1.5.1.5
3728 Freight & Delivery | 0
0
SUBTOTAL (for overhead) | 12887.04
9998 Indirect Cost | 5214.7392
|  | 2184.6912 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 629.0112 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 581.3472 | 1020 Graduate Assistants | 2.1.7.1.1.6.2
|  | 0 | 2075 Student (Other)
|  | 894.4272 | 2775 Tuition Waiver GA | 2.1.7.1.1.6.2
|  | 0 | 3728 Freight & Delivery
|  | 925.2624 | 3321 Travel - Out-of-State | 2.1.1.8.6.9
|  | 0 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 5214.7392 | Total
Total Direct+Indirect | 18101.7792
4060 Computers-Admin | 0
0
4348 Construction Equipment | 14571.23
|  | 6857.2 | 9725 2/9 ENG | 2.1.7.1.1.6.2
|  | 7712.21 | 9725 2/23 ENG | 2.1.7.9.1
|  | 1.82 | capacitors | 2.1.7.1.1.5.2
14571.23
Subtotal | 14571.23
Total Cost | 32673.0092
|  | 2.1.1.5.1.5 | Computing in building 186 | 1863.39
|  | 2.1.1.8.6.9 | Travel | 2852.8924
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S | 1.82
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG | 11567.1144
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration | 7712.21
|  | 2.1.7.11.1.1 | Universal Tester ENG |  | 2890 | 2890
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 8675.5824
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 32673.0092
|  |  | Check | 0

## Mar 02
Period | 3/1/2002-3/31/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4551.44
|  | 2275.72 | Tullio 3/09 | 2.1.7.13.1
|  | 2275.72 | Tullio 3/23 | 2.1.7.13.1
|  | 4551.44 | TOTAL
2705+2710+2711 Benefits | 1310.44
|  | 215.07 | Tullio 3/9 TIAA Optional | 2.1.7.13.1
|  | 215.07 | Tullio 3/23 TIAA Optional | 2.1.7.13.1
|  | 402.42 | Tullio Health Ins 3/9 | 2.1.7.13.1
|  | 402.42 | Tullio Health Ins 3/23 | 2.1.7.13.1
|  | 37.73 | Tullio Retiree 3/9 | 2.1.7.13.1
|  | 37.73 | Tullio Retiree 3/23 | 2.1.7.13.1
|  | 1310.44 | TOTAL
1020 Graduate Assistants | 1211.14
|  | 605.57 | Adarsh 3/9 | 2.1.7.1.1.6.2
|  | 605.57 | Adarsh 3/23 | 2.1.7.1.1.6.2
|  | 1211.14 | TOTAL
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 0
0
3360 Travel - Foreign | 0
0
3722 Subcontract<$25k | 2308.3
|  | 2308.3 | CERN | 2.1.1.5.1.5
3724 General | 1905.44
|  | 1905.44 | CERN daSilva | 2.1.7.15.2
3728 Freight & Delivery | 0
0
SUBTOTAL (for overhead) | 11286.76
9998 Indirect Cost | 5417.6448
|  | 2184.6912 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 629.0112 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 581.3472 | 1020 Graduate Assistants | 2.1.7.1.1.6.2
|  | 0 | 2075 Student (Other)
|  | 1107.984 | 3722 Subcontract<$25k | 2.1.1.5.1.5
|  | 914.6112 | 3724 General | 2.1.7.15.2
|  | 0 | 3728 Freight & Delivery
|  | 0 | 3321 Travel - Out-of-State
|  | 0 | 3360 Travel - Foreign
|  | 5417.6448 | Total
Total Direct+Indirect | 16704.4048
4060 Computers-Admin | 0
0
4348 Construction Equipment | 13951.44
|  | 6878.46 | 9725 3/9 ENG | 2.1.7.1.1.6.2
|  | 6217.95 | 9725 3/23 ENG | 2.1.7.1.1.6.2
|  | 710.43 | HTR parts (includes TI parts) | 2.1.7.1.1.5.2
|  | 144.6 | Freight and shipping | 2.1.7.1.1.5.2
13951.44
Subtotal | 13951.44
Total Cost | 30655.8448
|  | 2.1.1.5.1.5 | Computing in building 186 | 3416.284
|  | 2.1.1.8.6.9 | Travel | 0
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S | 855.03
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG | 14888.8972
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG |  | 2890 | 2890
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 8675.5824
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG | 2820.0512
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 30655.8448
|  |  | Check | 0

## Apr 02
Period | 4/1/2002-4/30/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4551.44
|  | 2275.72 | Tullio 4/06 | 2.1.7.13.1
|  | 2275.72 | Tullio 4/20 | 2.1.7.13.1
|  | 4551.44 | TOTAL
2705+2710+2711 Benefits | 1310.44
|  | 215.07 | Tullio 4/6 TIAA Optional | 2.1.7.13.1
|  | 215.07 | Tullio 4/20 TIAA Optional | 2.1.7.13.1
|  | 402.42 | Tullio Health Ins 4/6 | 2.1.7.13.1
|  | 402.42 | Tullio Health Ins 4/20 | 2.1.7.13.1
|  | 37.73 | Tullio Retiree 4/6 | 2.1.7.13.1
|  | 37.73 | Tullio Retiree 4/20 | 2.1.7.13.1
|  | 1310.44 | TOTAL
1020 Graduate Assistants | 1211.14
|  | 605.57 | Adarsh 4/6 | 2.1.7.1.1.6.2
|  | 605.57 | Adarsh 4/20 | 2.1.7.1.1.6.2
|  | 1211.14 | TOTAL
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 188.55
188.55
3360 Travel - Foreign | 0
0
3722 Subcontract<$25k | 0
|  | 0 | CERN
3724 General | 1967.67
|  | 1967.67 | CERN daSilva | 2.1.7.15.2
3728 Freight & Delivery | 0
0
SUBTOTAL (for overhead) | 9229.24
9998 Indirect Cost | 4430.0352
|  | 2184.6912 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 629.0112 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 581.3472 | 1020 Graduate Assistants | 2.1.7.1.1.6.2
|  | 0 | 2075 Student (Other)
|  | 0 | 3722 Subcontract<$25k
|  | 944.4816 | 3724 General | 2.1.7.15.2
|  | 0 | 3728 Freight & Delivery
|  | 90.504 | 3321 Travel - Out-of-State | 2.1.1.8.6.9
|  | 0 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 4430.0352 | Total
Total Direct+Indirect | 13659.2752
4060 Computers-Admin | 0
0
4348 Construction Equipment | 14039.2
|  | 4184.14 | 9725 4/6 ENG | 2.1.7.1.1.6.2
|  | 6421.71 | 9725 4/20 ENG | 2.1.7.1.1.6.2
|  | 1890 | TI/Stratos test boards | 2.1.10.11.5
|  | 1140.4 | Computer | 2.1.7.1.1.5.2
|  | 402.95 | Misc parts for HTR | 2.1.7.1.1.5.2
Subtotal | 14039.2 | 14039.2
Total Cost | 27698.4752
|  | 2.1.1.5.1.5 | Computing in building 186 | 1140.4
|  | 2.1.1.8.6.9 | Travel | 279.054
|  | 2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland
|  | 2.1.10.11.5 | Test BeamTRIDAS M&S | 1890
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S | 402.95
|  | 2.1.7.1.1.6.1 | HTR Production M&S
|  | 2.1.7.1.1.6.2 | HTR Production ENG | 12398.3372
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 8675.5824
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG | 2912.1516
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 27698.4752
|  |  | Check | 0

## May 02
Period | 5/1/2002-5/31/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 4551.44
|  | 2275.72 | Tullio 5/4 | 2.1.7.13.1
|  | 2275.72 | Tullio 5/18 | 2.1.7.13.1
|  | 4551.44 | TOTAL
2705+2710+2711 Benefits | 1310.44
|  | 215.07 | Tullio 5/4 TIAA Optional | 2.1.7.13.1
|  | 215.07 | Tullio 5/18 TIAA Optional | 2.1.7.13.1
|  | 402.42 | Tullio Health Ins 5/4 | 2.1.7.13.1
|  | 402.42 | Tullio Health Ins 5/18 | 2.1.7.13.1
|  | 37.73 | Tullio Retiree 5/4 | 2.1.7.13.1
|  | 37.73 | Tullio Retiree 5/18 | 2.1.7.13.1
|  | 1310.44 | TOTAL
1020 Graduate Assistants | 1211.14
|  | 605.57 | Adarsh 5/4 | 2.1.7.1.1.6.2
|  | 605.57 | Adarsh 5/18 | 2.1.7.1.1.6.2
|  | 1211.14 | TOTAL
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 632.97
|  | 273.11 | SKUJA | 2.1.1.8.6.9
|  | 359.86 | GRASSI | 2.1.1.8.6.9
632.97
3360 Travel - Foreign | 0
0
3722 Subcontract<$25k | 0
|  | 0 | CERN
3724 General | 1997.62
|  | 1997.62 | CERN daSilva | 2.1.7.15.2
3728 Freight & Delivery | 0
0
SUBTOTAL (for overhead) | 9703.61
9998 Indirect Cost | 4657.7328
|  | 2184.6912 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 629.0112 | 2710+2711+2725 Benefits | 2.1.7.13.1
|  | 581.3472 | 1020 Graduate Assistants | 2.1.7.1.1.6.2
|  | 0 | 2075 Student (Other)
|  | 0 | 3722 Subcontract<$25k
|  | 958.8576 | 3724 General | 2.1.7.15.2
|  | 0 | 3728 Freight & Delivery
|  | 303.8256 | 3321 Travel - Out-of-State | 2.1.1.8.6.9
|  | 0 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 4657.7328 | Total
Total Direct+Indirect | 14361.3428
4060 Computers-Admin | 0
0
4348 Construction Equipment | 12804.15
|  | 6944.7 | 9725 5/4 ENG | 2.1.7.1.1.6.2
|  | 5835.96 | 9725 5/18 ENG | 2.1.7.1.1.6.2
|  | 23.49 | Misc parts for HTR | 2.1.7.1.1.6.1
Subtotal | 12804.15 | 12804.15
Total Cost | 27165.4928
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel | 936.7956
|  | 2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland
|  | 2.1.10.11.5 | Test BeamTRIDAS M&S
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S | 23.49
|  | 2.1.7.1.1.6.2 | HTR Production ENG | 14573.1472 | 2890 | 2890
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 8675.5824
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG | 2956.4776
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 27165.4928
|  |  | Check | 0

## Jun 02
Period | 6/1/2002-6/30/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 6989.71
|  | 6827.16 | Tullio 6/1 6/15 6/29 | 2.1.7.13.1
|  | 162.55 | Tullio end of year | 2.1.7.13.1
|  | 6989.71 | TOTAL
1020 Graduate Assistants | 3219.96
|  | 3176.71 | Adarsh 6/1 6/15 6/29 | 2.1.7.1.1.6.2
|  | 43.25 | Ardash end of year | 2.1.7.1.1.6.2
|  | 3219.96 | TOTAL
2705+2710+2711+2725+2770 Benefits | 1454.22
|  | 215.07 | 2705 Tullio 6/1 TIAA Optional | 2.1.7.13.1
|  | 804.84 | 2710 Tullio Health Ins 6/1-6/15 | 2.1.7.13.1
|  | 75.46 | 2711 Tullio Retiree 6/1-6/15 | 2.1.7.13.1
|  | 356.05 | 2725 Tullio SocSec 6/15 6/29 6/30 | 2.1.7.13.1
|  | 2.8 | 2770 Tullio 6/15,29,30 unemply ins ? | 2.1.7.13.1
|  | 1454.22 | TOTAL
2075 Student (Other) | 0 |  |  |  | 11663.89
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 1030.49
|  | 159.71 | GRASSI | 2.1.1.8.6.9
|  | 582.78 | GRASSI | 2.1.1.8.6.9
|  | 24 | Omega | 2.1.1.8.6.9
|  | 264 | Natl RR PA | 2.1.1.8.6.9
1030.49
3360 Travel - Foreign | 0
0
3722 Subcontract<$25k | 0
|  | 0 | CERN
3724 General | 13693.38 |  |  |  | SF
|  | 55.1822 | CMS Transportation | 2.1.10.11.5 | 116
|  | 8395.9676 | CMS SBS Bit3 cards | 2.1.10.11.5 | 17649.4
|  | 3296.6591 | HEP Salavat | 2.1.10.11.5 | 6930
|  | 25.2125 | HEP Kunori Hostel | 2.1.10.11.5 | 53
|  | 40.4352 | DRIF Travel | 2.1.10.11.5 | 85
|  | 10.3895 | HEP ??? | 2.1.10.11.5 | 21.84
|  | 927.6313 | CMS Computer Salavat | 2.1.1.5.1.5 | 1950
|  | 941.9026 | CMS Computer Salavat | 2.1.1.5.1.5 | 1980
|  | 13693.38 | CERN |  | 28785.24 | 0.47571
3728 Freight & Delivery | 29.28
|  | 12.63 | 6/19 Godinez | 2.1.5.14.2
|  | 16.65 | 6/19 Godinez | 2.1.5.14.2
29.28
SUBTOTAL (for overhead) | 26417.04
9998 Indirect Cost | 12680.1792
|  | 3355.0608 | 1012 Faculty/Staff | 2.1.7.13.1 | 5598.6672
|  | 698.0256 | 2705+2710+2711+2725+2770 Benefits | 2.1.7.13.1
|  | 1545.5808 | 1020 Graduate Assistants | 2.1.7.1.1.6.2
|  | 0 | 2075 Student (Other)
|  | 0 | 3722 Subcontract<$25k
|  | 897.3763 | 3724 Salavat Computer | 2.1.1.5.1.5
|  | 5675.4461 | 3724 General | 2.1.10.11.5 | 6586.8768
|  | 14.0544 | 3728 Freight & Delivery | 2.1.5.14.2
|  | 494.6352 | 3321 Travel - Out-of-State | 2.1.1.8.6.9
|  | 0 | 3360 Travel - Foreign
|  | 12680.1792 | Total
Total Direct+Indirect | 39097.2192
4060 Computers-Admin | 0
0
4348 Construction Equipment | 28212.32
|  | 530.02 | 9725 6/1 MDG | 2.1.10.11.5
|  | 13959.1 | parts for HTR | 2.1.7.1.1.6.1
|  | 9.99 | parts for HTR | 2.1.7.1.1.6.1
|  | 10.31 | parts for HTR | 2.1.7.1.1.6.1
|  | 7330.03 | 9725 6/15 EDG | 2.1.7.1.1.6.2
|  | 133.19 | parts for HTR | 2.1.7.1.1.6.1
|  | 6239.68 | 9725 6/1 EDG | 2.1.7.1.1.6.2
Subtotal | 28212.32 | 28212.32
Total Cost | 67309.5392
|  | 2.1.1.5.1.5 | Computing in building 186 | 2766.9102 | 18029.3122 | 2766.9131
|  | 2.1.1.8.6.9 | Travel | 1525.1252 | 1525.1252 | 1525.1252
|  | 2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland | 43.3344 | 18029.3122 | 85.8866
|  | 2.1.10.11.5 | Test BeamTRIDAS M&S | 18029.3122 | 18029.3122
|  | 2.1.7.1.1.1 | HTR Requirements Report |  | 18029.3122
|  | 2.1.7.1.1.2 | HTR Module Specification Report |  | 18029.3122
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG |  | 18029.3122
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S |  | 18029.3122
|  | 2.1.7.1.1.4.1 | Prototype ENG |  | 18029.3122
|  | 2.1.7.1.1.4.2 | PrototypeM&S |  | 18029.3122
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG |  | 18189.0222
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S |  | 18189.0222
|  | 2.1.7.1.1.6.1 | HTR Production M&S | 14112.59 | 18189.0222
|  | 2.1.7.1.1.6.2 | HTR Production ENG | 18335.2508 | 18189.0222
|  | 2.1.7.1.1.6.3 | HTR Production Shipping |  | 18189.0222
|  | 2.1.7.9.1 | VME Pipeline Module Integration |  | 18189.0222
|  | 2.1.7.11.1.1 | Universal Tester ENG |  | 18029.3122
|  | 2.1.7.11.1.2 | Universal Tester M&S |  | 18029.3122
|  | 2.1.7.11.1.5 | TTC Setup |  | 18029.3122
|  | 2.1.7.11.2.1 | FEE ENG |  | 18029.3122
|  | 2.1.7.11.2.2 | FEE M&S |  | 18029.3122
|  | 2.1.7.12.1 | Demonstrator Integration |  | 18029.3122
|  | 2.1.7.13.1 | Integration | 12497.0164 | 18029.3122
|  | 2.1.7.15.1 | SLB Trigger Link M&S |  | 18029.3122
|  | 2.1.7.15.2 | SLB Trigger Link ENG |  | 18029.3122
|  | 2.1.7.15.3 | SLB Transition Boards |  | 18029.3122
|  |  | TOTAL | 67309.5392
|  |  | Check | 0
Note on D39: Drew Baden: to be credited...
Note on D40: Drew Baden: to be credited...
Note on D41: Drew Baden: to be credited...
Note on D42: Drew Baden: to be credited...
Note on D75: Drew Baden: FRS records a $12,075.64 debit and a $5,835.96 credit = this value

## Jul 02
Period | 7/1/2002-7/31/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 6065.8
|  | 6228.35 | Tullio 7/13 7/27 | 2.1.7.13.1
|  | -162.55 | Tullio from last month | 2.1.7.13.1
|  | 6065.8 | TOTAL
1020 Graduate Assistants | 1346.32
|  | 1389.57 | Adarsh 7/13 7/27 | 2.1.7.1.1.6.2
|  | -43.25 | Ardash from last month | 2.1.7.1.1.6.2
|  | 1346.32 | TOTAL
2705+2710+2711+2725+2770 Benefits | 1339.31
|  | 0 | 2705 Tullio 6/1 TIAA Optional | 2.1.7.13.1
|  | 804.84 | 2710 Tullio Health Ins 7/13 7/27 | 2.1.7.13.1
|  | 76.02 | 2711 Tullio Retiree 7/13 7/27 | 2.1.7.13.1
|  | 454.89 | 2725 Tullio SocSec 7/13 7/27 | 2.1.7.13.1
|  | 3.56 | 2770 Tullio 7/13 7/27 | 2.1.7.13.1
|  | 1339.31 | TOTAL
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 262.82
|  | 262.82 | GRASSI | 2.1.1.8.6.9
262.82
3360 Travel - Foreign | 0
0
3722 Subcontract<$25k | 2000
|  | 2000 | CERN daSilva | 2.1.7.15.2
3724 General | 2280.93
|  | 2280.93 | CERN daSilva | 2.1.7.15.2
|  | 2280.93 | CERN
3728 Freight & Delivery | 0
0
SUBTOTAL (for overhead) | 13295.18
9998 Indirect Cost | 6381.6864
|  | 2911.584 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 646.2336 | 1020 Graduate Assistants | 2.1.7.1.1.6.2 | 3557.8176
|  | 642.8688 | 2705+2710+2711+2725+2770 Benefits | 2.1.7.13.1
|  | 0 | 2075 Student (Other)
|  | 1094.8464 | 3724 General | 2.1.7.15.2
|  | 960 | 3722 Subcontract<$25k | 2.1.7.15.2
|  | 0 | 3728 Freight & Delivery
|  | 126.1536 | 3321 Travel - Out-of-State | 2.1.1.8.6.9
|  | 0 | 3360 Travel - Foreign
|  | 6381.6864 | Total
Total Direct+Indirect | 19676.8664
4060 Computers-Admin | 0
0
4348 Construction Equipment | 13920.94
|  | 72 | 9725 6/29 MDG | 2.1.10.11.5
|  | 54.19 | parts for HTR | 2.1.7.1.1.6.1
|  | 29.08 | parts for HTR | 2.1.7.1.1.6.1
|  | 7683.25 | 9725 6/29 EDG | 2.1.7.1.1.6.1
|  | 6082.42 | 9725 7/13 EDG | 2.1.7.1.1.6.2
Subtotal | 13920.94 | 13920.94
Total Cost | 33597.8064
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel | 388.9736
|  | 2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland | 0
|  | 2.1.10.11.5 | Test BeamTRIDAS M&S
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S | 83.27
|  | 2.1.7.1.1.6.2 | HTR Production ENG | 15830.2236
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 10959.5628
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG | 6335.7764
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 33597.8064
|  |  | Check | 0

## Aug 02
Period | 8/1/2002-8/31/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 6290.46
|  | 6290.46 | Tullio 8/10 8/24 | 2.1.7.13.1
|  | 6290.46 | TOTAL
1020 Graduate Assistants | 1396.18
|  | 1396.18 | Adarsh 8/10 8/24 | 2.1.7.1.1.6.2
|  | 1396.18 | TOTAL
2705+2710+2711+2725+2770 Benefits | 1356.64
|  | 804.84 | 2710 Tullio Health Ins 8/10 8/24 | 2.1.7.13.1
|  | 76.02 | 2711 Tullio Retiree 8/10 8/24 | 2.1.7.13.1
|  | 472.08 | 2725 Tullio SocSec 6/15 8/10 8/24 | 2.1.7.13.1
|  | 3.7 | 2770 Tullio unemply ins 8/10 8/24 | 2.1.7.13.1
|  | 1356.64 | TOTAL |  | 9043.28
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 0
0
3360 Travel - Foreign | 297.95 |  |  | 2.1.1.8.6.9
|  | 273.95 | DELTA AIR 8/14
|  | 24 | Omega
297.95
3952 Tektronix | 885.75
|  | 885.75 | Megonigal 8/21 probe for new scope | 2.1.5.14.2
3722 Subcontract<$25k | 0
3724 General | 2438.1
|  | 2438.1 | CMS S-Link cards | 2.1.10.11.5
3728 Freight & Delivery | 66.45
|  | 66.45 | McQueen 8/27 | 2.1.5.14.2
SUBTOTAL (for overhead) | 12731.53
9998 Indirect Cost | 4940.8464
|  | 3019.4208 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 670.1664 | 1020 Graduate Assistants | 2.1.7.1.1.6.2
|  | 649.4112 | 2705+2710+2711+2725 Benefits | 2.1.7.13.1
|  | 1.776 | 2770 Benefits | 2.1.7.13.1
|  | 0 | 2075 Student (Other)
|  | 0 | 3722 CERN
|  | 0 | 3724 CERN
|  | 425.16 | 3952 to be credited next month… | 2.1.5.14.2
|  | 31.896 | 3728 Freight & Delivery | 2.1.5.14.2
|  | 0 | 3321 Travel - Out-of-State
|  | 143.016 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 4940.8464 | Total
Total Direct+Indirect | 17672.3764
4060 Computers-Admin | 0
0
4348 Construction Equipment | 30436.71
|  | 420 | 9725 7/27 MDG | 2.1.7.1.1.6.2
|  | 5457.41 | 9725 7/27 EDG | 2.1.7.1.1.6.2
|  | 3624.5 | 9725 7/13 EDG | 2.1.7.1.1.6.2
|  | 7218.8 | parts for HTR | 2.1.7.1.1.6.1
|  | 7556.24 | parts for HTR | 2.1.7.1.1.6.1
|  | 6159.76 | 9725 6/15 EDG | 2.1.7.1.1.6.2
Subtotal | 30436.71 | 30436.71
Total Cost | 48109.0864
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel | 440.966
|  | 2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland | 1409.256
|  | 2.1.10.11.5 | Test BeamTRIDAS M&S | 2438.1
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S | 14775.04
|  | 2.1.7.1.1.6.2 | HTR Production ENG | 17728.0164
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 11317.708
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 48109.0864
|  |  | Check | 0

## Sep 02
Period | 9/1/2002-9/30/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 6290.46 |  |  | 2.1.7.13.1
|  | 6290.46 | Tullio 9/7 9/21
|  | 6290.46 | TOTAL
1020 Graduate Assistants | 1396.18 |  |  | 2.1.7.1.1.6.2
|  | 1396.18 | Ardash 9/7 9/21
|  | 1396.18 | TOTAL
2705+2710+2711+2725+2770 Benefits | 1949.43 |  |  | 2.1.7.13.1
|  | 594.5 | 2705 Tullio TIAA optional 9/7 9/21
|  | 804.84 | 2710 Tullio Health Ins 9/7 9/21
|  | 76.02 | 2711 Tullio Retiree 9/7 9/21
|  | 470.39 | 2725 Tullio SocSec 9/7 9/21
|  | 3.68 | 2770 Tullio unemply ins 9/7 9/21
|  | 1949.43 | TOTAL
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 3949 |  |  | 2.1.7.1.1.6.2
|  | 1204 | Summer Session 1 2002 Ardash
|  | 2745 | Fall 2002 Ardash
3949
3321 Travel - Out-of-State | 0
0
3360 Travel - Foreign | 1968.08 |  |  | 2.1.1.8.6.9
|  | 1968.08 | Grassi 9/7
1968.08
3722 Subcontract<$25k | 0
3724 General | 5071.07
|  | 2894.6451 | CERN Testbeam stuff | 2.1.10.11.5
|  | 2176.4249 | CERN daSilva | 2.1.7.15.2
|  | 5071.07 | ?
3728 Freight & Delivery | -29.28 |  |  | 2.1.5.14.2
|  | -16.65 | FedEx credit?
|  | -12.63 | FedEx credit?
-29.28
3952 Other Supply/Matl | 1701.75
|  | 1701.75 | Megonigal Scope Probe | 2.1.5.14.2
SUBTOTAL (for overhead) | 22296.69
9998 Indirect Cost | 8806.8912
|  | 3019.4208 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 670.1664 | 1020 Graduate Assistants | 2.1.7.1.1.6.2
|  | 933.96 | 2705+2710+2711+2725 Benefits | 2.1.7.13.1
|  | 1.7664 | 2770 Benefits | 2.1.7.13.1
|  | 0 | 2075 Student (Other)
|  | 0 | 3722 CERN
|  | 2434.1136 | 3724 CERN | 2.1.10.11.5
|  | 816.84 | 3952 to be credited next month… | 2.1.5.14.2
|  | -14.0544 | 3728 Freight & Delivery | 2.1.5.14.2
|  | 0 | 3321 Travel - Out-of-State
|  | 944.6784 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 8806.8912 | Total
Total Direct+Indirect | 31103.5812
4060 Computers-Admin | 0
0
4348 Construction Equipment | 21554.3
|  | 6507.2 | 9725 9/7 EDG | 2.1.7.1.1.6.2
|  | 6661.99 | 9725 9/21 EDG | 2.1.7.1.1.6.2
|  | 2481.48 | Laptop for Testbeam | 2.1.10.11.5
|  | 5903.63 | parts for HTR | 2.1.7.1.1.6.1
Subtotal | 21554.3 | 21554.3
Total Cost | 52657.8812
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel | 2912.7584
|  | 2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland | 2475.2556
|  | 2.1.10.11.5 | Test BeamTRIDAS M&S | 7810.2387
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S | 5903.63
|  | 2.1.7.1.1.6.2 | HTR Production ENG | 19184.5364
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 12195.0372
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG | 2176.4249
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 52657.8812
|  |  | Check | 0

## Oct 02
Period | 10/1/2002-10/31/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 6290.46
|  | 6290.46 | Tullio 10/05 10/19 | 2.1.7.13.1
|  | 6290.46 | TOTAL
1020 Graduate Assistants | 1396.18
|  | 1396.18 | Ardash 10/05 10/19 | 2.1.7.1.1.6.2
|  | 1396.18 | TOTAL
2705+2710+2711+2725+2770 Benefits | 1949.44 |  |  | 2.1.7.13.1
|  | 594.5 | 2705 Tullio TIAA optional 10/05 10/19
|  | 804.84 | 2710 Tullio Health Ins 10/05 10/19
|  | 76.02 | 2711 Tullio Retiree 10/05 10/19
|  | 470.4 | 2725 Tullio SocSec 10/05 10/19
|  | 3.68 | 2770 Tullio unemply ins 10/05 10/19
|  | 1949.44 | TOTAL
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 0
0
3360 Travel - Foreign | 0
0
3952 Tektronix | -673.29 |  |  | 2.1.5.14.2
|  | -885.75 | Credit from Aug/02 purchase (moved to 4348)
|  | 212.46 | Arrow (Megonigal), wrong subcode
-673.29
3722+3724+3732 (CERN) | 9461.17
|  | 2692.17 | da Silva | 2.1.7.15.2
|  | 1959.63 | da Silva | 2.1.7.15.2
|  | 4809.37 | testbeam stuff (S-link, etc.) | 2.1.10.11.5
9461.17
3728 Freight & Delivery | 0
0
SUBTOTAL (for overhead) | 18423.96
9998 Indirect Cost | 5599.1792
|  | 3019.4208 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 670.1664 | 1020 Graduate Assistants | 2.1.7.1.1.6.2
|  | 933.9648 | 2705+2710+2711+2725 Benefits | 2.1.7.13.1
|  | 1.7664 | 2770 Benefits | 2.1.7.13.1
|  | 0 | 2075 Student (Other)
|  | 1297.04 | 3722+3724+3732 (CERN) (hit $25k limit) | 2.1.10.11.5
|  | -425.16 | 3952 to be credited next month… | 2.1.5.14.2
|  | 101.9808 | Arrow (Megonigal), wrong subcode | 2.1.5.14.2
|  | 0 | 3728 Freight & Delivery
|  | 0 | 3321 Travel - Out-of-State
|  | 0 | 3360 Travel - Foreign
|  | 5599.1792 | Total
Total Direct+Indirect | 24023.1392
4060 Computers-Admin | 0
0
4348 Construction Equipment | 11656.1
|  | 5704.47 | 9725 10/05 EDG | 2.1.7.1.1.6.2
|  | 4182.21 | 9725 10/19 EDG | 2.1.7.1.1.6.2
|  | 885.75 | Megonigal 8/21 probe for new scope | 2.1.5.14.2
|  | 883.67 | parts for HTR | 2.1.7.1.1.6.1
Subtotal | 11656.1 | 11656.1
Total Cost | 35679.2392
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel | 0
|  | 2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland
|  | 2.1.10.11.5 | Test BeamTRIDAS M&S | 5995.6908
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S | 883.67
|  | 2.1.7.1.1.6.2 | HTR Production ENG | 11953.0264
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 12195.052
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG | 4651.8
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 35679.2392
|  |  | Check | 0

## Nov 02
Period | 11/1/2002-11/30/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 6290.46
|  | 6290.46 | Tullio 11/02 11/16 | 2.1.7.13.1
|  | 6290.46 | TOTAL
1020 Graduate Assistants | 1396.18
|  | 1396.18 | Ardash 11/02 11/16 | 2.1.7.1.1.6.2
|  | 1396.18 | TOTAL
2705+2710+2711+2725+2770 Benefits | 1948.59
|  | 594.5 | 2705 Tullio TIAA optional 11/02 11/16 | 2.1.7.13.1
|  | 804.84 | 2710 Tullio Health Ins 11/02 11/16 | 2.1.7.13.1
|  | 76.02 | 2711 Tullio Retiree 11/02 11/16 | 2.1.7.13.1
|  | 469.55 | 2725 Tullio SocSec 11/02 11/16 | 2.1.7.13.1
|  | 3.68 | 2770 Tullio unemply ins 11/02 11/16 | 2.1.7.13.1
|  | 1948.59 | TOTAL |  | 9635.23
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 0
0
3360 Travel - Foreign | 0 |  |  | 2.1.1.8.6.9
0
3952 Other Supply/Matl | 2049.97
|  | 1599.97 | Sony PC Drew (Laptop) | 2.1.7.1.1.6.1
|  | 450 | Aldec renewal | 2.1.7.1.1.6.1
2049.97
3722+3724+3732 (CERN) | 4880.88
|  | 2188.19 | da Silva | 2.1.7.15.2
|  | 2692.69 | SBS Bit3 adapter | 2.1.5.14.2
4880.88
3728 Freight & Delivery | 0
0
SUBTOTAL (for overhead) | 16566.08
9998 Indirect Cost | 7951.7184
|  | 3019.4208 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 670.1664 | 1020 Graduate Assistants | 2.1.7.1.1.6.2
|  | 933.5568 | 2705+2710+2711+2725 Benefits | 2.1.7.13.1
|  | 1.7664 | 2770 Benefits | 2.1.7.13.1
|  | 0 | 2075 Student (Other)
|  | 2342.8224 | 3722+3724+3732 (CERN) (hit $25k limit) | 2.1.5.14.2
|  | 983.9856 | 3952 to be credited next month… | 2.1.5.14.2
|  | 0 | 3728 Freight & Delivery | 2.1.5.14.2
|  | 0 | 3321 Travel - Out-of-State
|  | 0 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 7951.7184 | Total
Total Direct+Indirect | 24517.7984
4060 Computers-Admin | 0
0
4348 Construction Equipment | 17095.18
|  | 9254.16 | 9725 11/02 EDG | 2.1.7.1.1.6.2
|  | 7841.02 | 9725 11/16 EDG | 2.1.7.1.1.6.2
Subtotal | 17095.18 | 17095.18
Total Cost | 41612.9784
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel
|  | 2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland | 6019.498
|  | 2.1.10.11.5 | Test BeamTRIDAS M&S
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S | 2049.97
|  | 2.1.7.1.1.6.2 | HTR Production ENG | 19161.5264
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 12193.794
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG | 2188.19
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 41612.9784
|  |  | Check | 0

## Dec 02
Period | 12/1/2002-12/31/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 6290.46
|  | 6290.46 | Tullio 11/30 12/14 | 2.1.7.13.1
|  | 6290.46 | TOTAL
1020 Graduate Assistants | 1396.18
|  | 1396.18 | Ardash 11/30 12/14 | 2.1.7.1.1.6.2
|  | 1396.18 | TOTAL
2705+2710+2711+2725+2770 Benefits | 1948.59
|  | 594.5 | 2705 Tullio TIAA optional 11/30 12/14 | 2.1.7.13.1
|  | 804.84 | 2710 Tullio Health Ins 11/30 12/14 | 2.1.7.13.1
|  | 76.02 | 2711 Tullio Retiree 11/30 12/14 | 2.1.7.13.1
|  | 469.55 | 2725 Tullio SocSec 11/30 12/14 | 2.1.7.13.1
|  | 3.68 | 2770 Tullio unemply ins 11/30 12/14 | 2.1.7.13.1
|  | 1948.59 | TOTAL |  | 9635.23
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 0
0
3360 Travel - Foreign | 1209.83
|  | 1209.83 | Drew trip to CERN | 2.1.1.8.6.9
3952 Other Supply/Matl | 0
0
3722+3724+3732 (CERN) | 0
0
3728 Freight & Delivery | 0
0
SUBTOTAL (for overhead) | 10845.06
9998 Indirect Cost | 5205.6288
|  | 3019.4208 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 670.1664 | 1020 Graduate Assistants | 2.1.7.1.1.6.2
|  | 933.5568 | 2705+2710+2711+2725 Benefits | 2.1.7.13.1
|  | 1.7664 | 2770 Benefits | 2.1.7.13.1
|  | 0 | 2075 Student (Other)
|  | 0 | 3722+3724+3732 (CERN) (hit $25k limit)
|  | 0 | 3952 to be credited next month… | 2.1.5.14.2
|  | 0 | 3728 Freight & Delivery | 2.1.5.14.2
|  | 0 | 3321 Travel - Out-of-State
|  | 580.7184 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 5205.6288 | Total
Total Direct+Indirect | 16050.6888
4060 Computers-Admin | 0
0
4348 Construction Equipment | 15683.98
|  | 5609.14 | 9725 11/30 EDG | 2.1.7.1.1.6.2
|  | 7219.56 | 9725 12/14 EDG+MDG | 2.1.7.1.1.6.2
|  | 2855.28 | parts for HTR | 2.1.7.1.1.6.1
Subtotal | 15683.98 | 15683.98
Total Cost | 31734.6688
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel | 1790.5484
|  | 2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland
|  | 2.1.10.11.5 | Test BeamTRIDAS M&S
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S | 2855.28
|  | 2.1.7.1.1.6.2 | HTR Production ENG | 14895.0464
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 12193.794
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 31734.6688
|  |  | Check | 0

## Jan 03
Period | 1/1/2003-1/31/2002
Contract | 509604
Overhead rate | 0.48
UMD Amount
1012 Faculty/Staff | 9435.69
|  | 9435.69 | Tullio 12/28 1/11 1/25 | 2.1.7.13.1
|  | 9435.69 | TOTAL
1020 Graduate Assistants | 2094.27
|  | 2094.27 | Ardash 12/28 1/11 1/25 | 2.1.7.1.1.6.2
|  | 2094.27 | TOTAL
2705+2710+2711+2725+2770 Benefits | 2424.45
|  | 891.75 | 2705 Tullio TIAA optional 11/30 12/14 | 2.1.7.13.1
|  | 748.04 | 2710 Tullio Health Ins 11/30 12/14 | 2.1.7.13.1
|  | 59.96 | 2711 Tullio Retiree 11/30 12/14 | 2.1.7.13.1
|  | 715.05 | 2725 Tullio SocSec 11/30 12/14 | 2.1.7.13.1
|  | 9.65 | 2770 Tullio unemply ins 11/30 12/14 | 2.1.7.13.1
|  | 2424.45 | TOTAL |  | 13954.41
2075 Student (Other) | 0
0
0
2775 Tuition Waiver GA | 0
0
3321 Travel - Out-of-State | 0
0
3360 Travel - Foreign | 531.03
|  | 24 | OMEGA 1/14 | 2.1.1.8.6.9
|  | 507.03 | United 1/14 Megonigal | 2.1.1.8.6.9
531.03
3952 Other Supply/Matl | -3301.72
|  | -1599.97 | Drew Laptop (see Nov 02) | 2.1.7.1.1.6.1
|  | -1701.75 | Scope Probe (see Sep 02) | 2.1.5.14.2
-3301.72
3722+3724+3732 (CERN) | 0
0
3728 Freight & Delivery | 0
0
SUBTOTAL (for overhead) | 11183.72
9998 Indirect Cost | 5368.1856
|  | 4529.1312 | 1012 Faculty/Staff | 2.1.7.13.1
|  | 1005.2496 | 1020 Graduate Assistants | 2.1.7.1.1.6.2
|  | 1159.104 | 2705+2710+2711+2725 Benefits | 2.1.7.13.1
|  | 4.632 | 2770 Benefits | 2.1.7.13.1
|  | 0 | 2075 Student (Other)
|  | 0 | 3722+3724+3732 (CERN) (hit $25k limit)
|  | -816.84 | credit from Sep 02 | 2.1.5.14.2
|  | -767.9856 | credit from Nov 02 | 2.1.7.1.1.6.1
|  | 0 | 3728 Freight & Delivery | 2.1.5.14.2
|  | 0 | 3321 Travel - Out-of-State
|  | 254.8944 | 3360 Travel - Foreign | 2.1.1.8.6.9
|  | 5368.1856 | Total
Total Direct+Indirect | 16551.9056
4060 Computers-Admin | 0
0
4348 Construction Equipment | 15683.98
|  | 5609.14 | 9725 11/30 EDG | 2.1.7.1.1.6.2
|  | 7219.56 | 9725 12/14 EDG+MDG | 2.1.7.1.1.6.2
|  | 2855.28 | parts for HTR | 2.1.7.1.1.6.1
Subtotal | 15683.98 | 15683.98
4361 Sens Equip Comp Ac/R | 3301.72
|  | 1701.75 | Megonigal Scope Probe (see Sep 02) | 2.1.5.14.2
|  | 1599.97 | Sony PC Drew (Laptop, see Nov 02) | 2.1.7.1.1.6.1
3301.72
Total Cost | 32235.8856
|  | 2.1.1.5.1.5 | Computing in building 186
|  | 2.1.1.8.6.9 | Travel | 785.9244
|  | 2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland
|  | 2.1.10.11.5 | Test BeamTRIDAS M&S
|  | 2.1.7.1.1.1 | HTR Requirements Report
|  | 2.1.7.1.1.2 | HTR Module Specification Report
|  | 2.1.7.1.1.3.1 | HTR Demonstrator ENG
|  | 2.1.7.1.1.3.2 | HTR Demonstrator M&S
|  | 2.1.7.1.1.4.1 | Prototype ENG
|  | 2.1.7.1.1.4.2 | PrototypeM&S
|  | 2.1.7.1.1.5.1 | 2nd Prototype ENG
|  | 2.1.7.1.1.5.2 | 2nd PrototypeM&S
|  | 2.1.7.1.1.6.1 | HTR Production M&S | 2855.28
|  | 2.1.7.1.1.6.2 | HTR Production ENG | 15928.2196
|  | 2.1.7.1.1.6.3 | HTR Production Shipping
|  | 2.1.7.9.1 | VME Pipeline Module Integration
|  | 2.1.7.11.1.1 | Universal Tester ENG
|  | 2.1.7.11.1.2 | Universal Tester M&S
|  | 2.1.7.11.1.5 | TTC Setup
|  | 2.1.7.11.2.1 | FEE ENG
|  | 2.1.7.11.2.2 | FEE M&S
|  | 2.1.7.12.1 | Demonstrator Integration
|  | 2.1.7.13.1 | Integration | 17553.0072
|  | 2.1.7.15.1 | SLB Trigger Link M&S
|  | 2.1.7.15.2 | SLB Trigger Link ENG
|  | 2.1.7.15.3 | SLB Transition Boards
|  |  | TOTAL | 37122.4312
|  |  | Check | -4886.5456

## WBS Expended
| FNAL not mine | [22 empty] | 56773.7
| FNAL total | [22 empty] | 463733.06
|  | 2000-02-01 | 2000-03-01 | 2000-04-01 | 2000-05-01 | 2000-06-01 | 2000-07-01 | 2000-08-01 | 2000-09-01 | 2000-10-01 | 2000-11-01 | 2000-12-01 | 2001-01-01 | 2001-02-01 | 2001-03-01 | 2001-04-01 | 2001-05-01 | 2001-06-01 | 2001-07-01 | 2001-08-01 | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01 | 2002-01-02 | 2002-02-02 | 2002-03-02 | Apr-Aug 02 | TOTAL | TOTAL thru 10/01 | Total UMD thinks FNAL paid | Allocated | Remaining | FNAL Billed | Diff
2.1.1.5.1.5 | Computing in building 186 | 2000-10-01: 7041.17; 2001-05-01: 14642.2912; 2001-06-01: -10679.7984; 2001-08-01: 15924.2524; 2001-09-01: -15924.2524; 2001-10-01: 0; 2001-12-01: 2892.7; 2002-01-02: 0; 2002-02-02: 1863.39; 2002-03-02: 6236.3352 | 3907.3102 | 25903.3982 | 11003.6628 | 11003.6628 |  |  | 11816.54 | -812.8772
2.1.1.8.6.9 | Travel |  | 3554.5604 | 403.8328 | 1953.4668 | 6427.0924 |  | 1903.65 | 612.1132 | 2293.4812 | 7733.2664 | 1581.59 | 2219.2304 | 5661.5476 | 9449.6964 | 3647.4008 | 9957.8988 | 6031.8436 | 7277.1156 | 1962.0656 | 347.504 | 2901.3772 | 462.5888 | 3654.6084 | 2495.5908 | 2852.8924 | 0 | 3570.9144 | 88955.328 | 75918.7332 | 49644.7816 |  |  | 67395.16 | -17750.3784 | -33740.1208
2.1.7.1.1.1 | HTR Requirements Report | [27 empty] | 0 | 0 | 0 | 0 | 0 |  | 0
2.1.7.1.1.2 | HTR Module Specification Report | 2000-03-01: 2585.07; 2000-05-01: 1830.4048; 2000-07-01: 33.25; 2001-09-01: 351.2752 |  | 4800 | 4800 | 2936.3452 | 4800 | 0 | 4899 | -1962.6548
2.1.7.1.1.3.1 | HTR Demonstrator ENG | 2000-03-01: 3203.2084; 2000-04-01: 1830.4048; 2000-05-01: 1084.7512; 2000-06-01: 7628.2256; 2000-07-01: 1017.9728; 2000-08-01: 5445.8768; 2000-09-01: 3543.4872; 2000-10-01: 2101.4008; 2000-11-01: 3897.7472; 2000-12-01: 8122.27; 2001-01-01: 975.42; 2001-02-01: 1842.27; 2001-03-01: -2480.28; 2001-06-01: -6426.0416; 2002-01-02: 8761.88 |  | 40548.5932 | 31786.7132 | 14767.6168 | 40584 | 35.4068 | 7695.39 | 7072.2268
2.1.7.1.1.3.2 | HTR Demonstrator M&S | 2000-09-01: 1474; 2001-02-01: 5399.06; 2001-03-01: 2.31; 2001-04-01: 2581.4884; 2001-05-01: -662.3784; 2001-06-01: 6068.13 |  | 14862.61 | 14862.61 | 9463.55 | 15000 | 137.39 | 12877.76 | -3414.21
2.1.7.1.1.4.1 | Prototype ENG | 2001-04-01: 5335.7552; 2001-06-01: 2012.8; 2001-07-01: 12470.32; 2001-09-01: 3695.1308; 2001-10-01: 35032.5072; 2001-11-01: 8863.2872 |  | 67409.8004 | 58546.5132 | 58546.5132 | 68520 | 1110.1996 | 19970.74 | 38575.7732
2.1.7.1.1.4.2 | PrototypeM&S | 2000-08-01: 494.4; 2000-12-01: 3875.1; 2001-01-01: 4488.28; 2001-04-01: 5929.3684; 2001-07-01: 6336.31; 2001-08-01: 2701.81; 2001-09-01: 1108.932; 2001-10-01: 265.588; 2001-11-01: 2635.8268 |  | 27835.6152 | 25199.7884 | 24705.3884 | 30000 | 2164.3848 | 30750 | -6044.6116
2.1.7.1.1.5.1 | 2nd Prototype ENG | 2001-08-01: 22169.42; 2001-11-01: 5899.3; 2001-12-01: 13964.9272; 2002-01-02: 7741.7008 |  | 49775.348 | 22169.42 | 0 | 50011.29 | 235.942 |  | 0
2.1.7.1.1.5.2 | 2nd PrototypeM&S | 2000-11-01: 2492.5; 2001-12-01: 6321.63; 2002-01-02: 4889.95; 2002-02-02: 1.82; 2002-03-02: 855.03 | 402.95 | 14963.88 | 2492.5 | 2492.5 | 20000 | 5036.12 |  | 2492.5
2.1.7.1.1.6.1 | HTR Production M&S | [26 empty] | 28994.39 | 28994.39 | 0 | 0 |  | -28994.39 |  | 0
2.1.7.1.1.6.2 | HTR Production ENG | 2002-02-02: 11567.1144; 2002-03-02: 14888.8972 | 78864.9752 | 105320.9868 | 0 | 0 | 110000 | 4679.0132 |  | 0
2.1.7.1.1.6.3 | HTR Production Shipping | [27 empty] | 0 | 0 | 0 | 3150 | 3150 |  | 0
2.1.7.9.1 | VME Pipeline Module Integration | 2002-01-02: 3255.7; 2002-02-02: 7712.21 |  | 10967.91 | 0 | 0 | 12000 | 1032.09 |  | 0
2.1.7.11.1.1 | Universal Tester ENG | 2000-04-01: 11398.972; 2000-06-01: 5226.6; 2000-09-01: 653.04; 2000-11-01: 1059.06; 2001-01-01: 13055.56; 2001-05-01: 10687.46; 2001-06-01: 17326.32; 2001-09-01: 376.988 |  | 59784 | 59784 | 54557.4 | 59784 | 0 | 56595.71 | -2038.31
2.1.7.11.1.2 | Universal Tester M&S | 2000-05-01: 247.5; 2000-06-01: 1048.44; 2000-10-01: 640; 2001-01-01: 1371.64; 2002-01-02: 195 |  | 3502.58 | 3307.58 | 2011.64 | 4000 | 497.42 | 3026.84 | -1015.2
2.1.7.11.1.5 | TTC Setup | 2000-05-01: 1778.2; 2000-06-01: 2771.4628; 2000-10-01: 1047.9; 2001-01-01: 101.454; 2001-02-01: 402.634 |  | 6101.6508 | 6101.6508 | 1551.988 | 9000 | 2898.3492 | 7481.35 | -5929.362
2.1.7.11.2.1 | FEE ENG | 2000-02-01: 3393.81; 2000-03-01: 7589.56; 2000-05-01: 8808.7; 2000-08-01: 2315.76; 2000-12-01: 7815.78; 2001-02-01: 6481.26; 2001-03-01: 4087.15; 2001-04-01: 7584.16 |  | 48076.18 | 48076.18 | 36951.72 | 50184 | 2107.82 | 32808.46 | 4143.26
2.1.7.11.2.2 | FEE M&S | 2000-02-01: 113.62; 2000-03-01: 383.75; 2000-06-01: 2904; 2000-08-01: 77.7; 2000-09-01: 1407.88; 2000-10-01: 293.34; 2000-12-01: 1120.8; 2001-02-01: 5684.03 |  | 11985.12 | 11985.12 | 9003.42 | 12500 | 514.88 | 10998.55 | -1995.13
2.1.7.12.1 | Demonstrator Integration | 2001-01-01: 12394.37; 2001-03-01: 7708.1152; 2001-09-01: 2161.7368 |  | 22264.222 | 22264.222 | 22264.222 | 24000 | 1735.778 | 24600 | -2335.778
2.1.7.13.1 | Integration |  |  |  |  | 13356.836 | 3380.0396 | 9264.4672 | 6751.8856 | 18965.342 | 7073.6472 | 6692.372 | 10754.642 | 7329.9072 | 5791.7376 | 6982.272 | 7329.9072 | 10163.2044 | 6958.1904 | 7081.6076 | 7693.7356 | 7570.3184 | 7951.9216 | 8134.5536 | 12201.6676 | 8675.5824 | 8675.5824 | 52125.452 | 240904.8716 | 143140.112 | 117138.7692 | 283785.61 | 42880.7384 | 116043.86 | 1094.9092
2.1.7.15.1 | SLB Trigger Link M&S | [27 empty] | 0 | 0 | 0 | 62600 |  |  | 0
2.1.7.15.2 | SLB Trigger Link ENG | [26 empty] | 12204.4056 | 12204.4056 | 0 | 0 | 21840 |  |  | 0
2.1.7.15.3 | SLB Transition Boards | [27 empty] | 0 | 0 | 0 | 66000 |  |  | 0
2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland | [26 empty] | 1452.5904 | 1452.5904
2.1.10.11.5 | Test BeamTRIDAS M&S | [26 empty] | 22357.4122 | 22357.4122
TOTAL |  | 3507.43 | 17316.1488 | 13633.2096 | 15703.0228 | 39362.6568 | 4431.2624 | 19501.854 | 14442.406 | 32382.634 | 22256.2208 | 29207.912 | 45360.5964 | 32800.7088 | 24558.7292 | 32060.4448 | 41955.1788 | 24496.458 | 33041.936 | 49839.1556 | -188.95 | 45769.7908 | 25812.9244 | 34968.4192 | 39541.4892 | 32673.0092 | 30655.8448 | 203880.4 | 908970.8924 | 541438.8056 | 417039.5172 | 947758.9 | 39221.142 | 406959.36 | 10080.1572
TOTAL Check |  | 3507.43 | 17316.1488 | 13633.2096 | 15703.0228 | 39362.6568 | 4431.2624 | 19501.854 | 14442.406 | 32382.634 | 22256.2208 | 29207.9128 | 45360.5964 | 32800.7088 | 24558.7292 | 32060.4448 | 41955.1788 | 24496.458 | 33041.936 | 49839.1556 | -188.95 | 45769.7908 | 25812.9244 | 34968.4192 | 39541.4892 | 32673.0092 | 30655.8448 | 203880.4
Difference |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.0008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.638e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fermilab Paid | 2001-05-01: 32037.28; 2001-06-01: 18464.62; 2001-08-01: 27669.74
|  | 2000-05-01 | 2000-06-01 | 2000-07-01 | 2000-08-01 | TOTAL
2.1.1.5.1.5 | Computing in building 186
2.1.1.8.6.9 | Travel | 2000-02-01: 1953.4668; 2000-03-01: 6427.0924; 2000-05-01: 1903.65; 2000-06-01: 10284.2092
2.1.7.1.1.1 | HTR Requirements Report | 2000-06-01: 0
2.1.7.1.1.2 | HTR Module Specification Report | 2000-02-01: 1830.4048; 2000-04-01: 33.25; 2000-06-01: 1863.6548
2.1.7.1.1.3.1 | HTR Demonstrator ENG | 2000-02-01: 1084.7512; 2000-03-01: 7628.2256; 2000-04-01: 1017.9728; 2000-05-01: 5445.8768; 2000-06-01: 15176.8264
2.1.7.1.1.3.2 | HTR Demonstrator M&S | 2000-06-01: 0
2.1.7.1.1.4.1 | Prototype ENG | 2000-06-01: 0
2.1.7.1.1.4.2 | PrototypeM&S | 2000-05-01: 494.4; 2000-06-01: 494.4
2.1.7.1.1.5.1 | 2nd Prototype ENG | 2000-06-01: 0
2.1.7.1.1.5.2 | 2nd PrototypeM&S | 2000-06-01: 0
2.1.7.1.1.6.1 | HTR Production M&S
2.1.7.1.1.6.2 | HTR Production ENG
2.1.7.1.1.6.3 | HTR Production Shipping
2.1.7.9.1 | VME Pipeline Module Integration
2.1.7.11.1.1 | Universal Tester ENG | 2000-03-01: 5226.6; 2000-06-01: 5226.6
2.1.7.11.1.2 | Universal Tester M&S | 2000-02-01: 247.5; 2000-03-01: 1048.44; 2000-06-01: 1295.94
2.1.7.11.1.5 | TTC Setup | 2000-02-01: 1778.2; 2000-03-01: 2771.4628; 2000-06-01: 4549.6628
2.1.7.11.2.1 | FEE ENG | 2000-02-01: 8808.7; 2000-05-01: 2315.76; 2000-06-01: 11124.46
2.1.7.11.2.2 | FEE M&S | 2000-03-01: 2904; 2000-05-01: 77.7; 2000-06-01: 2981.7
2.1.7.12.1 | Demonstrator Integration
2.1.7.13.1 | Integration | 2000-03-01: 13356.836; 2000-04-01: 3380.0396; 2000-05-01: 9264.4672; 2000-06-01: 26001.3428
2.1.7.15.1 | SLB Trigger Link M&S
2.1.7.15.2 | SLB Trigger Link ENG
2.1.7.15.3 | SLB Transition Boards
| TOTAL | 2000-02-01: 15703.0228; 2000-03-01: 39362.6568; 2000-04-01: 4431.2624; 2000-05-01: 19501.854; 2000-06-01: 78998.796
|  | May-Aug 00 | 2001-02-01 | 2001-05-01 | 2001-06-01 | 2001-08-01 | Total
2.1.1.5.1.5 | Computing in building 186 | 2000-02-01: 0; 2000-07-01: 0
2.1.1.8.6.9 | Travel | 2000-02-01: 10284.2092; 2000-04-01: 9957.8988; 2000-05-01: 6031.8436; 2000-07-01: 26273.9516
2.1.7.1.1.1 | HTR Requirements Report | 2000-02-01: 0; 2000-07-01: 0
2.1.7.1.1.2 | HTR Module Specification Report | 2000-02-01: 1863.6548; 2000-07-01: 1863.6548
2.1.7.1.1.3.1 | HTR Demonstrator ENG | 2000-02-01: 15176.8264; 2000-03-01: 1842.27; 2000-07-01: 17019.0964
2.1.7.1.1.3.2 | HTR Demonstrator M&S | 2000-02-01: 0; 2000-03-01: 5399.06; 2000-07-01: 5399.06
2.1.7.1.1.4.1 | Prototype ENG | 2000-02-01: 0; 2000-07-01: 0
2.1.7.1.1.4.2 | PrototypeM&S | 2000-02-01: 494.4; 2000-07-01: 494.4
2.1.7.1.1.5.1 | 2nd Prototype ENG | 2000-02-01: 0; 2000-06-01: 22169.42; 2000-07-01: 22169.42
2.1.7.1.1.5.2 | 2nd PrototypeM&S | 2000-02-01: 0; 2000-07-01: 0
2.1.7.1.1.6.1 | HTR Production M&S | 2000-02-01: 0; 2000-07-01: 0
2.1.7.1.1.6.2 | HTR Production ENG | 2000-02-01: 0; 2000-07-01: 0
2.1.7.1.1.6.3 | HTR Production Shipping | 2000-02-01: 0; 2000-07-01: 0
2.1.7.9.1 | VME Pipeline Module Integration | 2000-02-01: 0; 2000-07-01: 0
2.1.7.11.1.1 | Universal Tester ENG | 2000-02-01: 5226.6; 2000-07-01: 5226.6
2.1.7.11.1.2 | Universal Tester M&S | 2000-02-01: 1295.94; 2000-07-01: 1295.94
2.1.7.11.1.5 | TTC Setup | 2000-02-01: 4549.6628; 2000-07-01: 4549.6628
2.1.7.11.2.1 | FEE ENG | 2000-02-01: 11124.46; 2000-07-01: 11124.46
2.1.7.11.2.2 | FEE M&S | 2000-02-01: 2981.7; 2000-07-01: 2981.7
2.1.7.12.1 | Demonstrator Integration | 2000-02-01: 0; 2000-07-01: 0
2.1.7.13.1 | Integration | 2000-02-01: 26001.3428; 2000-07-01: 26001.3428
2.1.7.15.1 | SLB Trigger Link M&S | 2000-02-01: 0; 2000-07-01: 0
2.1.7.15.2 | SLB Trigger Link ENG | 2000-02-01: 0; 2000-07-01: 0
2.1.7.15.3 | SLB Transition Boards | 2000-02-01: 0; 2000-07-01: 0
TOTAL |  | 2000-02-01: 78998.796; 2000-03-01: 7241.33; 2000-04-01: 9957.8988; 2000-05-01: 6031.8436; 2000-06-01: 22169.42; 2000-07-01: 124399.2884

## Invoices Apr-Aug 02
Po Line # | CE | PO # | WKPKG | Item Description | Vendor Name | Gl Encumbered Date | TOTAL OBLG | Amt Billed | AMT REMAINING | Inv 33204-34 April | Inv 33204-35 May | Inv 33204-36 June | Inv 33204-37 July | Inv 33024- 38 August | Total
1 | 44 | 509604 | 4HKH | 2.1.1.1 - BARREL EDIA. | MARYLAND, UNIVERSITY OF | 1998-04-30 | 0 | 0 | 0
2 | 44 | 509604 | 4HKH | 2.1.10.4.3 - ACCELEROMETER (PPPI SHIPPING) EDIA AND M&S. | MARYLAND, UNIVERSITY OF | 1998-04-30 | 0 | 0 | 0
3 | 44 | 509604 | 4HKH | 2.1.7 - TRIGGER/DAQ. | MARYLAND, UNIVERSITY OF | 1998-04-30 | 0 | 0 | 0
4 | 43 | 509604 | 4HKD | 2.1.1.8.5 HCAL INSTALLATION INTEGRATION-FY97 | MARYLAND, UNIVERSITY OF | 2001-11-27 | 12808 | 12808 | 0
| 4H | 509604 | 4HKD | 2.1.1.8.5 HCAL INSTALLATION INTEGRATION-FY97 | MARYLAND, UNIVERSITY OF | 2001-11-27 | 78814 | 28330.06 | 50483.94
5 | 43 | 509604 | 4HKG | 2.1.10.4.3 - ACCELEROMETERS (PPPA SHIPPING) EDIA | MARYLAND, UNIVERSITY OF | 1998-08-21 10:32 | 4357.06 | 0 | 4357.06
6 | 43 | 509604 | 4HKH | 2.1.7 - TRIGGER/DAQ | MARYLAND, UNIVERSITY OF | 1998-08-21 10:32 | 30738.74 | 0 | 30738.74
| 4H | 509604 | 4HKH | 2.1.7 - TRIGGER/DAQ | MARYLAND, UNIVERSITY OF | 2000-04-13 15:27 | 0 | 0 | 0
7 | 43 | 509604 | 4HHD | 2.1.1.5.1.3 - BLDG PREP & INFRASTRUCTURE | MARYLAND, UNIVERSITY OF | 1999-02-08 10:29 | 0 | 0 | 0
8 | 43 | 509604 | 4HHE | 2.1.1.5.1.4 - INSTALLATION FIXTURES | MARYLAND, UNIVERSITY OF | 1999-02-08 10:29 | 0 | 0 | 0
9 | 43 | 509604 | 4HHF | 2.1.1.5.1.5 - WORKSTATIONS | MARYLAND, UNIVERSITY OF | 1999-02-08 10:29 | 0 | 0 | 0 | 1140.4 |  | 2766.9102 |  |  | 3907.3102
10 | 4H | 509604 | 4HHG | 2.1.1.8.6.9 - MARYLAND MGMT TRAVEL | MARYLAND, UNIVERSITY OF | 2001-11-27 | 44831 | 44831 | 0
| 4H | 509604 | 4HHG | 2.1.1.8.6.9 - MARYLAND MGMT TRAVEL | MARYLAND, UNIVERSITY OF | 2001-12-10 | 21495 | 18772.59 | 2722.41 | 279.054 | 936.7956 | 1525.1252 | 388.9736 | 440.966 | 3570.9144
| 43 | 509604 | 4HHG | 2.1.1.8.6.9 - MARYLAND MGMT TRAVEL | MARYLAND, UNIVERSITY OF | 2001-11-27 | 10286 | 10286 | 0
11 | 43 | 509604 | 4HHH | 2.1.10.1.6.4 - MOUNT ACCELEROMETERS | MARYLAND, UNIVERSITY OF | 2001-11-27 | 2057 | 0 | 2057
12 | 4H | 509604 | 4HHF | 2.1.7.1.1.2 - HTR MODULE SPECIFICATION - ADD LINE 12 | MARYLAND, UNIVERSITY OF | 2001-11-27 | 4899 | 4899 | 0
13 | 4H | 509604 | 4HHD | 2.1.1.5.1.3 - BLDG. PREP. & INFRASTRUCTURE | MARYLAND, UNIVERSITY OF | 2001-11-27 | 45000 | 1576.64 | 43423.36
14 | 4H | 509604 | 4HHE | 2.1.1.5.1.4 - INSTALLATION FIXTURES | MARYLAND, UNIVERSITY OF | 2001-08-30 | 0 | 0 | 0
15 | 4H | 509604 | 4HAR | 2.1.1.5.1.5 - WORKSTATIONS | MARYLAND, UNIVERSITY OF | 2001-11-27 | 50000 | 11816.54 | 38183.46
16 | 4H | 509604 | 4HAU | 2.1.7.11.1.1 - UNIVERSAL TESTER MODULE DESIGN & TESTING | MARYLAND, UNIVERSITY OF | 2001-11-27 | 58900 | 56595.71 | 2304.29
17 | 4H | 509604 | 4HAV | 2.1.7.11.1.2 - UNIVERSAL TESTER MODULE DESIGN M&S | MARYLAND, UNIVERSITY OF | 2001-11-27 | 3941 | 3026.84 | 914.16
18 | 4H | 509604 | 4HAW | 2.1.7.11.2.1 - FEE EMULATOR DESIGN & TESTING | MARYLAND, UNIVERSITY OF | 2001-12-10 | 742 | 0 | 742
| 4H | 509604 | 4HAW | 2.1.7.11.2.1 - FEE EMULATOR DESIGN & TESTING | MARYLAND, UNIVERSITY OF | 2001-11-27 | 49442 | 32808.46 | 16633.54
19 | 4H | 509604 | 4HAX | 2.1.7.11.2.2 - FEE EMULATOR M&S | MARYLAND, UNIVERSITY OF | 2001-12-10 | 185 | 0 | 185
| 4H | 509604 | 4HAX | 2.1.7.11.2.2 - FEE EMULATOR M&S | MARYLAND, UNIVERSITY OF | 2001-11-27 | 12315 | 10998.55 | 1316.45
20 | 4H | 509604 | 4HAY | 2.1.7.13.1 - TRIGGER/DAQ HCAL INTEGRATION | MARYLAND, UNIVERSITY OF | 2001-11-27 | 24805 | 24805 | 0
21 | 4J | 509604 | 4HSS | 2.1.7.1.1.4.1 - PROTOTYPE MODULE DESIGN & TESTING | MARYLAND, UNIVERSITY OF | 2001-12-10 | 424 | 0 | 424
| 4J | 509604 | 4HSS | 2.1.7.1.1.4.1 - PROTOTYPE MODULE DESIGN & TESTING | MARYLAND, UNIVERSITY OF | 2002-03-13 | 4052 | 0 | 4052
| 4J | 509604 | 4HSS | 2.1.7.1.1.4.1 - PROTOTYPE MODULE DESIGN & TESTING | MARYLAND, UNIVERSITY OF | 2001-11-27 | 66033 | 62073.98 | 3959.02
22 | 4J | 509604 | 4HSS | 2.1.7.1.1.4.2 - HTR PROTOTYPE MODULE M&S | MARYLAND, UNIVERSITY OF | 2001-11-27 | 16400 | 2635.83 | 13764.17
| 4J | 509604 | 4HSS | 2.1.7.1.1.4.2 - HTR PROTOTYPE MODULE M&S | MARYLAND, UNIVERSITY OF | 2001-12-10 | 14350 | 10763.92 | 3586.08
23 | 4J | 509604 | 4HSX | 2.1.7.11.1.5 - TTC AND LHC EMULATOR SETUP | MARYLAND, UNIVERSITY OF | 2001-11-27 | 9225 | 7481.35 | 1743.65
24 | 4J | 509604 | 4HSY | 2.1.7.12.1 - DEMONSTRATOR INTEGRATION TESTS (MARYLAND) | MARYLAND, UNIVERSITY OF | 2001-11-27 | 24600 | 24600 | 0
25 | 4J | 509604 | 4HAY | 2.1.7.13.1 - TRIGGER/DAQ HCAL DAQ/TRIGGER INTEGRATION (MARYLAND) | MARYLAND, UNIVERSITY OF | 2002-03-13 | 107613 | 0 | 107613 | 8675.5824 | 8675.5824 | 12497.0164 | 10959.5628 | 11317.708 | 52125.452
| 4J | 509604 | 4HAY | 2.1.7.13.1 - TRIGGER/DAQ HCAL DAQ/TRIGGER INTEGRATION (MARYLAND) | MARYLAND, UNIVERSITY OF | 2001-11-27 | 61935 | 61935 | 0
| 4J | 509604 | 4HAY | 2.1.7.13.1 - TRIGGER/DAQ HCAL DAQ/TRIGGER INTEGRATION (MARYLAND) | MARYLAND, UNIVERSITY OF | 2001-12-10 | 97008 | 38060.91 | 58947.09
26 | 4J | 509604 | 6HUT | 2.1.10.1.5.4 - MOUNT HB PPP1 ACCELEROMETERS | MARYLAND, UNIVERSITY OF | 2001-11-27 | 5182 | 0 | 5182
27 | 4J | 509604 | 6HUU | 2.1.7.1.1.3.1 - HTR DEMONSTRATOR MODULE DESIGN & TESTING | MARYLAND, UNIVERSITY OF | 2001-11-27 | 40584 | 7695.39 | 32888.61
28 | 4J | 509604 | 6HUU | 2.1.7.1.1.3.2 - HTR DEMONSTRATOR MODULE M&S | MARYLAND, UNIVERSITY OF | 2001-11-27 | 15000 | 12877.76 | 2122.24
29 | 4J | 509604 | 4HVO | 2.1.7.1.1.5.1 - HTR PROTOTYPE MODULE DESIGN & TESTING | MARYLAND, UNIVERSITY OF | 2002-03-13 | 52594 | 28068.72 | 24525.28
30 | 4J | 509604 | 4HVO | 2.1.7.1.1.5.2 - HTR PROTOTYPE MODULE M&S | MARYLAND, UNIVERSITY OF | 2002-03-13 | 21033 | 0 | 21033 | 402.95 |  |  |  |  | 402.95
31 | 4J | 509604 | 4HVP | 2.1.7.1.1.6.1 - HTR PRODUCTION MODULE M&S (10% SPARES) | MARYLAND, UNIVERSITY OF | 2002-03-13 | 303254 | 0 | 303254 |  | 23.49 | 14112.59 | 83.27 | 14775.04 | 28994.39
32 | 4J | 509604 | 4HVP | 2.1.7.5.1 - VME RELAY RACKS M&S (NO SPARES) | MARYLAND, UNIVERSITY OF | 2002-03-13 | 6310 | 0 | 6310
33 | 4J | 509604 | 4HVQ | 2.1.7.1.1.6.2 - HTR PRODUCTION MODULE ENGINEERING SUPPORT | MARYLAND, UNIVERSITY OF | 2002-03-13 | 20742 | 0 | 20742 | 12398.3372 | 14573.1472 | 18335.2508 | 15830.2236 | 17728.0164 | 78864.9752
34 | 4J | 509604 | 4HVR | 2.1.7.12.4 - PROTOTYPE INTEGRATION TESTS (MARYLAND) | MARYLAND, UNIVERSITY OF | 2002-03-13 | 42680 | 0 | 42680
35 | 4J | 509604 | 4HVS | 2.2.7.1.1 - HTR MODULE M&S (10% SPARES) | MARYLAND, UNIVERSITY OF | 2002-03-13 | 252712 | 0 | 252712
36 | 4J | 509604 | 4HVT | 2.3.7.1.1 - HTR MODULE M&S (10% SPARES) | MARYLAND, UNIVERSITY OF | 2002-03-13 | 303254 | 0 | 303254
37 | 4J | 509604 | 4HVU | 2.3.7.5 - VME RELAY RACKS M&S (NO SPARES) | MARYLAND, UNIVERSITY OF | 2002-03-13 | 6310 | 0 | 6310
38 | 4J | 509604 | 4HVV | 2.5.7.1.1 - HTR MODULE M&S (10% SPARES) | MARYLAND, UNIVERSITY OF | 2002-03-13 | 237549 | 137838.77 | 99710.23
39 | 4J | 509604 | 4HVW | 2.5.7.5 - VME RELAY RACKS M&S (NO SPARES) | MARYLAND, UNIVERSITY OF | 2002-03-13 | 3155 | 0 | 3155
Total: 961 | [6 empty] | 2167614.8 | 655586.02 | 1512028.78
|  |  |  | 2.1.5.14.2 - |  |  |  |  | 36808 |  |  | 43.3344 |  | 1409.256 | 1452.5904
|  |  |  | 2.1.10.11.5 |  |  |  |  | 42066 | 1890 |  | 18029.3122 |  | 2438.1 | 22357.4122
|  |  |  | 2.1.7.15.2 | [5 empty] | 2912.1516 | 2956.4776 |  | 6335.7764 |  | 12204.4056
[10 empty] | 27698.4752 | 27165.4928 | 67309.5392 | 33597.8064 | 48109.0864 | 203880.4
[10 empty] | Invoice Total | Invoice Total | Invoice Total | Invoice Total | Invoice Total
[10 empty] | 27698.47 | 27165.5 | 67309.54 | 33597.81 | 48109.1

## Engineering
WBS | Item | Spent | Allocated | Remaining
2.1.7.1.1.3.1 | HTR Demonstrator ENG | 40548.5932 | 40584 | 35.4068
2.1.7.1.1.4.1 | Prototype ENG | 67409.8004 | 68520 | 1110.1996
2.1.7.1.1.5.1 | 2nd Prototype ENG | 49775.348 | 50011.29 | 235.942
2.1.7.1.1.6.2 | HTR Production ENG | 105320.9868 | 110000 | 4679.0132
2.1.7.11.1.1 | Universal Tester ENG | 59784 | 59784 | 0
2.1.7.11.2.1 | FEE ENG | 48076.18 | 50184 | 2107.82
2.1.7.12.1 | Demonstrator Integration | 22264.222 | 24000 | 1735.778
2.1.7.13.1 | Integration | 240904.8716 | 283785.61 | 42880.7384
| TOTAL | 634084.002 | 686868.9 | 52784.898
| Graduate Student help | 36968.102

## 9715
9715
Labor | [11 empty] | Materials
Date | Bard | Baum | Breden | Giganti | Schaffer | Sharp | Touart | Total | Integral | PAID |  | Date | Type | Who | Cost | Integral | PAID | WBS
[8 empty] | 8118.72 | 8118.72 | [5 empty] | 1267.3 | 1267.3
1999-09-11 | 538.88 | [6 empty] | 538.88 | 8657.6 |  |  | 1999-11-22 | PC Connection | Bard | 1078 | 2345.3
1999-09-25 | 1077.76 | [6 empty] | 1077.76 | 9735.36 |  |  | 2000-02-01 | PC Cost | Bard | 113.62 | 2458.92 |  | 2.1.7.11.2.2
1999-10-09 | 1616.64 | [6 empty] | 1616.64 | 11352 |  |  | 2000-02-28 | Marshall Industries | Baum | 383.75 | 2842.67 | 2000-03-01 | 2.1.7.11.2.2
1999-10-23 | 867.6 | [6 empty] | 867.6 | 12219.6 |  |  | 2000-03-14 | Shipping | Baum | 16.7 | 2859.37 | 2000-04-01
1999-11-06 | 1156.8 | [6 empty] | 1156.8 | 13376.4 |  |  | 2000-03-17 | Black Box Cabling | Baum | 124.7 | 2984.07 | 2000-04-01
1999-11-20 | 1156.8 | [6 empty] | 1156.8 | 14533.2 |  |  | 2000-04-07 | DAWN VME | Baum | 61.46 | 3045.53 | 2000-04-01
1999-12-04 | 867.6 | [6 empty] | 867.6 | 15400.8 |  |  | 2000-04-21 | Vitesse | Touart | 247.5 | 3293.03 | 2000-05-01
1999-12-18 | 723 | [6 empty] | 723 | 16123.8 |  |  |  | COMPUSA | Baden | 324 | 3617.03 |  | 2.1.7.1.1.1
2000-01-01 | 582.8 | [6 empty] | 582.8 | 16706.6 |  |  |  | COMPUSA | Baden | 2261 | 5878.03 |  | 2.1.7.1.1.2
2000-01-15 | 1457 | [6 empty] | 1457 | 18163.6 | 2000-02-01 | 2.1.7.11.2.1 | 2000-05-05 | DAWN VME | Baum | 1656 | 7534.03 | May-Aug 00
2000-01-29 | 874.2 | [6 empty] | 874.2 | 19037.8 | 2000-02-01 | 2.1.7.11.2.1 | 2000-05-05 | Shipping | Baum | 80.3 | 7614.33 | May-Aug 00
2000-02-12 | 1457 | 174.04 |  |  |  |  | 796 | 2427.04 | 21464.84 | 2000-03-01 | 2.1.7.11.2.1 | 2000-08-08 | misc | Touart | 3.7 | 7618.03 | 2000-08-01
2000-02-26 | 1748.4 | 261.06 | [5 empty] | 2009.46 | 23474.3 | 2000-03-01 | 2.1.7.11.2.1 | 2000-11-14 | methode optical stuff | Bard | 2459.5 | 10077.53 | 2000-11-01
2000-03-11 | 2039.8 | 130.53 | [5 empty] | 2170.33 | 25644.63 | 2000-04-01 | 2.1.7.11.1.1 | 2000-11-14 | dept surcharge | Bard | 33 | 10110.53 | 2000-11-01
2000-03-25 | 1457 | [6 empty] | 1457 | 27101.63 | 2000-04-01 | 2.1.7.11.1.1 | 2000-12-15 | VME CPU computer | Bard | 3842.1 | 13952.63 | 2000-12-01
2000-04-08 | 1457 | 130.53 | [5 empty] | 1587.53 | 28689.16 | 2000-05-01 |  | 2000-12-15 | dept surcharge | Bard | 33 | 13985.63 | 2000-12-01
2000-04-22 | 1748.4 | 43.51 |  |  | 169.4 | 5 |  | 1966.31 | 30655.47 | 2000-05-01 |  | Total |  |  | 10077.53
2000-05-06 | 1748.4 |  | 200.12 |  |  |  |  | 1948.52 | 32603.99 | 2000-06-01
2000-05-20 | 1748.4 | [6 empty] | 1748.4 | 34352.39 | 2000-06-01
2000-06-03 | 1457 |  |  | 371.91 |  |  |  | 1828.91 | 36181.3 | 2000-06-01
2000-07-01 | [6 empty] | 489.1 | 489.1 | 36670.4 | 2000-08-01
2000-08-26 |  |  |  | 653.04 |  |  |  | 653.04 | 37323.44 | 2000-09-01
2000-09-09 |  |  |  | 136.06 |  |  |  | 136.06 | 37459.5 | 2000-12-01
2000-10-07 |  |  |  | 625.84 |  |  |  | 625.84 | 38085.34 | 2000-12-01
TOTAL | 25780.48 | 739.67 | 200.12 | 1786.85 | 169.4 | 5 | 1285.1 | 38085.34

## 9725
[11 empty] | 9725 |  | 01-433204
Labor | [13 empty] | Materials
Date | Bard | Baum | Breden | Giganti | Kleber | McQueen | Touart | Schaeffer | MDG | Total | Integral | PAID |  | Date | Type | Who | Cost | Billed | Summed
[10 empty] | 4922.84 | 4922.84 |  |  | 2000-04-07 | Advanced Circuits | Touart | 812.25 | 2000-04-01
1999-08-14 |  |  |  | 239.09 | [5 empty] | 239.09 | 5161.93 |  |  | 2000-04-24 | DKS | Touart | 41.9
1999-09-11 |  |  |  | 717.26 | [5 empty] | 717.26 | 5879.19 |  |  | 2000-05-19 | DKC | Touart | 5.89 | 2000-06-01
1999-09-25 |  |  |  | 956.34 | [5 empty] | 956.34 | 6835.53 |  |  | 2000-05-22 | misc | Touart | 1042.55 | 2000-06-01
1999-10-09 |  |  |  | 850.08 | [5 empty] | 850.08 | 7685.61 |  |  | 2000-07-25 | software | McQueen | 33.25 | 2000-07-01
1999-10-23 |  |  |  | 544.58 | [5 empty] | 544.58 | 8230.19 |  |  | 2000-08-08 | leds | Grassi | 1.6 | 2000-08-01
1999-11-06 |  |  |  | 611 | [5 empty] | 611 | 8841.19 |  |  | 2000-09-07 | ???? | ???? | 1474
1999-11-20 |  |  |  | 531.3 | [5 empty] | 531.3 | 9372.49 |  |  | 2000-09-12 | allied | Z | 181.37
1999-12-04 |  |  |  | 345.35 | [5 empty] | 345.35 | 9717.84 |  |  | 2000-09-22 | 20k400 | Hans | 1226.51
1999-12-18 |  |  |  | 611 | [5 empty] | 611 | 10328.84 |  |  | 2000-09-27 | DKC | Z | 228.61 | 2000-10-01
2000-01-01 | [9 empty] | 0 | 10328.84 |  |  | 2000-09-28 | Black Box | Z | 80.33 | 2000-10-01
2000-01-15 |  |  |  | 504.74 | [5 empty] | 504.74 | 10833.58 | 2000-02-01 | 2.1.7.11.2.1 | 2000-10-06 | Freight |  | -15.6 | 2000-10-01
2000-01-29 |  |  |  | 557.87 | [5 empty] | 557.87 | 11391.45 | 2000-02-01 | 2.1.7.11.2.1 | 2000-11-08 | 2 FPGA etc for HTR | Hans | 2099.86 | 2000-11-01
2000-02-12 |  |  |  | 876.65 | [5 empty] | 876.65 | 12268.1 | 2000-03-01 | 2.1.7.11.2.1 | 2000-11-14 | VME stuff | Grassi | 1059.06 | 2000-11-01
2000-02-26 |  |  |  | 982.91 |  |  | 1293.5 |  |  | 2276.41 | 14544.51 | 2000-03-01 | 2.1.7.11.2.1 | 2000-12-15 | Wyle | Z | 1083.38 | 2000-12-01
2000-03-11 |  |  |  | 1195.43 |  |  | 2388 |  |  | 3583.43 | 18127.94 | 2000-04-01 | 2.1.7.11.1.1 | 2000-12-15 | dept surcharge |  | 37.42 | 2000-12-01
2000-03-25 |  |  |  | 345.35 |  |  | 1393 |  |  | 1738.35 | 19866.29 | 2000-04-01 | 2.1.7.11.1.1 | 2000-12-21 | Misc for HTR/FEE |  | 942.42 | 2001-01-01
2000-04-08 |  |  |  | 1647.03 |  |  | 1442.75 |  |  | 3089.78 | 22956.07 | 2000-05-01 |  | 2000-12-21 | dept surcharge |  | 33 | 2001-01-01
2000-04-22 |  |  |  | 796.95 |  |  | 1368.13 |  |  | 2165.08 | 25121.15 | 2000-05-01 |  | 2001-01-08 | Caps | Breden | 128.03 | 2001-01-01
2000-05-06 |  |  |  | 584.43 |  |  | 149.25 |  |  | 733.68 | 25854.83 | 2000-06-01 |  | 2001-01-08 | dept surcharge | Breden | 33 | 2001-01-01 | 161.03
2000-05-20 | [6 empty] | 796 |  |  | 796 | 26650.83 | 2000-06-01 |  | 2001-01-11 | Limo connectors (50) etc | Baum | 1172.59 | 2001-01-01
2000-06-03 | [6 empty] | 398 |  |  | 398 | 27048.83 | 2000-06-01 |  | 2001-01-11 | dept surcharge | Baum | 38.02 | 2001-01-01 | 1210.61
2000-06-17 | 1748.4 | 137.97 |  | 690.69 | [5 empty] | 2577.06 | 29625.89 | 2000-06-01 |  | 2001-01-31 | Misc for HTR/FEE | Grassi/Breden | 1213.49 | 2001-02-01
2000-07-01 | 1748.4 | 135.45 |  | 371.91 | 60 |  |  |  |  | 2315.76 | 31941.65 | 2000-07-01 |  | 2001-01-31 | dept surcharge |  | 53.63 | 2001-02-01
2000-07-15 | 1616.56 | 90.3 |  | 680.26 |  |  | 49.49 |  |  | 2436.61 | 34378.26 | 2000-07-01 |  | 2001-02-01 | Misc for HTR/FEE | Baum/Breden | 482.64 | 2001-02-01
2000-07-29 |  | 90.3 | [7 empty] | 90.3 | 34468.56 | 2000-07-01 |  | 2001-02-01 | dept surcharge |  | 56.48 | 2001-02-01
2000-08-12 | [9 empty] | 0 | 34468.56 |  |  | 2001-02-02 | Misc for HTR/FEE | Baum | 36.03 | 2001-02-01
2000-08-26 | 1469.6 | [8 empty] | 1469.6 | 35938.16 | 2000-09-01 |  | 2001-02-23 | Misc for HTR/FEE | Baum/Breden | 5480.96 | 2001-02-01
2000-09-09 | 2057.44 | 45.15 | 810.4 | [6 empty] | 2912.99 | 38851.15 | 2000-12-01 |  | 2001-02-23 | Freight |  | 178.77 | 2001-02-01
2000-09-23 | 2057.44 | 225.75 | 2228.6 | [6 empty] | 4511.79 | 43362.94 | 2000-12-01 | 7424.78 | 2001-02-23 | dept surcharge |  | 24.3 | 2001-02-01
2000-10-07 | 1763.52 |  | 1013 | [6 empty] | 2776.52 | 46139.46 | 2000-12-01 |  | 2001-03-02 | Misc for HTR/FEE | Breden | 2.31 | 2001-03-01
2000-10-21 | 2351.36 |  | 810.4 | 1251.66 | [5 empty] | 4413.42 | 50552.88 | 2000-12-01 | 7189.94 | 2001-03-30 | Misc for HTR/FEE | Breden | 189.41 | 2001-04-01
2000-11-04 | 2498.32 |  | 557.15 | 761.88 | [5 empty] | 3817.35 | 54370.23 | 2001-01-01 |  | 2001-04-04 | Freight |  | 8.66 | 2001-04-01
2000-11-18 | 2438.4 |  | 2245.46 | [6 empty] | 4683.86 | 59054.09 | 2001-01-01 |  | 2001-04-04 | dept surcharge |  | 21.95 | 2001-04-01
2000-12-02 | 2743.2 |  | 1149.96 | [6 empty] | 3893.16 | 62947.25 | 2001-01-01 | 12394.37 | 2001-04-05 | DIMM/EPROM/TTL-ECL |  | 436.29 | 2001-04-01
2000-12-16 | 2438.4 |  | 2190.4 | [6 empty] | 4628.8 | 67576.05 | 2001-01-01 |  | 2001-04-05 | Freight |  | 24.18 | 2001-04-01
2000-12-30 | 1219.2 |  | 219.04 | [6 empty] | 1438.24 | 69014.29 | 2001-01-01 | 6067.04 | 2001-04-05 | dept surcharge |  | 99 | 2001-04-01
2001-01-13 | 2133.6 |  | 2354.68 | [6 empty] | 4488.28 | 73502.57 | 2001-01-01 | 4488.28 | 2001-04-06 | Misc for HTR/FEE | US Electronics | 156 | 2001-04-01
2001-01-27 | 3048 | 194.44 | 2847.52 | 761.88 | [5 empty] | 6851.84 | 80354.41 | 2001-01-01 | 6851.84 | 2001-04-06 | Misc computer equip | PC Connection | 1113.85 | 2001-04-01
2001-01-27 | [8 empty] | 136.68 | 136.68 | 80491.09 | 2001-01-01 | 136.68 | 2001-04-06 | memory | Crucial | 286.17 | 2001-04-01
2001-02-10 | 2743.2 |  | 2655.86 | [6 empty] | 5399.06 | 85890.15 | 2001-02-01 |  | 2001-04-06 | dept surcharge |  | 99 | 2001-04-01
2001-02-24 | 3344.8 |  | 2599.2 | 163.26 |  | 374 |  |  |  | 6481.26 | 92371.41 | 2001-02-01 |  | 2001-04-06 | Freight |  | 77.67 | 2001-04-01 | 2512.18
2001-03-10 | 3344.8 |  | 3091.68 |  |  | 924 |  |  |  | 7360.48 | 99731.89 | 2001-03-01 |  | 2001-04-30 | credit |  | -1053.33 | 2001-05-01
2001-03-24 | 2341.36 | 50.41 | 1313.28 | 272.1 |  | 110 |  |  |  | 4087.15 | 103819.04 | 2001-03-01 |  | 2001-05-03 | Misc computer equip |  | 200 | 2001-05-01
2001-04-07 | 3344.8 | 100.82 | 1094.4 | 272.1 |  | 176 |  |  |  | 4988.12 | 108807.16 | 2001-04-01 |  | 2001-05-03 | Freight |  | 20.05 | 2001-05-01
2001-04-21 | 3344.8 |  | 3447.36 |  |  | 792 |  |  |  | 7584.16 | 116391.32 | 2001-04-01 |  | 2001-05-03 | dept surcharge |  | 57.75 | 2001-05-01
2001-05-05 | 3344.8 |  | 3009.6 | 544.2 |  | 88 |  |  |  | 6986.6 | 123377.92 | 2001-05-01 |  | 2001-05-04 | Misc for HTR/FEE |  | 499.41 | 2001-05-01
2001-05-19 |  |  | 3009.6 | 163.26 |  | 528 |  |  |  | 3700.86 | 127078.78 | 2001-05-01 |  | 2001-05-04 | Freight |  | 43.74 | 2001-05-01
2001-06-02 | 6355.12 | 50.41 | 2954.88 |  |  |  |  | 132.65 |  | 9493.06 | 136571.84 | 2001-06-01 |  | 2001-05-04 | dept surcharge |  | 75.6 | 2001-05-01 | 896.55
2001-06-16 | 3048 | 100.82 | 3064.32 | 163.26 |  | 1364 |  | 92.86 |  | 7833.26 | 144405.1 | 2001-06-01 |  | 2001-05-29 | Misc stuff |  | 391.53 | 2001-06-01
2001-06-30 |  | 50.41 | 2407.68 |  |  | 550 |  |  |  | 3008.09 | 147413.19 | 2001-07-01 |  | 2001-05-29 | VME Crate | DAWN VME | 4613 | 2001-06-01
2001-07-14 |  |  | 1749 |  | 25.75 | 100.5 |  | 149.88 |  | 2025.13 | 149438.32 | 2001-07-01 |  | 2001-05-29 | Freight |  | 143.46 | 2001-06-01
2001-07-28 |  |  | 2756 | 454.5 |  | 201 |  |  |  | 3411.5 | 152849.82 | 2001-07-01 |  | 2001-05-29 | dept surcharge |  | 112.96 | 2001-06-01
2001-08-11 | 4961.28 |  | 3339 | 151.5 |  | 536 |  |  | 206 | 9193.78 | 162043.6 | 2001-08-01 |  | 2001-05-30 | Transmitters | Agilent | 597 | 2001-06-01
2001-08-25 | 3100.8 | 242.5 | 3286 | 656.5 |  | 1038.5 |  |  |  | 8324.3 | 170367.9 | 2001-08-01 |  | 2001-05-30 | Freight |  | 15 | 2001-06-01
2001-09-08 | 2790.72 |  | 3339 | 303 |  | 703.5 |  | 354.25 |  | 7490.47 | 177858.37 | 2001-10-01 |  | 2001-05-30 | dept surcharge |  | 33 | 2001-06-01
2001-09-22 | 6201.6 | 48.5 | 3763 | 353.5 |  | 904.5 |  |  |  | 11271.1 | 189129.47 | 2001-10-01 |  | 2001-05-31 | Misc for HTR/FEE |  | 76.01 | 2001-06-01 | 5981.96
2001-10-06 |  |  | 3180 | 227.26 |  | 837.5 |  |  |  | 4244.76 | 193374.23 | 2001-10-01 |  | 2001-06-14 | Misc for HTR/FEE | Grassi | 86.17 | 2001-06-01
2001-10-20 | 5581.44 | 48.5 | 3365.5 | 151.5 |  | 1005 |  | 81.75 |  | 10233.69 | 203607.92 | 2001-10-01 |  | 2001-06-25 | Misc for HTR/FEE | Breden | 51.08 | 2001-08-01
2001-11-03 | 3100.8 |  | 3233 |  |  | 737 |  |  |  | 7070.8 | 210678.72 | 2001-11-01 |  | 2001-06-29 | Misc for HTR/FEE | Nu Horizons | 147 | 2001-08-01
2001-11-17 | 3100.8 |  | 1961 |  |  | 837.5 |  |  |  | 5899.3 | 216578.02 | 2001-11-01 |  | 2001-06-29 | Misc for HTR/FEE | Insight | 338.3 | 2001-08-01
2001-12-01 | 2480.64 |  | 2332 |  |  | 670 | 103 |  |  | 5585.64 | 222163.66 | 2001-12-01 |  | 2001-06-29 | Freight |  | 13.32 | 2001-08-01
2001-12-15 | 3100.8 |  | 3047.5 |  |  | 435.5 |  |  |  | 6583.8 | 228747.46 | 2001-12-01 |  | 2001-06-29 | dept surcharge |  | 66 | 2001-08-01 | 615.7
2001-12-29 | 1240.32 |  | 1484 |  |  |  |  | 531.38 |  | 3255.7 | 232003.16 | 2002-01-01 |  | 2001-07-09 | Misc for HTR/FEE |  | 20.5 | 2001-07-01
2002-01-12 | 2572.16 |  | 3270 | 934.26 |  | 168.75 |  |  |  | 6945.17 | 238948.33 | 2002-01-02 |  | 2001-07-16 | HTR | Data Circuit | 2628.15 | 2001-07-01
2002-01-26 | 2893.68 |  | 3433.5 |  |  | 270 |  | 272.5 |  | 6869.68 | 245818.01 | 2002-01-02 |  | 2001-07-16 | Testfixture | Data Circuit | 905.23 | 2001-07-01
2002-02-09 | 3215.2 | 102 | 2834 |  |  | 270 | 436 |  |  | 6857.2 | 252675.21 | 2002-02-02 |  | 2001-07-16 | FEE | Data Circuit | 1918.5 | 2001-07-01
2002-02-23 | 3215.2 |  | 3433.5 | 498.38 |  | 33.75 | 218 | 313.38 |  | 7712.21 | 260387.42 | 2002-02-02 |  | 2001-07-16 | Testfixture | Data Circuit | 797.93 | 2001-07-01
2002-03-09 | 3215.2 |  | 3460.76 |  |  | 202.5 |  |  |  | 6878.46 | 267265.88 | 2002-03-02 |  | 2001-07-16 | dept surcharge |  | 66 | 2001-07-01 | 6315.81
2002-03-23 | 3215.2 |  | 2834 |  |  | 168.75 |  |  |  | 6217.95 | 273483.83 | 2002-03-02 |  | 2001-08-01 | TI Eval module | TI | 750 | 2001-08-01
2002-04-06 | 2250.64 |  | 1798.5 |  |  | 135 |  |  |  | 4184.14 | 277667.97 | 2002-04-02 |  | 2001-08-01 | Books | Amazon | 79.95 | 2001-08-01
2002-04-20 | 3215.2 |  | 2970.26 |  |  | 236.25 |  |  |  | 6421.71 | 284089.68 | 2002-04-02 |  | 2001-08-01 | Freight |  | 4.48 | 2001-08-01
2002-05-04 | 3215.2 |  | 3324.5 |  |  | 405 |  |  |  | 6944.7 | 291034.38 | 2002-05-02 |  | 2001-08-01 | dept surcharge |  | 59.38 | 2001-08-01
2002-05-18 | 3215.2 | 102 | 2316.26 |  |  | 202.5 |  |  |  | 5835.96 | 296870.34 | 2002-05-02 |  | 2001-08-02 | SSOP Test Clip | Newark/Baum | 385 | 2001-08-01
2002-06-01 | [8 empty] | 530.02 | 530.02 | 297400.36 | 2002-06-01 |  | 2001-08-02 | Freight |  | 35 | 2001-08-01
2002-06-01 | 2893.68 | 408 | 2398 |  |  | 540 |  |  |  | 6239.68 | 303110.02 | 2002-06-02 |  | 2001-08-02 | dept surcharge |  | 33 | 2001-08-01 | 1346.81
2002-06-15 | 3215.2 | 201.68 | 3316.09 |  |  | 597.06 |  |  |  | 7330.03 | 310440.05 | 2002-06-02 |  | 2001-08-08 | HTR Boards+CHIP KIT | CR | 1289 | 2001-08-01
2002-06-29 | [8 empty] | 72 | 72 | 310512.05 | 2002-07-02 |  | 2001-08-08 | dept surcharge |  | 66 | 2001-08-01 | 1355
2002-06-29 | 3215.2 | 403.36 | 3100.41 | 367.22 |  | 597.06 |  |  |  | 7683.25 | 318195.3 | 2002-07-02 |  | 2001-08-17 | EDM wire beta cut |  | 5.02 | 2001-08-01
2002-07-13 | 2925.72 | 102.72 | 1765.12 | 314.76 |  | 826.32 |  |  | 147.78 | 6082.42 | 324277.72 | 2002-07-02 |  | 2001-08-22 | EDM wire beta cut |  | 5.02 | 2001-08-01
2002-07-27 | [8 empty] | 420 | 420 | 318615.3 | 2002-08-02 |  | 2001-08-30 | Transceivers | Finisar | 338 | 2001-09-01
2002-07-27 | 1625.4 |  | 3107.51 |  |  | 724.5 |  |  |  | 5457.41 | 329735.13 | 2002-08-02 |  | 2001-08-30 | Transceivers | Finisar | 338 | 2001-09-01
2002-08-10 |  |  | 3245 |  |  | 379.5 |  |  |  | 3624.5 | 333359.63 | 2002-08-02 |  | 2001-08-30 | Books | Amazon | 166 | 2001-09-01
2002-08-24 | 2600.64 |  | 2640 | 643.12 |  | 276 |  |  |  | 6159.76 | 339519.39 | 2002-08-02 |  | 2001-08-30 | Freight |  | 20.56 | 2001-09-01
2002-09-07 | 2985.84 | 101.92 | 3282.6 |  |  | 136.84 |  |  |  | 6507.2 | 346026.59 | 2002-09-01 |  | 2001-08-30 | dept surcharge |  | 66 | 2001-09-01
2002-09-21 | 2985.84 |  | 3009.05 |  |  | 667.1 |  |  |  | 6661.99 | 352688.58 | 2002-09-01 |  | 2001-08-30 | HTR Boards Assembly | CR | 450 | 2001-09-01
2002-10-05 | 3317.6 |  | 2078.98 |  |  | 307.89 |  |  |  | 5704.47 | 358393.05 | 2002-10-01 |  | 2001-08-30 | dept surcharge |  | 33 | 2001-09-01 | 1073.56
2002-10-19 | 3200.54 |  |  | 78.76 |  | 410.52 | 492.39 |  |  | 4182.21 | 362575.26 | 2002-10-01 |  | 2001-10-05 | Fiber cables/plugs | Allied/ComCable | 144.92 | 2001-10-01
2002-11-02 | 6303.44 | 50.96 | 2626.08 |  |  | 273.68 |  |  |  | 9254.16 | 371829.42 | 2002-11-01 |  | 2001-10-05 | Freight |  | 27.56 | 2001-10-01
2002-11-16 | 3317.6 | 611.52 | 3638.22 |  |  | 273.68 |  |  |  | 7841.02 | 379670.44 | 2002-11-01 |  | 2001-10-05 | dept surcharge |  | 47.82 | 2001-10-01 | 220.3
2002-11-30 | 2654.08 | 458.64 | 1914.85 |  |  | 581.57 |  |  |  | 5609.14 | 385279.58 | 2002-12-01 |  | 2001-11-06 | Xilinx FPGA | Nu Horizons | 2240.1 | 2002-11-01
2002-12-14 | 2985.84 | 1070.16 | 2735.5 |  |  | 376.31 |  |  | 51.75 | 7219.56 | 392499.14 | 2002-12-01 |  | 2001-11-06 | dept surcharge |  | 33 | 2002-11-01
2002-12-18 | 1997.28 | 559.46 | 1586.59 |  |  | 581.57 |  |  | 290.11 | 5015.01 | 397514.15 |  |  | 2001-11-06 | Freight |  | 19.95 | 2002-11-01
2003-01-11 | 2332.4 | 666.12 | 2738 |  |  | 376.86 |  |  | 987.31 | 7100.69 | 404614.84 |  |  | 2001-11-09 | misc | McQueen | 4.14 | 2002-11-01 | 2297.19
2003-01-25 | 3002.4 | 530 | 3339 |  |  | 396 |  |  |  | 7267.4 | 411882.24 |  |  | 2001-11-16 | misc |  | 49.06 | 2002-11-01
2003-02-08 | 3002.4 | 1166 | 3127 |  |  | 576 |  |  |  | 7871.4 | 419753.64 |  |  | 2001-12-11 | circuit boards | CR | 2982.17 | 2002-12-01
2003-02-22 | 2335.2 | 901 | 2411.5 |  |  | 576 |  |  |  | 6223.7 | 425977.34 |  |  | 2001-12-11 | Books | Amazon | 139.95 | 2002-12-01
2003-03-08 | 3336 | 742 | 3180 |  |  | 540 |  |  | 1825 | 9623 | 435600.34 |  |  | 2001-12-11 | SMA connectors | Pasternack | 459.93 | 2002-12-01
2003-03-22 | 3336 |  | 3206.5 |  |  | 360 |  |  | 676.51 | 7579.01 | 443179.35 |  |  | 2001-12-13 | Aldec | Baden | 365 | 2002-12-01
TOTAL | 191993.9 | 9789.27 | 170030.75 | 24128.08 | 85.75 | 25379.46 | 10527.51 | 1928.65 | 5343.16 | 444129.37 | 444129.37 |  |  | 2001-12-13 | FPGA | Arrow | 952 | 2002-12-01
[14 empty] | 2001-12-13 | misc | Breden | 961.67 | 2002-12-01
Including 9715 | 217774.38 | 10528.94 | 170230.87 | 25914.93 | 85.75 | 25379.46 | 11812.61 | 2098.05 | 5343.16 | 477286.87 |  |  |  | 2001-12-13 | Freight |  | 185.78 | 2002-12-01
[14 empty] | 2001-12-13 | dept surcharge |  | 275.13 | 2002-12-01 | 6321.63
| 3764.5863 | [12 empty] | 2002-01-15 | Stratos Rx (24) | Bard | 2256 | 2002-01-02
| 72052.48 | [12 empty] | 2002-01-15 | Agilent scope parts | Grassi | 656 | 2002-01-02
| 92175.5714 | 4473.1886 | 84849.9971 | 3511.8571 | 0 | 11217.799 | 1419.34 | 725.3752 | 1512.3952 | 107709.9524 |  |  |  | 2002-01-15 | HTR prototype CR | Breden | 1800 | 2002-01-02
[14 empty] | 2002-01-15 | CMS computer memory | McQueen | 195 | 2002-01-02
[14 empty] | 2002-01-15 | Freight |  | 45.95 | 2002-01-02
[14 empty] | 2002-01-15 | dept surcharge |  | 132 | 2002-01-02 | 5084.95
[14 empty] | 2002-01-29 | capacitor | Schaeffer | 0.91 | 2002-02-02
[14 empty] | 2002-02-01 | capacitor | Schaeffer | 0.91 | 2002-02-02
[14 empty] | 2002-03-06 | Misc for HTR (inc. TI parts) | Baum | 710.43 | 2002-03-02
[14 empty] | 2002-03-06 | Freight |  | 45.6 | 2002-03-02
[14 empty] | 2002-03-06 | dept surcharge |  | 99 | 2002-03-02 | 855.03
[14 empty] | 2002-04-10 | W-TEK | Baum | 1890 | 2002-04-02 |  | TI prototype boards
[14 empty] | 2002-04-10 | CMS computer | Baum | 1140.4 | 2002-04-02 |  | "Aaron special"
[14 empty] | 2002-04-10 | Freight |  | 143.87 | 2002-04-02
[14 empty] | 2002-04-10 | DKC misc |  | 47.11 | 2002-04-02
[14 empty] | 2002-04-11 | Chip resistors | Baum | 85 | 2002-04-02
[14 empty] | 2002-04-12 | Misc for HTR | Breden | 12.42 | 2002-04-02 | 3318.8
[14 empty] | 2002-04-26 | Misc for HTR | Breden | 8.43 | 2002-05-02
[14 empty] | 2002-05-03 | Misc for HTR | Breden | 8.24 | 2002-05-02
[14 empty] | 2002-05-17 | Misc for HTR | Bard | 6.82 | 2002-05-04
[14 empty] | 2002-05-28 | Parts for HTR | Breden | 3356.02 | 2002-06-02
[14 empty] | 2002-05-28 | Freight |  | 37.47 | 2002-06-02
[14 empty] | 2002-05-24 | Parts for HTR | Breden | 9.99 | 2002-06-02
[14 empty] | 2002-05-28 | dept surcharge |  | 66 | 2002-06-02
[14 empty] | 2002-05-29 | Parts for HTR | Breden | 3291.91 | 2002-06-02
[14 empty] | 2002-05-29 | Freight |  | 104.83 | 2002-06-02
[14 empty] | 2002-05-29 | dept surcharge |  | 132 | 2002-06-02
[14 empty] | 2002-05-31 | CMS computer | Breden | 1240.73 | 2002-06-02
[14 empty] | 2002-05-31 | Parts for HTR | Breden | 77.05 | 2002-06-02
[14 empty] | 2002-05-31 | HTR boards | Breden | 4646.56 | 2002-06-02
[14 empty] | 2002-05-31 | TLK eval board | Breden | 799 | 2002-06-02
[14 empty] | 2002-05-31 | Freight |  | 110.61 | 2002-06-02
[14 empty] | 2002-05-31 | dept surcharge |  | 107.53 | 2002-06-02 | 13979.7
[14 empty] | 2002-06-07 | Parts for HTR | Breden | 88.99 | 2002-06-02
[14 empty] | 2002-06-07 | Parts for HTR | Breden | 44.2 | 2002-06-02 | 133.19
[14 empty] | 2002-07-16 | Parts for emulator | Breden | 54.19 | 2002-07-01
[14 empty] | 2002-07-17 | EDM wire beta cut | Baum | 29.08 | 2002-07-02
[14 empty] | 2002-07-24 | Parts for HTR | Breden | 889 | 2002-08-02
[14 empty] | 2002-07-24 | JTAG | Bard | 695 | 2002-08-02
[14 empty] | 2002-07-24 | shipping |  | 61.68 | 2002-08-02
[14 empty] | 2002-07-24 | Freight |  | 27.3 | 2002-08-02
[14 empty] | 2002-07-24 | dept surcharge |  | 86.35 | 2002-08-02
[14 empty] | 2002-07-25 | Parts for HTR | Breden | 4676 | 2002-08-02
[14 empty] | 2002-07-25 | Freight |  | 64 | 2002-08-02
[14 empty] | 2002-07-25 | dept surcharge |  | 66 | 2002-08-02
[14 empty] | 2002-07-26 | Parts for HTR | Breden | 511.34 | 2002-08-02
[14 empty] | 2002-07-26 | Freight |  | 33.55 | 2002-08-02
[14 empty] | 2002-07-26 | dept surcharge |  | 108.58 | 2002-08-02
[14 empty] | 2002-08-20 | Parallel IV cable | Breden | 220 | 2002-08-02
[14 empty] | 2002-08-20 | Parts for HTR | Breden | 642.3 | 2002-08-02
[14 empty] | 2002-08-20 | 50 dual LC | Breden | 4750 | 2002-08-02
[14 empty] | 2002-08-20 | 25 TI TLK1501 | Breden | 575 | 2002-08-02
[14 empty] | 2002-08-20 | Freight |  | 120.39 | 2002-08-02
[14 empty] | 2002-08-20 | dept surcharge |  | 237.53 | 2002-08-02
[14 empty] | 2002-08-21 | Parts for HTR | Breden | 673.25 | 2002-08-02
[14 empty] | 2002-08-21 | Freight |  | 158.42 | 2002-08-02
[14 empty] | 2002-08-20 | dept surcharge |  | 179.35 | 2002-08-02 | 14775.04
[14 empty] | 2002-09-11 | HTR boards | Cranbury | 4800 | 2002-09-01
[14 empty] | 2002-09-11 | Xilinx FPGA V2 pro |  | 812 | 2002-09-01
[14 empty] | 2002-09-11 | Parts for HTR | Breden | 117.5 | 2002-09-01
[14 empty] | 2002-09-11 | Freight |  | 40.63 | 2002-09-01
[14 empty] | 2002-09-11 | dept surcharge |  | 99 | 2002-09-01
[14 empty] | 2002-09-13 | Parts for HTR | Breden | 1.5 | 2002-09-01
[14 empty] | 2002-09-13 | Latitude notebook for testbeam | Baum | 2481.48 | 2002-09-01
[14 empty] | 2002-09-13 | dept surcharge |  | 33 | 2002-09-01 | 8385.11 | 5903.63
[14 empty] | 2002-10-15 | Xilinx stuff | Baum | 300 | 2002-10-01
[14 empty] | 2002-10-15 | Parts for HTR | Baum | 298.72 | 2002-10-01
[14 empty] | 2002-10-15 | FedEx from CERN |  | 37.43 | 2002-10-01
[14 empty] | 2002-10-15 | Freight |  | 48.02 | 2002-10-01
[14 empty] | 2002-10-15 | dept surcharge |  | 124.91 | 2002-10-01
[14 empty] | 2002-10-16 | FedEx from CERN |  | 27.54 | 2002-10-01 | 836.62
[14 empty] | 2002-11-27 | HTR board | Cranbury | 690 | 2002-11-01
[14 empty] | 2002-11-27 | Xilinx FPGA |  | 1803 | 2002-11-01
[14 empty] | 2002-11-27 | Parts for HTR | Baum | 220.13 | 2002-11-01
[14 empty] | 2002-11-27 | Freight |  | 43.15 | 2002-11-01
[14 empty] | 2002-11-27 | dept surcharge |  | 99 | 2002-11-01 | 2855.28
[14 empty] | 2002-12-19 | disk drive for lab computer |  | 105
[14 empty] | 2002-12-19 | Freight |  | 11.9
[14 empty] | 2002-12-19 | dept surcharge |  | 33
[14 empty] | 2003-01-06 | stiffeners |  | 11.32
[14 empty] | 2003-01-06 | dept surcharge |  | 15.96
[14 empty] | 2003-01-13 | credit from MWAVE |  | -116.9
[14 empty] | 2003-01-24 | disk drive for lab computer |  | 105
[14 empty] | 2003-01-24 | Parts for HTR |  | 196.68
[14 empty] | 2003-01-24 | Freight |  | 41.4
[14 empty] | 2003-01-24 | dept surcharge |  | 75.46
[14 empty] | 2003-02-25 | stiffeners |  | 11.6
[14 empty] | 2003-02-25 | dept surcharge |  | 6.38
[14 empty] | 2003-02-27 | stiffeners |  | 57.2
[14 empty] | 2003-02-27 | EDG built computer |  | 1308.61
[14 empty] | 2003-02-27 | Freight |  | 70.61
[14 empty] | 2003-02-27 | dept surcharge |  | 51.88
[14 empty] | 2003-02-28 | VME connectors |  | 20
[14 empty] | 2003-02-28 | dept surcharge |  | 6.6
[14 empty] | 2003-03-03 | stiffeners |  | 1.39
[14 empty] | 2003-03-03 | dept surcharge |  | 6.38
[14 empty] | 2003-03-06 | stiffeners |  | 2
[14 empty] | 2003-03-06 | dept surcharge |  | 3.19
[14 empty] | 2003-03-11 | TTC Boards (Linsang) |  | 3925.2
[14 empty] | 2003-03-11 | dept surcharge |  | 33
[14 empty] | 2003-03-12 | stiffeners |  | 2.5
103972.84
5684.03

## Travel
Overhead | 0.48
| Travel |  |  | Overhead
Date | Domestic | Foreign | Total | Domestic | Foreign | Total | Total
2001-01-01 | 690.5 | 808.98 | 1499.48 | 331.44 | 388.3104 | 719.7504 | 2219.2304
2001-02-01 | 1495.53 | 2329.84 | 3825.37 | 717.8544 | 1118.3232 | 1836.1776 | 5661.5476
2001-03-01 | 3220.36 | 3164.57 | 6384.93 | 1545.7728 | 1518.9936 | 3064.7664 | 9449.6964
2001-04-01 | 1505.05 | 959.41 | 2464.46 | 722.424 | 460.5168 | 1182.9408 | 3647.4008
2001-05-01 | 1958.63 | 4769.68 | 6728.31 | 940.1424 | 2289.4464 | 3229.5888 | 9957.8988
2001-06-01 | 781.61 | 3293.96 | 4075.57 | 375.1728 | 1581.1008 | 1956.2736 | 6031.8436
2001-07-01 | 185 | 4731.97 | 4916.97 | 88.8 | 2271.3456 | 2360.1456 | 7277.1156
2001-08-01 | 0 | 1325.72 | 1325.72 | 0 | 636.3456 | 636.3456 | 1962.0656
2001-09-01 | 230.3 | 4.5 | 234.8 | 110.544 | 2.16 | 112.704 | 347.504
2001-10-01 | 0 | 1960.39 | 1960.39 | 0 | 940.9872 | 940.9872 | 2901.3772
2001-11-01 | 312.56 | 0 | 312.56 | 150.0288 | 0 | 150.0288 | 462.5888
2001-12-01 | 536.18 | 1933.15 | 2469.33 | 257.3664 | 927.912 | 1185.2784 | 3654.6084
TOTAL | 10915.72 | 25282.17 | 36197.89 | 5239.5456 | 12135.4416 | 17374.9872 | 53572.8772

## Cost 5_02
Channels/Fiber | 3
Spares | 0.2
| 24 Channel/8 Fiber HTR |  |  |  | 48 Channel/16 Fiber |  |  | DCC | 6200
Item | Number | Unit | Cost | Item | Number | Unit | Cost | HTR | 5126
FPGA | 1 | 1200 | 1200 | FPGA | 2 | 1200 | 2400 | VME cr | 5500
PC Board | 1 | 400 | 400 | PC Board | 1 | 500 | 500 | VME rack | 3000
Fab & Assy | 1 | 400 | 400 | Fab & Assy | 1 | 400 | 400 | TPGcable | 100
Rx chips | 8 | 36 | 288 | Rx chips | 16 | 36 | 576 | SLB | 100
LVDS | 1 | 25 | 25 | LVDS | 2 | 25 | 50 | SLB_HEX | 300
Connectors | 1 | 200 | 200 | Connectors | 1 | 200 | 200 | "HRC" | 1500
Optical-to-electrical | 8 | 32.5 | 260 | Optical-to-electrical | 16 | 40 | 640 | Bit3 | 3551
TTCrx and circuitry | 1 | 60 | 60 | TTCrx and circuitry | 1 | 160 | 160 | RackComp | 1500
Misc | 1 | 200 | 200 | Misc | 1 | 200 | 200
Total |  |  | 3033 | Total |  |  | 5126
SLB | 1 | 100 | 100
DCC | 1 | 6200 | 6200 |  | Bit3:
HRC | 1 | 1500 | 1500 |  | 620 | 3311 | both cards
VME Crate | 1 | 5500 | 5500 |  | 15-101 | 90 | 10m fiber
VME Rack | 1 | 3000 | 3000 |  | 400-202 | 150 | 128M dpram
TPG Cable | 1 | 80 | 80 |  |  | 3551
TPG Connection Cable | 2 | 20 | 40
Test Stands
1 crate | 5500
1 Rack Computer | 1500
1 Bit3 | 3551
2 HTR | 10252
1 TTC fanout | 1500
1 DCC | 6200
Total | 28503
| HB | HE | HO | HF | Total
HTR
Cards | 54 | 54 | 48 | 38 | 194
Spare Cards | 11 | 11 | 10 | 8 | 39
Spare Parts
Cost |  |  |  |  | 1194.358
SLB
Cards | 288 | 216 | 0 | 18 | 522
Spares | 58 | 43 | 0 | 4 | 104
Cost |  |  |  |  | 62.6
SLB_HEX
Cards | 54 | 54 | 0 | 38 | 146
Spares | 11 | 11 | 0 | 8 | 29
Cost |  |  |  |  | 52.5
TPG
Cables | 288 | 216 | 0 | 18 | 522
Cost |  |  |  |  | 52.2
VME
Racks | 2 | 2 | 2 | 2 | 8
Cost |  |  |  |  | 24
Rack Computer | 2 | 2 | 2 | 2 | 8
Cost |  |  |  |  | 12
Crates | 5 | 4 | 4 | 3 | 16
Cost |  |  |  |  | 88
Bit3 | 5 | 4 | 4 | 3 | 16
Cost |  |  |  |  | #REF!
DCC
Cards | 10 | 8 | 8 | 6 | 32
Spare Cards | 2 | 2 | 2 | 1 | 7
Spare Parts
Cost |  |  |  |  | 241.8
Fanout Card
Cards | 5 | 4 | 4 | 3 | 16
Spare Cards | 1 | 1 | 1 | 1 | 3
Spare Parts
Cost |  |  |  |  | 28.5
Total Costs |  |  |  |  | #REF!
Note on H12: Drew Baden: add $100 for xtal
Note on H11: Drew Baden: these are the x2, not the x4 parts
Note on H6: Drew Baden: more expensive due to all the constant impedance characteristics, etc.
Note on B39: Drew Baden: 20% cards, 10% commercial parts
Note on B64: Drew Baden: 20% cards, 10% commercial parts
Note on B69: Drew Baden: 20% cards, 10% commercial parts
Note on L3: Drew Baden: $5.7k for DCC, $500 for S-Link64
Note on G63: Drew Baden: BU wants 7 spares
Note on B46: Drew Baden: same numbers as HTRs if HO is put into the trigger

## Cost 12_11
ENGINEERING
| Tullio Grassi | Amount | FY03 Budget | Needed
| Biweekly pay period | 5658.854
| Yearly based on 26 pay periods | 147130.204 | 147130.204
| Amount for FY 2003 + rest of 2003 | 183912.755 |  | 183912.755
Rob Bard
| Average yearly based on first 9 months of 2002 | 61514.2171 | 61514.2171
| Amount for FY 2003 + rest of 2003 | 76892.7714 |  | 76892.7714
"SHOP"
| Average yearly based on first 9 months of 2002 | 80833.8638 | 80833.8638 | 80833.8638
| Amount for FY 2003 + rest of 2003 | 101042.3298
Ardash
| Biweekly pay period | 1033.1732
| Amount for 36 semester weeks | 18597.1176
| Maryland engineering |  | 289478.285 | 341639.3902
| Boston Engineering | 84600
Engineering Monies Remaining |  |  |  |  | From CPR |  |  | WBS Expended
WBS | Maryland | BAC infl | Complete | Remaining | Remains | BAC infl | ACWP | Billed | Remaining | BAC
2.1.7.1.1.5.1 | 2nd HTR Prototype Module Design & Testing | 52594.2808 | 80% | 10518.8562 | 52594.2808 | 52594.2808 | 0 | 49775.348 | 2818.9328 | 50011.2
2.1.7.1.1.6.2 | HTR Production Module Engineering Support | 118166.6578 | 0% | 118166.6578 | 118166.6578 | 118166.6578 | 0 | 105320.9868 | 12845.671 | 110052
2.1.7.4.2 | VME Crates Engineering Support | 7498.9636 | 0% | 7498.9636 | 7498.9636 | 7498.9636 | 0 | 0 | 7498.9636 | 6984
2.1.7.5.2 | VME Relay Racks Engineering Support | 2641.3874 | 0% | 2641.3874 | 2641.3874 | 2641.3874 | 0 | 0 | 2641.3874 | 2400
2.1.7.6.2 | Level 1 Trigger Links Engineering Support | 7267.0369 | 0% | 7267.0369 | 7267.0369 | 7267.0369 | 0 | 0 | 7267.0369 | 6768
2.1.7.12.4 | Prototype Integration Tests (Maryland) | 42680.1655 | 12% | 37558.5457 | 42680.1655 | 42680.1655 | 0 | 0 | 42680.1655 | 40584
2.1.7.13.1 | Trigger/DAQ HCAL DAQ/Trigger Integration (Maryland) | 291501.3988 | 36% | 186560.8953 | 166328.3988 | 291501.3988 | 125173 | 240904.8716 | 50596.5272 | 283200
2.1.7.13.11 | TRIDAS Engineering FY02,FY03 (Maryland) | 127504.735 | 0% | 127504.735 | 127504.735 | 127504.735 | 0 | 0 | 127504.735 | 120000
2.1.7.9.1 | VME Pipeline Module Integration | 12884.8171 | 0% | 12884.8171 | 12884.8171 | 12884.8171 | 0 | 10967.91 | 1916.9071 | 12000
2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland | 36807.7517 | 0% | 36807.7517 | 36807.7517 | 36807.7517 | 0 | 1452.5904 | 35355.1613 | 35000
2.1.10.11.5 | Test BeamTRIDAS M&S | 42066.0019 | 0% | 42066.0019 | 42066.0019 | 42066.0019 | 0 | 22357.4122 | 19708.5897 | 40000
| Total |  |  | 589475.6484 | 616440.1965 | 741613.1965 | 125173 | 430779.119 | 310834.0776 | 706999.2
Princeton
2.1.7.10.6.2 | Crate Fanout Production Module Engineering Support | 25648 | 0% | 25648
| Boston |  |  |  | From Hazen 11/02
2.1.7.3.4.1 | DCC Prototype Module Design & Testing | 53200 | 80% | 10640 | 53810.5036 | 54606.2224 | 795.7188
2.1.7.3.5.1 | DCC Prototype Module Design & Testing | 54667.2 | 0% | 54667.2 | 57490.7635
2.1.7.3.6.2 | DCC Production Module Engineering Support | 10780 | 0% | 10780 | 11336.7875
2.1.7.11.3.2 | DCC Module Software Development | 22831.2 | 80% | 4566.24 | 8154.0803 | 22891.8801 | 14737.7998
2.1.7.12.5 | Prototype Integration Tests (Boston) | 16912 | 80% | 3382.4 | 17785.5056
| Total | 158390.4 |  | 84035.84 | 148577.6405 | 77498.1025
MATERIALS
HTR
WBS | Item | BAC | BAC infl | Current | Difference (BAC) | Difference (BAC infl)
2.1.7.1.1.6.1 | HTR (HB) Production Module M&S (10% Spares) | 270100 | 290015.7588 | 337938 | -67838 | -47922.2412 | 268648.008
2.2.7.1.1 | HTR (HO) Module M&S (10% Spares) | 179162 | 192372.4671 | 263674 | -84512 | -71301.5329 | 209610.9194
2.3.7.1.1 | HTR (HE) Module M&S (10% Spares) | 231232 | 248281.8361 | 292860 | -61628 | -44578.1639 | 232812.6924
2.5.7.1.1 | HTR (HF) Module M&S (10% Spares) | 142002 | 152472.4834 | 196606 | -54604 | -44133.5166 | 156294.3802
| TOTAL HTR | 822496 | 883142.5454 | 1091078 | -268582 | -207935.4546 | 867366
SHIP HTR
2.1.7.1.1.6.3 | Ship HTR Production Module to CERN (HB) | 3150 | 3382.2645 | 1620 | 1530 | 1762.2645
2.2.7.1.3 | Ship HTR Modules to CERN (HO) | 0 | 0 | 1260 | -1260 | -1260
2.3.7.1.3 | Ship HTR Module to CERN (HE) | 3150 | 3382.2645 | 1400 | 1750 | 1982.2645
2.5.7.1.3 | Ship HTR Module to CERN (HF) | 3150 | 3382.2645 | 940 | 2210 | 2442.2645
| TOTAL HTR SHIPPING | 9450 | 10146.7935 | 5220 | 4230 | 4926.7935
DCC
2.1.7.3.6.1 | DCC (HB) Module M&S (10% Spares) | 105400 | 110843.915 | 68000 | 37400 | 42843.915
2.2.7.3.1 | Data Concentrator ( HO) M&S (10% Spares) | 62000 | 66571.5551 | 40000 | 22000 | 26571.5551
2.3.7.3.1 | Data Concentrator M&S (10% Spares) | 62000 | 66571.5551 | 40000 | 22000 | 26571.5551
2.5.7.3.1 | Data ConcentratorModule M&S (20% Spares) | 43400 | 45641.6121 | 28000 | 15400 | 17641.6121
| TOTAL DCC | 272800 | 289628.6373 | 176000 | 96800 | 113628.6373
FANOUT CARD
2.1.7.10.6.1 | Crate Fanout Production Module M&S (20% Spares) | 16500 | 17716.6235 | 16500 | 0 | 1216.6235
2.2.7.10.1 | Crate Fanout Production Module M&S (10% Spares) | 7500 | 8053.0107 | 7500 | 0 | 553.0107
2.3.7.10.1 | Crate Fanout Production Module M&S (10% Spares) | 7500 | 8053.0107 | 7500 | 0 | 553.0107
2.5.7.8.1 | Crate Fanout Production Module M&S (10% Spares) | 6000 | 6442.4086 | 6000 | 0 | 442.4086
| TOTAL Fanout | 37500 | 40265.0535 | 37500 | 0 | 2765.0535
SHIP DCC
2.1.7.3.6.3 | Ship DCC Module to CERN | 0 | 0 | 170 | -170 | -170
2.2.7.3.3 | Ship Data Concentrator Modules to CERN | 0 | 0 | 100 | -100 | -100
2.3.7.3.3 | Ship Data Concentrator Module to CERN | 0 | 0 | 100 | -100 | -100
2.5.7.3.3 | Ship Data Concentrator Module to CERN | 0 | 0 | 70 | -70 | -70
| TOTAL DCC SHIPPING | 0 | 0 | 440 | -440 | -440
VME CRATES
2.1.7.4.1 | VME Crates (HB) (no spares) | 45255 | 48591.8666 | 45255 | 0 | 3336.8666
2.2.7.4.1 | VME Crates (HO) M&S | 36204 | 38873.4933 | 36204 | 0 | 2669.4933
2.3.7.4.1 | VME Crates (HE) M&S | 36204 | 38873.4933 | 36204 | 0 | 2669.4933
2.5.7.4.1 | VME Crates (HF) M&S | 27153 | 29155.1199 | 27153 | 0 | 2002.1199
| TOTAL VME Crates | 144816 | 155493.973 | 144816 | 0 | 10677.973
VME RACKS | [6 empty] | "MISC" stuff
2.1.7.5.1 | VME Relay Racks (HB) M&S (no Spares) | 9000 | 9663.6128 | 9000 | 0 | 663.6128 |  | SLB PMC | 100
2.2.7.5 | VME Relay Racks (HO) M&S | 9000 | 9663.6128 | 9000 | 0 | 663.6128 |  | vme crystal | 5
2.3.7.5 | VME Relay Racks (HE) M&S (no Spares) | 9000 | 9663.6128 | 9000 | 0 | 663.6128 |  | vme connectors | 30
2.5.7.5 | VME Relay Racks ( HF) M&S (no Spares) | 9000 | 9663.6128 | 9000 | 0 | 663.6128 |  | vme buffers | 20
| TOTAL RACKS | 36000 | 38654.4514 | 36000 | 0 | 2654.4514 |  | front panel/extractors | 100
[8 empty] | stiffeners | 30
SLB | [7 empty] | labor | 50
2.1.7.15.1 | SLB Trigger Links (all) M&S (20% Spares) | 143750 | 151174.6943 | 143750 | 0 | 7424.6943 |  | misc electrical | 100
2.1.7.15.3 | SLB Trigger Links Transition Boards (all) | 66000 | 70866.4942 | 0 | 66000 | 70866.4942 |  |  | 435
| TOTAL SLB | 209750 | 222041.1885 | 143750 | 66000 | 78291.1885
TPG CABLES
2.1.7.6.1 | Level 1 Trigger Links M&S (20% Spares) (HB) | 100800 | 108232.4638 | 47520 | 53280 | 60712.4638
2.2.7.11.3 | HO Trigger Link Production (includes SLB) | 30000 | 32212.0428 | 33700 | -3700 | -1487.9572
2.3.7.6.1 | Level 1 Trigger Links M&S (20% Spares) (HE) | 75600 | 81174.3479 | 35640 | 39960 | 45534.3479
2.5.7.6.1 | Level 1 Trigger Links M&S (20% Spares) (HF) | 6300 | 6764.529 | 2970 | 3330 | 3794.529
| TOTAL TPG CABLES | 212700 | 228383.3835 | 119830 | 92870 | 108553.3835
SHIP FANOUT CARD
2.1.7.10.6.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 110 | -110 | -110
2.2.7.10.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 50 | -50 | -50
2.3.7.10.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 50 | -50 | -50
2.5.7.8.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 40 | -40 | -40
| TOTAL FANOUT SHIPPING | 0 | 0 | 250 | -250 | -250
| TOTAL COST | 1745512 | 1867756.0261 | 1754884 | -9372 | 112872.0261
| HTR Boards to Build for CMS Running | Raw Data | Calibration | Total
| HB | 54 | 5 | 59
| HE | 54 | 4 | 58
| HO | 48 | 4 | 52
| HF | 36 | 3 | 39
| HB | 59 | 20% | 12 |  | Needed |  | Extra | 10 | Spares |  | Total
| Item | Number | Unit | Cost | Spares | Parts | Cost | Parts | Cost | Parts | Cost | Parts | Cost
| Xilinx Virtex 3000 | 2 | 743 | 1486 | 20% | 118 | 87674 | 20 | 14860 | 24 | 17832 | 162 | 120366
| Xilinx Virtex 2000 | 0 | 472 | 0 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dual LC Optical-Electrical | 8 | 99 | 792 | 30% | 472 | 46728 | 80 | 7920 | 144 | 14256 | 696 | 68904
| 8-way Optical ports | 2 | 165 | 330 | 20% | 118 | 19470 | 20 | 3300 | 24 | 3960 | 162 | 26730
| TLK2501 RX chips | 16 | 13 | 208 | 30% | 944 | 12272 | 160 | 2080 | 288 | 3744 | 1392 | 18096
| TTCrx | 1 | 50 | 50 | 20% | 59 | 2950 | 10 | 500 | 12 | 600 | 81 | 4050
| Altera FPGA | 1 | 22 | 22 | 20% | 59 | 1298 | 10 | 220 | 12 | 264 | 81 | 1782
| TTC mezzanine board | 1 | 100 | 100 | 20% | 59 | 5900 | 10 | 1000 | 12 | 1200 | 81 | 8100
| Crystal | 1 | 25 | 25 | 20% | 59 | 1475 | 10 | 250 | 12 | 300 | 81 | 2025
| Misc (buffers, connectors…) | 1 | 435 | 435 | 20% | 59 | 25665 | 10 | 4350 | 12 | 5220 | 81 | 35235
| PCB | 1 | 300 | 300 | 20% | 59 | 17700 | 10 | 3000 | 12 | 3600 | 81 | 24300
| Fab/Assembly | 1 | 350 | 350 | 20% | 59 | 20650 | 10 | 3500 | 12 | 4200 | 81 | 28350
| Total for HTR |  |  | 4098 |  |  | 241782 |  | 40980 |  | 55176 |  | 337938
| HE | 58 | 20% | 12 |  | Needed |  | Extra | 0 | Spares |  | Total
| Item | Number | Unit | Cost | Spares | Parts | Cost | Parts | Cost | Parts | Cost | Parts | Cost
| Xilinx Virtex 3000 | 2 | 743 | 1486 | 20% | 116 | 86188 | 0 | 0 | 24 | 17832 | 140 | 104020
| Xilinx Virtex 2000 | 0 | 472 | 0 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dual LC Optical-Electrical | 8 | 99 | 792 | 30% | 464 | 45936 | 0 | 0 | 144 | 14256 | 608 | 60192
| 8-way Optical ports | 2 | 165 | 330 | 20% | 116 | 19140 | 0 | 0 | 24 | 3960 | 140 | 23100
| TLK2501 RX chips | 16 | 13 | 208 | 30% | 928 | 12064 | 0 | 0 | 288 | 3744 | 1216 | 15808
| TTCrx | 1 | 50 | 50 | 20% | 58 | 2900 | 0 | 0 | 12 | 600 | 70 | 3500
| Altera FPGA | 1 | 22 | 22 | 20% | 58 | 1276 | 0 | 0 | 12 | 264 | 70 | 1540
| TTC mezzanine board | 1 | 100 | 100 | 20% | 58 | 5800 | 0 | 0 | 12 | 1200 | 70 | 7000
| Crystal | 1 | 25 | 25 | 20% | 58 | 1450 | 0 | 0 | 12 | 300 | 70 | 1750
| Misc (buffers, connectors…) | 1 | 435 | 435 | 20% | 58 | 25230 | 0 | 0 | 12 | 5220 | 70 | 30450
| PCB | 1 | 300 | 300 | 20% | 58 | 17400 | 0 | 0 | 12 | 3600 | 70 | 21000
| Fab/Assembly | 1 | 350 | 350 | 20% | 58 | 20300 | 0 | 0 | 12 | 4200 | 70 | 24500
| Total for HTR |  |  | 4098 |  |  | 237684 |  | 0 |  | 55176 |  | 292860
| HF | 39 | 20% | 8 |  | Needed |  | Extra | 0 | Spares |  | Total
| Item | Number | Unit | Cost | Spares | Parts | Cost | Parts | Cost | Parts | Cost | Parts | Cost
| Xilinx Virtex 3000 | 2 | 743 | 1486 | 20% | 78 | 57954 | 0 | 0 | 16 | 11888 | 94 | 69842
| Xilinx Virtex 2000 | 0 | 472 | 0 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dual LC Optical-Electrical | 8 | 99 | 792 | 30% | 312 | 30888 | 0 | 0 | 96 | 9504 | 408 | 40392
| 8-way Optical ports | 2 | 165 | 330 | 20% | 78 | 12870 | 0 | 0 | 16 | 2640 | 94 | 15510
| TLK2501 RX chips | 16 | 13 | 208 | 30% | 624 | 8112 | 0 | 0 | 192 | 2496 | 816 | 10608
| TTCrx | 1 | 50 | 50 | 20% | 39 | 1950 | 0 | 0 | 8 | 400 | 47 | 2350
| Altera FPGA | 1 | 22 | 22 | 20% | 39 | 858 | 0 | 0 | 8 | 176 | 47 | 1034
| TTC mezzanine board | 1 | 100 | 100 | 20% | 39 | 3900 | 0 | 0 | 8 | 800 | 47 | 4700
| Crystal | 1 | 25 | 25 | 20% | 39 | 975 | 0 | 0 | 8 | 200 | 47 | 1175
| Misc (buffers, connectors…) | 1 | 435 | 435 | 20% | 39 | 16965 | 0 | 0 | 8 | 3480 | 47 | 20445
| PCB | 1 | 300 | 300 | 20% | 39 | 11700 | 0 | 0 | 8 | 2400 | 47 | 14100
| Fab/Assembly | 1 | 350 | 350 | 20% | 39 | 13650 | 0 | 0 | 8 | 2800 | 47 | 16450
| Total for HTR |  |  | 4098 |  |  | 159822 |  | 0 |  | 36784 |  | 196606
| HO | 52 | 20% | 11 |  | Needed |  | Extra | 0 | Spares |  | Total
| Item | Number | Unit | Cost | Spares | Parts | Cost | Parts | Cost | Parts | Cost | Parts | Cost
| Xilinx Virtex 3000 | 2 | 743 | 1486 | 20% | 104 | 77272 | 0 | 0 | 22 | 16346 | 126 | 93618
| Xilinx Virtex 2000 | 0 | 472 | 0 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dual LC Optical-Electrical | 8 | 99 | 792 | 30% | 416 | 41184 | 0 | 0 | 132 | 13068 | 548 | 54252
| 8-way Optical ports | 2 | 165 | 330 | 20% | 104 | 17160 | 0 | 0 | 22 | 3630 | 126 | 20790
| TLK2501 RX chips | 16 | 13 | 208 | 30% | 832 | 10816 | 0 | 0 | 264 | 3432 | 1096 | 14248
| TTCrx | 1 | 50 | 50 | 20% | 52 | 2600 | 0 | 0 | 11 | 550 | 63 | 3150
| Altera FPGA | 1 | 22 | 22 | 20% | 52 | 1144 | 0 | 0 | 11 | 242 | 63 | 1386
| TTC mezzanine board | 1 | 100 | 100 | 20% | 52 | 5200 | 0 | 0 | 11 | 1100 | 63 | 6300
| Crystal | 1 | 25 | 25 | 20% | 52 | 1300 | 0 | 0 | 11 | 275 | 63 | 1575
| Misc (buffers, connectors…) | 1 | 435 | 435 | 20% | 52 | 22620 | 0 | 0 | 11 | 4785 | 63 | 27405
| PCB | 1 | 300 | 300 | 20% | 52 | 15600 | 0 | 0 | 11 | 3300 | 63 | 18900
| Fab/Assembly | 1 | 350 | 350 | 20% | 52 | 18200 | 0 | 0 | 11 | 3850 | 63 | 22050
| Total for HTR |  |  | 4098 |  |  | 213096 |  | 0 |  | 50578 |  | 263674
1091078
| Boards | 208
| Spares | 43
| Extras | 10 |  |  |  |  | 939432
| Total | 261 |  | Total Cost |  |  | 855422
| Xilinx Virtex 3000 | 522 | 743 | 387846 | BU |  | 84010
| Xilinx Virtex 2000 | 0 | 472 | 0 |  |  | 0
| Dual LC Optical-Electrical | 2260 | 99 | 223740 | BU
| 8-way Optical ports | 522 | 165 | 86130 | BU?
| TLK2501 RX chips | 4520 | 13 | 58760 | Allied
| TTCrx | 261 | 50 | 13050 | 69 | 330 | Bit3:
| Altera FPGA | 261 | 22 | 5742 | N/A |  | 620 | 3311 | both cards
| TTC mezzanine board | 261 | 100 | 26100 |  |  | 15-101 | 90 | 10m fiber
| Crystal | 261 | 25 | 6525 | N/A |  | 400-202 | 150 | 128M dpram
| Misc (buffers, connectors…) | 261 | 435 | 113535 | Allied |  |  | 3551
| PCB | 261 | 300 | 78300 | BU
| Fab/Assembly | 261 | 350 | 91350 | BU
|  |  |  | 1091078 | 867366 | 0.79496 | 223712
| SLB (for cal TPG) | 6 | 250 | 1500 | 10%
| SLB (for muon bits) | [6 empty] | 192300
| Fanout Card | 1 | 1500 | 1500 | 20% |  |  | 108780
| DCC | 1 | 4000 | 4000 | 20% |  |  | 83520
| VME Crate | 1 | 5500 | 5500
| VME Rack | 1 | 3000 | 3000
| TPG Cable | 1 | 135 | 135 |  | 9 | 15
| TPG Connection Cable | 2 | 15 | 30
| Muon fiber | 1 | 100 | 100
| Bit3 | 1 | 3551 | 3551
| Rack computer | 1 | 1500 | 1500
| Shipping | 1 | 10 | 10
|  | HB | HE | HO | HF | Total
| HTR | 4098 | 4098 | 4098 | 4098
| Cards | 59 | 58 | 52 | 39 | 208
| Cost | 241782 | 237684 | 213096 | 159822 | 852384
| Spare Cards + Extra | 81 | 70 | 63 | 47 | 261
| Spare Cards + Extra + Spare Parts | 96156 | 55176 | 50578 | 36784 | 238694
| TOTAL COST | 337938 | 292860 | 263674 | 196606 | 1091078
| SLB | 250 | 250 | 250 | 250 |  | CAL SLB
| Cards | 288 | 216 | 104 | 18 | 626 | 522
| Spares | 29 | 22 | 10 | 2 | 63 | 53
| TOTAL BOARDS | 317 | 238 | 114 | 20 | 689 | 575
| Cost | 79250 | 59500 | 28500 | 5000 | 143750
| TPG | 165 | 165 | 100 | 165
| Cables | 288 | 216 | 52 | 18 | 574 | 10440
| Cost | 47520 | 35640 | 5200 | 2970 | 91330
VME
| Racks | 2 | 2 | 2 | 2 | 8
| Cost | 6000 | 6000 | 6000 | 6000 | 24000
| Rack Computer | 2 | 2 | 2 | 2 | 8
| Cost | 3000 | 3000 | 3000 | 3000 | 12000
| Crates | 5 | 4 | 4 | 3 | 16
| Cost | 27500 | 22000 | 22000 | 16500 | 88000 | 112000
| Bit3 | 5 | 4 | 4 | 3 | 16
| Cost | 17755 | 14204 | 14204 | 10653 | 56816 | 180816
DCC
| Cards | 10 | 8 | 8 | 6 | 32
| Cost | 40000 | 32000 | 32000 | 24000 | 128000
| Spare Cards | 2 | 2 | 2 | 1 | 7
| Cost | 8000 | 8000 | 8000 | 4000 | 28000
| Additional Boards | 5 | 0 | 0 | 0
| Cost | 20000 | 0 | 0 | 0 | 20000
| TOTAL BOARDS | 17 | 10 | 10 | 7 | 44
| TOTAL COST | 68000 | 40000 | 40000 | 28000 | 176000
Fanout Card
| Cards | 5 | 4 | 4 | 3 | 16
| Cost | 7500 | 6000 | 6000 | 4500 | 24000
| Spare Cards | 1 | 1 | 1 | 1 | 4
| Cost | 1500 | 1500 | 1500 | 1500 | 6000
| Additional Boards | 5 | 0 | 0 | 0 | 5
| Cost | 7500 | 0 | 0 | 0 | 7500
| TOTAL BOARDS | 11 | 5 | 5 | 4 | 25
| TOTAL COST | 16500 | 7500 | 7500 | 6000 | 37500
Note on F94: Drew Baden: includes rack and rack computer
Note on F87: Drew Baden: does not include bit3 cards (changed to DCSi) 11/02
Note on F101: Drew Baden: for HB, HE, and HF (not HO)
Note on F102: Drew Baden: obsolete, current plans have SLBs on HTR motherboard
Note on F88: Drew Baden: does not include bit3 cards (changed to DCSi) 11/02
Note on F96: Drew Baden: includes rack and rack computer
Note on F97: Drew Baden: includes rack and rack computer
Note on F95: Drew Baden: includes rack and rack computer
Note on F89: Drew Baden: does not include bit3 cards (changed to DCSi) 11/02
Note on F90: Drew Baden: does not include bit3 cards (changed to DCSi) 11/02
Note on H251: Drew Baden: BU wants 7 spares
Note on C251: Drew Baden: use 20% here
Note on C253: Drew Baden: test stands, etc
Note on C261: Drew Baden: 20% here because the numbers are so small
Note on F58: Drew Baden: includes shipping to FNAL or BU for system checkout, then to CERN
Note on F59: Drew Baden: includes shipping to FNAL or BU for system checkout, then to CERN
Note on F60: Drew Baden: includes shipping to FNAL or BU for system checkout, then to CERN
Note on F61: Drew Baden: includes shipping to FNAL or BU for system checkout, then to CERN
Note on D50: Drew Baden: from Nov02 project file
Note on C3: Drew Baden: includes benefits and 48% overhead
Note on F2: Drew Baden: till end of CY 2003
Note on D22: Drew Baden: from CPR 080202
Note on C225: Drew Baden: fully stuffed
Note on K128: : number of extra boards to build for test stands, etc. (not included in cms running spares)
Note on D128: : Total number of boards
Note on E128: : fraction of spare fully populated boards
Note on F128: : total number of spare boards
Note on D173: : Total number of boards
Note on E173: : fraction of spare fully populated boards
Note on F173: : total number of spare boards
Note on K173: : number of extra boards to build for test stands, etc. (not included in cms running spares)
Note on D158: : Total number of boards
Note on E158: : fraction of spare fully populated boards
Note on F158: : total number of spare boards
Note on K158: : number of extra boards to build for test stands, etc. (not included in cms running spares)
Note on D143: : Total number of boards
Note on E143: : fraction of spare fully populated boards
Note on F143: : total number of spare boards
Note on K143: : number of extra boards to build for test stands, etc. (not included in cms running spares)
Note on E210: Drew Baden: previous estimate was $6.2k: $5.7k for DCC, $500 for S-Link64
Note on I193: : difference between HB only having 3000s and all having 3000s, calculated by changing the value in the above table
Note on I191: : total cost if all systems have 3000s
Note on I192: : total cost if only HB has 3000s
Note on I194: : calculated by multiplying the number of 2000s by the cost difference (as a check against the above number)
Note on E132: Drew Baden: stratos asks $100, we add 10% for allied
Note on E133: Drew Baden: per julie whitmore's estimate of $300/HTR for 8way and the 8->LC pigtails or $330 if we use the 12-way trunk cables. Julie says to use $330
Note on C133: Drew Baden: plus pigtail, etc
Note on C139: Drew Baden: vme crystal, buffers, connectors, front panel, insertion handles, stiffeners, slb connectors... ...
Note on C138: Drew Baden: high quality pecl crystal for the TI serdes
Note on C140: Drew Baden: increases due to going to a 12 layer board
Note on J94: Drew Baden: 20 pmc connectors x $5
Note on J100: Drew Baden: to put standoffs, stiffeners, front panel stuff together, etc
Note on J101: Drew Baden: differential drivers, caps, resistors, etc.
Note on E50: : from CPR 110202
Note on D121: Drew Baden: From Jim Rohlf
Note on E121: Drew Baden: works out to be 1 per VME crate on average
Note on L22: Drew Baden: from CPR 080202
Note on G198: : additional TTCrx for DCC and fanout boards
Note on E134: : Allied's price, but Insight quote was $12
Note on F50: : increased spares to 20% and used XC2V3000s instead of 2000s
Note on F106: : 15m quad cables
Note on E140: : Data Circuits quote, $250 but including setup fees will come to around $300
Note on E141: : $300 zentech quote, add $50 for setup fees

## CPR110202
Cost Performance Report
Prepared on: | 2002-12-17 07:09
For month ending: 11/02
Hadron Calorimeter -- Cummulative Report --
WBS | Task Name | BCWS | BCWP | ACWP | Commit. | Oblig. | SV | CV | BAC | BAC Infl. | EAC | VAC | Institution | Grant | % Compl | Finish Date | Status
2 | Hadron Calorimeter (HCAL) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Green/Skuja/Freeman | No | 24 | 2006-11-09 08:00
2.1 | Barrel Hadron Calorimeter (HB) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Green/Skuja/Freeman | No | 34 | 2006-01-31 08:00
2.1.7 | Trigger/DAQ Electronics | 1729992.6641 | 1078016.9834 | 670718.3368 | 913529.3 | 1584247.6368 | -651975.6807 | 407298.6466 | 2389440.72 | 2493768.6687 | 2322006.595 | 171762.0737 | Baden/Maryland | No | 45 | 2006-01-31 08:00
2.1.7.1 | HCAL Trigger Readout (HTR) Module | 240556.5234 | 230037.668 | 129346.6172 | 415918.4 | 545265.0172 | -10518.8555 | 100691.0508 | 617437.2 | 652121.2046 | 586306.9774 | 65814.2272 | Baden/Maryland | No | 99 | 2003-11-17 08:39
2.1.7.1.1 | VME Readout Module Development | 240556.5234 | 230037.668 | 129346.6172 | 415918.4 | 545265.0172 | -10518.8555 | 100691.0508 | 617437.2 | 652121.2046 | 586306.9774 | 65814.2272 | Baden/Maryland | No | 93 | 2003-11-17 08:39
2.1.7.1.1.2 | HTR Module Specification Report | 6964.0703 | 6964.0703 | 4219.0898 | 0 | 4219.0898 | 0 | 2744.9805 | 6720 | 6964.0702 | 4219.0898 | 2744.9804 | Maryland | No | 100 | 1999-09-15 17:00 | Closed
2.1.7.1.1.3 | HTR Demonstrator Module (6U, N=8ch) | 58884 | 58884 | 21585.0801 | 35010.85 | 56595.9301 | 0 | 37298.9199 | 58884 | 58884 | 21585.0801 | 37298.9199 | Baden/Maryland | No | 100 | 2000-08-18 17:00 | Closed
2.1.7.1.1.3.1 | HTR Demonstrator Module Design & Testing | 40584 | 40584 | 0 | 0 | 0 | 0 | 40584 | 40584 | 40584 |  |  | Maryland | No | 100 | 2000-08-18 17:00 | Closed
2.1.7.1.1.3.2 | HTR Demonstrator Module M&S | 18300 | 18300 | 0 | 0 | 0 | 0 | 18300 | 18300 | 18300 |  |  | Maryland | No | 100 | 2000-06-23 17:00 | Closed
2.1.7.1.1.4 | HTR Prototype Module (9U, N=32ch) | 101081.1719 | 101081.1719 | 75473.7266 | 25785.27 | 101258.9966 | 0 | 25607.4453 | 98520 | 101081.1715 | 75473.7266 | 25607.4449 | Baden/Maryland | No | 100 | 2001-10-16 17:00 | Closed
2.1.7.1.1.4.1 | HTR Prototype Module Design & Testing | 70331.1719 | 70331.1719 | 0 | 0 | 0 | 0 | 70331.1719 | 68520 | 70331.1722 |  |  | Maryland | No | 100 | 2001-10-16 17:00 | Closed
2.1.7.1.1.4.2 | HTR Prototype Module M&S | 30750 | 30750 | 0 | 0 | 0 | 0 | 30750 | 30000 | 30749.9993 |  |  | Maryland | No | 100 | 2001-02-26 11:12 | Closed
2.1.7.1.1.5 | HTR 2nd Prototype Module (9U, N=32ch) | 73627.2812 | 63108.4258 | 28068.7207 | 45558.28 | 73627.0007 | -10518.8555 | 35039.7051 | 70011.2 | 73627.2818 | 71796.8737 | 1830.4081 | Baden/Maryland | No | 93 | 2002-07-18 17:00
2.1.7.1.1.5.1 | 2nd HTR Prototype Module Design & Testing | 52594.2812 | 42075.4258 | 0 | 0 | 0 | -10518.8555 | 42075.4258 | 50011.2 | 52594.2808 |  |  | Maryland | No | 80 | 2002-07-18 17:00
2.1.7.1.1.5.2 | 2nd HTR Prototype Module M&S | 21033 | 21033 | 0 | 0 | 0 | 0 | 21033 | 20000 | 21033.0009 |  |  | Maryland | No | 90 | 2002-07-18 17:00
2.1.7.1.1.6 | HTR Production Module (9U, N=48ch) | 0 | 0 | 0 | 309564 | 309564 | 0 | 0 | 383302 | 411564.6811 | 413232.2072 | -1667.5261 | Baden/Maryland | No | 0 | 2003-11-17 08:39
2.1.7.1.1.6.1 | HTR Production Module M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270100 | 290015.7588 |  |  | Maryland | No | 0 | 2003-11-17 08:39
2.1.7.1.1.6.2 | HTR Production Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110052 | 118166.6578 |  |  | Maryland | No | 0 | 2003-06-19 17:00
2.1.7.1.1.6.3 | Ship HTR Production Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3150 | 3382.2645 |  |  | Maryland | No | 0 | 2003-07-03 17:00
2.1.7.1.1.6.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Maryland | No | 0 | 2003-02-27 17:00
2.1.7.1.2 | VME Readout Module Production (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Baden/Maryland | No | 100 | 2003-05-06 17:00
2.1.7.2 | VME Transition Module (deleted WBS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 100 | 2003-05-20 17:00
2.1.7.2.2 | Demonstrator Module (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Baden/Maryland | No | 100 | 2000-06-22 17:00
2.1.7.2.3 | VME Transition Module Development (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Baden/Maryland | No | 100 | 2001-08-31 17:00
2.1.7.2.4 | VME Transition Module Production (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Baden/Maryland | No | 100 | 2003-05-20 17:00
2.1.7.3 | Data Concentrator Card (DCC) Module | 410060.2832 | 219467.5742 | 150496.2569 | 186418.71 | 336914.9669 | -190592.709 | 68971.3173 | 433939.2 | 448897.8872 | 434334.5679 | 14563.3193 | Hazen/Boston | No | 66 | 2004-02-13 12:00
2.1.7.3.1 | DCC Specification Report | 56412 | 56412 | 60849.1201 | 29122.76 | 89971.8801 | 0 | -4437.1201 | 56412 | 56412 | 60849.1201 | -4437.1201 | Boston | No | 100 | 2003-09-26 17:00
2.1.7.3.1.1 | VME Data Concentrator Requirements Report (deleted WBS) | 0 | 0 | 5179.5498 | 0 | 5179.5498 | 0 | -5179.5498 |  |  | 5179.5498 | -5179.5498 | Boston | No | 100 | 1999-09-03 17:00 | Open
2.1.7.3.1.3 | VME Data Concentrator Development (deleted WBS) | 56412 | 56412 | 55669.5703 | 29122.76 | 84792.3303 | 0 | 742.4297 | 56412 | 56412 | 55669.5703 | 742.4297 | Hazen/Boston | No | 100 | 2000-04-06 17:00 | Closed
2.1.7.3.1.3.10 | VME Data Concentrator Development M&S | 56412 | 56412 | 0 | 0 | 0 | 0 | 56412 | 56412 | 56412 |  |  | Boston | No | 100 | 2000-04-06 17:00 | Closed
2.1.7.3.1.4 | VME Data Concentrator Prototype (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Hazen/Boston | No | 100 | 2003-09-26 17:00
2.1.7.3.2 | VME Data Concentrator Production (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Hazen/Boston | No | 100 | 1998-01-07 17:00
2.1.7.3.3 | DCC Demonstrator Module | 77837.5977 | 77837.5977 | 87690.9668 | 6687.95 | 94378.9168 | 0 | -9853.3691 | 113480 | 116675.1984 | 97674.7589 | 19000.4395 | Hazen/Boston | No | 100 | 2004-02-13 12:00
2.1.7.3.3.1 | DCC Demonstrator Module Design & Testing | 38837.5977 | 38837.5977 | 67691.4062 | 6687.95 | 74379.3562 | 0 | -28853.8086 | 74480 | 77675.1984 | 77675.1984 |  | Boston | No | 100 | 2004-02-13 12:00
2.1.7.3.3.2 | DCC Demonstrator Module M&S | 39000 | 39000 | 19999.5605 | 0 | 19999.5605 | 0 | 19000.4395 | 39000 | 39000 | 19999.5605 | 19000.4395 | Boston | No | 100 | 2000-02-17 17:00 | Closed
2.1.7.3.4 | DCC Prototype Module (9U, N=18ch) | 75106.2227 | 64184.9766 | 795.7188 | 73245 | 74040.7188 | -10921.2461 | 63389.2578 | 73200 | 75106.222 | 75106.222 | 0 | Hazen/Boston | No | 75 | 2001-10-16 17:00
2.1.7.3.4.1 | DCC Prototype Module Design & Testing | 54606.2227 | 43684.9766 | 795.7188 | 53048 | 53843.7188 | -10921.2461 | 42889.2578 | 53200 | 54606.2224 | 54606.2224 |  | Boston | No | 80 | 2001-10-16 17:00
2.1.7.3.4.2 | DCC Prototype Module M&S | 20500 | 20500 | 0 | 20197 | 20197 | 0 | 20500 | 20000 | 20499.9995 | 20499.9995 |  | Boston | No | 60 | 2001-07-30 17:00
2.1.7.3.5 | DCC 2nd Prototype Module (9U, N=18ch) | 78523.7617 | 21033 | 1160.4512 | 77363 | 78523.4512 | -57490.7617 | 19872.5488 | 74667.2 | 78523.7644 | 78523.7644 | 0 | Hazen/Boston | No | 34 | 2002-08-16 17:00
2.1.7.3.5.1 | DCC Prototype Module Design & Testing | 57490.7617 | 0 | 849.6211 | 56641 | 57490.6211 | -57490.7617 | -849.6211 | 54667.2 | 57490.7635 | 57490.7635 |  | Boston | No | 0 | 2002-08-16 17:00
2.1.7.3.5.2 | DCC Prototype Module M&S | 21033 | 21033 | 310.8301 | 20722 | 21032.8301 | 0 | 20722.1699 | 20000 | 21033.0009 | 21033.0009 |  | Boston | No | 85 | 2002-06-21 17:00
2.1.7.3.6 | DCC Module Production | 122180.7012 | 0 | 0 | 0 | 0 | -122180.7012 | 0 | 116180 | 122180.7025 | 122180.7025 | 0 | Hazen/Boston | No | 0 | 2002-08-16 17:00
2.1.7.3.6.1 | DCC Module M&S (10% Spares) | 110843.9141 | 0 | 0 | 0 | 0 | -110843.9141 | 0 | 105400 | 110843.915 | 110843.915 |  | Boston | No | 0 | 2002-07-16 15:07
2.1.7.3.6.2 | DCC Production Module Engineering Support | 11336.7871 | 0 | 0 | 0 | 0 | -11336.7871 | 0 | 10780 | 11336.7875 | 11336.7875 |  | Boston | No | 0 | 2002-07-12 17:00
2.1.7.3.6.3 | Ship DCC Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2002-06-14 17:00
2.1.7.3.6.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2002-08-16 17:00
2.1.7.4 | VME Crates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52239 | 56165.8194 | 56165.8194 | 0 | Baden/Maryland | No | 5 | 2003-11-06 17:00
2.1.7.4.1 | VME Subrack M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45255 | 48591.8666 | 48591.8666 |  | FIT | No | 0 | 2003-08-28 17:00
2.1.7.4.2 | VME Crates Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6984 | 7573.9529 | 7573.9529 |  | FIT | No | 0 | 2003-10-23 17:00
2.1.7.4.3 | Ship VME Crates to CERN (Zero Cost-Purchase in Europe) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-11-06 17:00
2.1.7.5 | VME Relay Racks | 0 | 0 | 0 | 20742 | 20742 | 0 | 0 | 11400 | 12305.0002 | 12305.0002 | 0 | Baden/Maryland | No | 0 | 2003-12-04 17:00
2.1.7.5.1 | VME Relay Racks M&S (no Spares) | 0 | 0 | 0 | 20742 | 20742 | 0 | 0 | 9000 | 9663.6128 | 9663.6128 |  | Maryland | No | 0 | 2003-11-06 17:00
2.1.7.5.2 | VME Relay Racks Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 2641.3874 | 2641.3874 |  | Maryland | No | 0 | 2003-11-20 17:00
2.1.7.5.3 | Ship VME Relay Racks to CERN (Zero Cost-Purchase in Europe) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-12-04 17:00
2.1.7.6 | Level 1 Trigger Links | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107568 | 115499.5007 | 115499.5007 | 0 | Baden/Maryland | No | 35 | 2003-08-19 10:25
2.1.7.6.1 | Level 1 Trigger Links M&S (20% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100800 | 108232.4638 | 108232.4638 |  | Maryland | No | 0 | 2003-07-08 10:25
2.1.7.6.2 | Level 1 Trigger Links Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6768 | 7267.0369 | 7267.0369 |  | Maryland | No | 0 | 2003-08-05 10:25
2.1.7.6.3 | Ship Level 1 Trigger Links to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-08-19 10:25
2.1.7.7 | DCC Input Link | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 0 | 2003-07-11 17:00
2.1.7.7.1 | DCC Input Link M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-27 17:00
2.1.7.7.2 | Ship DCC Input Link to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-11 17:00
2.1.7.8 | PCI Receiver Module (deleted WBS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 100 | 1999-01-21 17:00
2.1.7.8.1 | PCI Receiver Module Development (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Hazen/Boston | No | 100 | 1999-01-21 17:00
2.1.7.8.2 | PCI Receiver Module Production (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Hazen/Boston | No | 100 | 1998-05-06 17:00
2.1.7.9 | VME Pipeline Module | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12884.8171 | 12884.8171 | 0 | Baden/Maryland | No | 59 | 2003-06-19 17:00
2.1.7.9.1 | VME Pipeline Module Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12884.8171 | 12884.8171 |  | Maryland | No | 0 | 2003-06-19 17:00
2.1.7.9.2 | VME Pipeline Module M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-02-27 17:00
2.1.7.9.3 | Ship VME Pipeline Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-03-13 17:00
2.1.7.10 | HCAL Readout Control (Crate Fanout) Module | 156985.6338 | 156985.6338 | 50608 | 0 | 50608 | 0 | 106377.6338 | 215285 | 224392.2842 | 162478.415 | 61913.8692 | Adams/UIC | No | 88 | 2004-06-30 17:00
2.1.7.10.2 | Crate Fanout Specification Report | 4526.6455 | 4526.6455 | 4368 | 0 | 4368 | 0 | 158.6455 | 4368 | 4526.6456 | 4368 | 158.6456 | UIC | No | 100 | 1999-09-03 17:00 | Closed
2.1.7.10.3 | Crate Fanout Demonstrator Module (6U VME) | 46240 | 46240 | 46240 | 0 | 46240 | 0 | 0 | 46240 | 46240 | 46240 | 0 | Adams/UIC | No | 100 | 2000-08-18 17:00
2.1.7.10.3.1 | Crate Fanout Demonstrator Module Design & Testing | 21140 | 21140 | 21140 | 0 | 21140 | 0 | 0 | 21140 | 21140 | 21140 | 0 | UIC | No | 100 | 2000-08-18 17:00 | Closed
2.1.7.10.3.2 | Crate Fanout Demonstrator Module M&S | 25100 | 25100 | 25100 | 0 | 25100 | 0 | 0 | 25100 | 25100 | 25100 | 0 | UIC | No | 100 | 2000-06-23 17:00 | Closed
2.1.7.10.4 | Crate Fanout Prototype Module (9U VME) | 61755.2246 | 61755.2246 | 0 | 0 | 0 | 0 | 61755.2246 | 60249 | 61755.2236 | 0 | 61755.2236 | Adams/UIC | No | 100 | 2001-08-23 08:00
2.1.7.10.4.1 | Crate Fanout Prototype Module Design & Testing | 31005.2246 | 31005.2246 | 0 | 0 | 0 | 0 | 31005.2246 | 30249 | 31005.2243 | 0 | 31005.2243 | UIC | No | 100 | 2001-08-23 08:00 | Closed
2.1.7.10.4.2 | Crate Fanout Prototype Module M&S | 30750 | 30750 | 0 | 0 | 0 | 0 | 30750 | 30000 | 30749.9993 | 0 | 30749.9993 | UIC | No | 100 | 2001-02-20 17:00 | Closed
2.1.7.10.5 | Crate Fanout 2nd Prototype Module (9U VME) | 44463.7637 | 44463.7637 | 0 | 0 | 0 | 0 | 44463.7637 | 62280 | 65938.4592 | 65938.4592 | 0 | Adams/UIC | No | 56 | 2003-06-30 17:00
2.1.7.10.5.1 | Crate Fanout Prototype Module Design & Testing | 22379.1133 | 22379.1133 | 0 | 0 | 0 | 0 | 22379.1133 | 21280 | 22379.113 | 22379.113 |  | UIC | No | 100 | 2002-06-20 17:00
2.1.7.10.5.2 | Crate Fanout Prototype Module M&S | 22084.6504 | 22084.6504 | 0 | 0 | 0 | 0 | 22084.6504 | 21000 | 22084.651 | 22084.651 |  | UIC | No | 100 | 2002-06-20 17:00
2.1.7.10.5.3 | Crate Fanout Prototype Module M&S-Princeton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 21474.6952 | 21474.6952 |  | Princeton | No | 0 | 2003-06-30 17:00
2.1.7.10.6 | Crate Fanout Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42148 | 45931.9557 | 45931.9557 | 0 | Tully/Princeton | No | 0 | 2004-06-30 17:00
2.1.7.10.6.1 | Crate Fanout Production Module M&S (20% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | 17716.6235 | 17716.6235 |  | Princeton | No | 0 | 2003-09-30 11:38
2.1.7.10.6.2 | Crate Fanout Production Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25648 | 28215.3322 | 28215.3322 |  | Princeton | No | 0 | 2003-11-25 11:38
2.1.7.10.6.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Princeton | No | 0 | 2003-12-09 11:38
2.1.7.10.6.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Princeton | No | 0 | 2004-06-30 17:00
2.1.7.11 | Tester Stations | 358946.332 | 350810.8574 | 215094.4705 | 108115.09 | 323209.5605 | -8135.4746 | 135716.387 | 355782.32 | 362295.1085 | 332824.4506 | 29470.6579 | Baden/Maryland | No | 95 | 2004-03-26 12:00
2.1.7.11.1 | Universal Tester Module | 79559.3711 | 79559.3711 | 68924.0505 | 4962.1 | 73886.1505 | 0 | 10635.3206 | 79264.12 | 79559.3697 | 68924.0505 | 10635.3192 | Baden/Maryland | No | 100 | 2000-11-09 17:00
2.1.7.11.1.1 | Universal Tester Module Design & Testing | 63072.1211 | 63072.1211 | 57765.8008 | 2304.29 | 60070.0908 | 0 | 5306.3203 | 63072.12 | 63072.12 | 57765.8008 | 5306.3192 | Maryland | No | 100 | 2000-08-04 17:00 | Closed
2.1.7.11.1.2 | Universal Tester Module M&S | 4382 | 4382 | 3072.24 | 914.16 | 3986.4 | 0 | 1309.76 | 4382 | 4382 | 3072.24 | 1309.76 | Maryland | No | 100 | 2000-08-17 17:00 | Closed
2.1.7.11.1.3 | Universal Tester Module Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Maryland | No | 100 | 2000-09-14 17:00 | Closed
2.1.7.11.1.4 | Universal Tester Module Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Maryland | No | 100 | 2000-10-12 17:00 | Closed
2.1.7.11.1.5 | TTC and LHC Emulator Setup | 12105.25 | 12105.25 | 8086.0098 | 1743.65 | 9829.6598 | 0 | 4019.2402 | 11810 | 12105.2497 | 8086.0098 | 4019.24 | Maryland | No | 100 | 2000-11-09 17:00 | Closed
2.1.7.11.2 | Front-End Electronic (FEE) Emulator | 64359 | 64359 | 48024.1602 | 18876.99 | 66901.1502 | 0 | 16334.8398 | 64359 | 64359 | 48024.1602 | 16334.8398 | Baden/Maryland | No | 100 | 2000-10-12 17:00
2.1.7.11.2.1 | FEE Emulator Design & Testing | 50184 | 50184 | 36745.5 | 17375.54 | 54121.04 | 0 | 13438.5 | 50184 | 50184 | 36745.5 | 13438.5 | Maryland | No | 100 | 2000-07-20 17:00 | Closed
2.1.7.11.2.2 | FEE Emulator M&S | 14175 | 14175 | 11278.6602 | 1501.45 | 12780.1102 | 0 | 2896.3398 | 14175 | 14175 | 11278.6602 | 2896.3398 | Maryland | No | 100 | 2000-08-17 17:00 | Closed
2.1.7.11.2.3 | FEE Emulator Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Maryland | No | 100 | 2000-09-14 17:00 | Closed
2.1.7.11.2.4 | FEE Emulator Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Maryland | No | 100 | 2000-10-12 17:00 | Closed
2.1.7.11.3 | DCC Module Test Equipment | 47891.8789 | 43313.5059 | 30738.2598 | 2142 | 32880.2598 | -4578.373 | 12575.2461 | 47831.2 | 47891.8801 | 47891.8801 | 0 | Hazen/Boston | No | 82 | 2004-03-26 12:00
2.1.7.11.3.1 | DCC Module Test Equipment | 25000 | 25000 | 16000.46 | 0 | 16000.46 | 0 | 8999.54 | 25000 | 25000 | 25000 |  | Boston | No | 90 | 2004-03-26 12:00
2.1.7.11.3.2 | DCC Module Software Development | 22891.8789 | 18313.5059 | 14737.7998 | 2142 | 16879.7998 | -4578.373 | 3575.7061 | 22831.2 | 22891.8801 | 22891.8801 |  | Boston | No | 80 | 2000-11-02 17:00
2.1.7.11.4 | Crate Fanout Demo Tester | 23640 | 23640 | 21140 | 0 | 21140 | 0 | 2500 | 23640 | 23640 | 21140 | 2500 | Adams/UIC | No | 100 | 2000-05-25 17:00
2.1.7.11.4.1 | Crate Fanout Demo Tester Design & Testing | 21140 | 21140 | 21140 | 0 | 21140 | 0 | 0 | 21140 | 21140 | 21140 | 0 | UIC | No | 100 | 2000-03-02 17:00 | Closed
2.1.7.11.4.2 | Crate Fanout Demo Tester M&S | 2500 | 2500 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 2500 | UIC | No | 100 | 2000-03-30 17:00 | Closed
2.1.7.11.4.3 | Crate Fanout Demo Tester | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | UIC | No | 100 | 2000-04-27 17:00 | Closed
2.1.7.11.4.4 | FEE Emulator Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | UIC | No | 100 | 2000-05-25 17:00 | Closed
2.1.7.12.1 | Demontrator Integration Tests (Maryland) | 24600 | 24600 | 24600 | 0 | 24600 | 0 | 0 | 24000 | 24599.9994 | 24600 | -0.0005722 | Maryland | No | 100 | 2000-12-08 17:00 | Closed
2.1.7.12.2 | Demontrator Integration Tests (Boston) | 18976.4062 | 18976.4062 | 0 | 21668 | 21668 | 0 | 18976.4062 | 21140 | 22325.1831 | 22325.1831 |  | Boston | No | 100 | 2004-02-24 17:00
2.1.7.12.3 | Demontrator Integration Tests (UIC) | 21668.5 | 21668.5 | 21668 | 0 | 21668 | 0 | 0.5 | 21140 | 21668.4995 | 21668 | 0.4995 | UIC | No | 100 | 2000-12-08 17:00 | Closed
2.1.7.12.4 | Prototype Integration Tests (Maryland) | 42680.1641 | 42680.1641 | 0 | 42680 | 42680 | 0 | 42680.1641 | 40584 | 42680.1655 | 42680.1655 |  | Maryland | No | 100 | 2002-04-01 17:00
2.1.7.12.5 | Prototype Integration Tests (Boston) | 17785.5059 | 14228.4043 | 0 | 17786 | 17786 | -3557.1016 | 14228.4043 | 16912 | 17785.5056 | 17785.5056 |  | Boston | No | 80 | 2002-02-04 17:00
2.1.7.12.6 | Prototype Integration Tests (UIC) | 17785.5059 | 17785.5059 | 0 | 0 | 0 | 0 | 17785.5059 | 16912 | 17785.5056 | 17785.5056 |  | UIC | No | 100 | 2002-02-04 17:00
2.1.7.12.7 | Installation at CERN (Maryland) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2004-09-29 17:00
2.1.7.12.8 | Installation at CERN (Boston) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2004-09-29 17:00
2.1.7.12.9 | Installation at CERN (UIC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2004-09-29 17:00
2.1.7.13 | Trigger/DAQ Coordination | 381264.7422 | 104940.5 | 125172.9922 | 166560.1 | 291733.0922 | -276324.2422 | -20232.4922 | 403200 | 419006.1338 | 419006.1338 | 0 | Baden/Maryland | No | 47 | 2004-09-28 17:00
2.1.7.13.1 | Trigger/DAQ HCAL DAQ/Trigger Integration (Maryland) | 291501.4062 | 104940.5 | 125172.9922 | 166560.1 | 291733.0922 | -186560.9062 | -20232.4922 | 283200 | 291501.3988 | 291501.3988 |  | Maryland | No | 36 | 2002-08-05 17:00
2.1.7.13.2 | Trigger/DAQ Project Engineering (Boston) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 26 | 2004-09-28 17:00
2.1.7.13.3 | Trigger/DAQ Project Engineering (Maryland) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 35 | 2004-09-28 17:00
2.1.7.13.4 | Trigger/DAQ Project Engineering (UIC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 100 | 2004-09-28 17:00
2.1.7.13.5 | Trigger/DAQ Shipping Costs (Boston) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2004-09-28 17:00
2.1.7.13.6 | Trigger/DAQ Shipping Costs (Maryland) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2004-09-28 17:00
2.1.7.13.7 | Trigger/DAQ Shipping Costs (UIC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 100 | 2004-09-28 17:00
2.1.7.13.10 | DCC Module Software Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 32 | 2003-09-26 17:00
2.1.7.13.11 | TRIDAS Engineering FY02,FY03 (Maryland) | 89763.3359 | 0 | 0 | 0 | 0 | -89763.3359 | 0 | 120000 | 127504.735 | 127504.735 |  | Maryland | No | 0 | 2003-03-28 17:00
2.1.7.14 | HCAL DAQ Concentrator (HDC) Module (deleted) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Adams/UIC | No | 100 | 2002-11-08 17:00
2.1.7.14.1 | HDC Prototype Module (9U VME) (deleted) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Adams/UIC | No | 100 | 2002-05-23 17:00
2.1.7.14.2 | HDC 2nd Prototype Module (9U VME) (deleted) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Adams/UIC | No | 100 | 2002-02-28 17:00
2.1.7.14.3 | HDC Module Production (deleted) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Adams/UIC | No | 100 | 2002-11-08 17:00
2.1.7.15 | SLB Modules | 182179.1494 | 15774.75 | 0 | 15775 | 15775 | -166404.3994 | 15774.75 | 180590 | 190200.9128 | 190200.9128 | 0 | Baden/Maryland | No | 33 | 2003-03-24 10:47
2.1.7.15.1 | SLB Trigger Links M&S (20% Spares) | 151174.6875 | 0 | 0 | 0 | 0 | -151174.6875 | 0 | 143750 | 151174.6943 | 151174.6943 |  | Maryland | No | 0 | 2003-03-24 10:47
2.1.7.15.2 | SLB Trigger Engineering | 15229.7119 | 0 | 0 | 0 | 0 | -15229.7119 | 0 | 21840 | 23251.4678 | 23251.4678 |  | Maryland | No | 0 | 2003-03-21 17:00
2.1.7.16 | Teststand equipment | 15774.75 | 15774.75 | 0 | 15775 | 15775 | 0 | 15774.75 | 15000 | 15774.7507 | 15774.7507 | 0 | Baden/Maryland | No | 93 | 2002-03-29 17:00
2.1.7.16.1 | CPUs | 5258.25 | 5258.25 | 0 | 5258 | 5258 | 0 | 5258.25 | 5000 | 5258.2502 | 5258.2502 |  | Boston | No | 80 | 2002-03-15 17:00
2.1.7.16.2 | Oscilloscope | 10516.5 | 10516.5 | 0 | 10517 | 10517 | 0 | 10516.5 | 10000 | 10516.5005 | 10516.5005 |  | Boston | No | 100 | 2002-03-29 17:00
2.2 | Outer Barrel Calorimeter (HO) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Mondal/TATA | No | 17 | 2005-11-30 08:00
2.2.7 | Trigger/DAQ Electronics | 47035.166 | 0 | 204546.1875 | 48831.58 | 253377.7675 | -47035.166 | -204546.1875 | 355006 | 381423.8721 | 381423.8721 | 0 | Baden/Maryland | No | 17 | 2005-06-14 17:00
2.2.7.1 | HTR Module Production | 0 | 0 | 204546.1875 | 48831.58 | 253377.7675 | 0 | -204546.1875 | 179162 | 192372.4671 | 192372.4671 | 0 | Baden/Maryland | No | 0 | 2003-07-07 14:48
2.2.7.1.1 | HTR Module M&S (10% Spares) | 0 | 0 | 204546.1875 | 48831.58 | 253377.7675 | 0 | -204546.1875 | 179162 | 192372.4671 | 192372.4671 |  | Maryland | No | 0 | 2003-07-07 14:48
2.2.7.1.2 | HTR Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-02-27 17:00
2.2.7.1.3 | Ship HTR Modules to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-03-13 17:00
2.2.7.1.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-05-15 17:00
2.2.7.2 | VME Transition Module (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Baden/Maryland | No | 100 | 1998-05-20 17:00
2.2.7.3 | Data Concentrator Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 66571.5551 | 66571.5551 | 0 | Hazen/Boston | No | 0 | 2003-04-18 17:00
2.2.7.3.1 | Data Concentrator M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 66571.5551 | 66571.5551 |  | Boston | No | 0 | 2003-04-09 12:00
2.2.7.3.2 | Data Concentrator Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2003-01-31 17:00
2.2.7.3.3 | Ship Data Concentrator Modules to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2003-02-14 17:00
2.2.7.3.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2003-04-18 17:00
2.2.7.4 | VME Crates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36204 | 38873.4933 | 38873.4933 | 0 | Baden/Maryland | No | 0 | 2003-07-03 17:00
2.2.7.4.1 | VME Subracks M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36204 | 38873.4933 | 38873.4933 |  | FIT | No | 0 | 2003-05-22 17:00
2.2.7.4.2 | VME Subracks Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-19 17:00
2.2.7.4.3 | Ship VME Subracks to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-03 17:00
2.2.7.5 | VME Relay Racks M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9905.2026 | 9905.2026 |  | Maryland | No | 0 | 2005-06-14 17:00
2.2.7.6 | Data Link (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Baden/Maryland | No | 100 | 1997-12-09 17:00
2.2.7.7 | DAQ Links | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 0 | 2003-07-11 17:00
2.2.7.7.1 | DAQ Link M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-27 17:00
2.2.7.7.2 | Ship DAQ Links to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-11 17:00
2.2.7.7.3 | Ship PCI Receiver Modules to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2002-07-29 17:00
2.2.7.8 | DCC Input Link | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 0 | 2003-07-11 17:00
2.2.7.8.1 | DCC Input Link M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-27 17:00
2.2.7.8.2 | Ship DCC Input Link to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-11 17:00
2.2.7.10 | Crate Fanout Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8053.0107 | 8053.0107 | 0 | Tully/Princeton | No | 0 | 2004-01-14 17:00
2.2.7.10.1 | Crate Fanout Production Module M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8053.0107 | 8053.0107 |  | Princeton | No | 0 | 2003-11-17 17:00
2.2.7.10.2 | Crate Fanout Production Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Princeton | No | 0 | 2003-12-15 17:00
2.2.7.10.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Princeton | No | 0 | 2004-01-14 17:00
2.2.7.10.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Princeton | No | 0 | 2003-10-13 17:00
2.2.7.11 | HO Trigger Link Development | 47035.166 | 0 | 0 | 0 | 0 | -47035.166 | 0 | 61140 | 65648.1432 | 65648.1432 | 0 | Baden/Maryland | No | 0 | 2003-09-29 17:00
2.2.7.11.1 | HO Trigger Link Development EDIA | 4085.7754 | 0 | 0 | 0 | 0 | -4085.7754 | 0 | 21140 | 22698.7528 | 22698.7528 |  | Maryland | No | 0 | 2003-09-29 17:00
2.2.7.11.2 | HO Trigger Link Development M&S | 10737.3477 | 0 | 0 | 0 | 0 | -10737.3477 | 0 | 10000 | 10737.3476 | 10737.3476 |  | Princeton | Yes | 0 | 2003-09-29 17:00
2.2.7.11.3 | HO Trigger Link Development M&S | 32212.043 | 0 | 0 | 0 | 0 | -32212.043 | 0 | 30000 | 32212.0428 | 32212.0428 |  | Princeton | Yes | 0 | 2003-09-29 17:00
2.3 | Endcap Hadron Calorimeter (HE) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Golutvin/RDMS | No | 21 | 2006-06-30 08:00
2.3.5.9.1 | VCSEL Acquisition | 9396.8965 | 0 | 0 | 0 | 0 | -9396.8965 | 0 | 8751.6 | 9396.8971 | 9396.8971 |  | Boston | No | 0 | 2003-02-03 17:00
2.3.5.9.2 | VCSEL Spares | 3754.7429 | 0 | 0 | 0 | 0 | -3754.7429 | 0 | 3496.9 | 3754.7431 | 3754.7431 |  | Boston | No | 0 | 2003-02-03 17:00
2.3.6.3.1 | Source Drivers and Controllers | 92755.5312 | 92755.5312 | 1370.7812 | 91385 | 92755.7812 | 0 | 91384.75 | 88200 | 92755.5342 | 92755.5342 |  | Purdue | No | 10 | 2001-10-26 17:00
2.3.6.3.2 | Wire Sources | 0 | 0 | 314.7207 | 20981 | 21295.7207 | 0 | -314.7207 | 20250 | 22286.7059 | 22286.7059 |  | Purdue | No | 0 | 2003-10-28 17:00
2.3.6.3.3 | Source Distribution Manifolds | 25239.6016 | 0 | 167.8096 | 24867 | 25034.8096 | -25239.6016 | -167.8096 | 24000 | 25239.6011 | 25239.6011 |  | Purdue | No | 0 | 2001-10-26 17:00
2.3.6.3.4 | Ship Source Drivers to CERN | 1682.6401 | 0 | 0 | 1658 | 1658 | -1682.6401 | 0 | 1600 | 1682.6401 | 1682.6401 |  | Purdue | No | 0 | 2001-11-23 17:00
2.3.7 | Trigger/DAQ Electronics | 0 | 0 | 0 | 309564 | 309564 | 0 | 0 | 424686 | 456000.1204 | 456000.1204 | 0 | Baden/Maryland | No | 33 | 2004-03-31 17:00
2.3.7.1 | HTR Module Production | 0 | 0 | 0 | 303254 | 303254 | 0 | 0 | 234382 | 251664.1006 | 251664.1006 | 0 | Baden/Maryland | No | 29 | 2003-08-21 11:00
2.3.7.1.1 | HTR Module M&S (10% Spares) | 0 | 0 | 0 | 303254 | 303254 | 0 | 0 | 231232 | 248281.8361 | 248281.8361 |  | Maryland | No | 0 | 2003-07-10 11:00
2.3.7.1.2 | HTR Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-08-07 11:00
2.3.7.1.3 | Ship HTR Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3150 | 3382.2645 | 3382.2645 |  | Maryland | No | 0 | 2003-08-21 11:00
2.3.7.2 | VME Transition Module (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Boston | No | 100 | 1998-01-28 17:00
2.3.7.3 | Data Concentrator Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 66571.5551 | 66571.5551 | 0 | Hazen/Boston | No | 0 | 2003-05-21 12:00
2.3.7.3.1 | Data Concentrator M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62000 | 66571.5551 | 66571.5551 |  | Boston | No | 0 | 2003-04-09 12:00
2.3.7.3.2 | Data Concentrator Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2003-05-07 12:00
2.3.7.3.3 | Ship Data Concentrator Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2003-05-21 12:00
2.3.7.3.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-04-18 17:00
2.3.7.4 | VME Crates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36204 | 38873.4933 | 38873.4933 | 0 | Baden/Maryland | No | 0 | 2003-08-28 17:00
2.3.7.4.1 | VME Subracks M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36204 | 38873.4933 | 38873.4933 |  | FIT | No | 0 | 2003-07-17 17:00
2.3.7.4.2 | VME Subracks Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-08-14 17:00
2.3.7.4.3 | Ship VME Subracks to CERN (Zero Cost-Purchase in Europe) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-08-28 17:00
2.3.7.4.4 | Ship VME Crates to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2002-02-04 17:00
2.3.7.5 | VME Relay Racks M&S (no Spares) | 0 | 0 | 0 | 6310 | 6310 | 0 | 0 | 9000 | 9663.6128 | 9663.6128 |  | Maryland | No | 0 | 2003-10-21 12:00
2.3.7.6 | Level 1Trigger Links | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75600 | 81174.3479 | 81174.3479 | 0 | Baden/Maryland | No | 7 | 2003-10-09 15:11
2.3.7.6.1 | Level 1 Link M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75600 | 81174.3479 | 81174.3479 |  | Maryland | No | 0 | 2003-08-28 15:11
2.3.7.6.2 | Level 1 Link Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-09-25 15:11
2.3.7.6.3 | Ship Level 1 Link to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-10-09 15:11
2.3.7.7 | DAQ Links | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 0 | 2003-07-11 17:00
2.3.7.7.1 | DAQ Link M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-27 17:00
2.3.7.7.2 | Ship DAQ Link to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-11 17:00
2.3.7.8 | PCI Receiver Module (deleted WBS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8053.0107 | 8053.0107 | 0 | Hazen/Boston | No | 51 | 2004-03-31 17:00
2.3.7.10 | Crate Fanout Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8053.0107 | 8053.0107 | 0 | Tully/Princeton | No | 0 | 2004-03-31 17:00
2.3.7.10.1 | Crate Fanout Production Module M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8053.0107 | 8053.0107 |  | Princeton | No | 0 | 2004-01-21 17:00
2.3.7.10.2 | Crate Fanout Production Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Princeton | No | 0 | 2004-03-17 17:00
2.3.7.10.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Princeton | No | 0 | 2004-03-31 17:00
2.3.7.10.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Princeton | No | 0 | 2003-10-13 17:00
2.5 | Forward Calorimeter (HF) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Akchurin/Texas Tech | No | 22 | 2006-11-09 08:00
2.5.6.6 | HF Source Routing System #3 | 45100 | 41000 | 0 | 4100 | 4100 | -4100 | 41000 | 44000 | 45099.999 | 45099.999 | 0 | Barnes/Purdue | No | 38 | 2001-09-28 17:00
2.5.6.6.1 | HF Source Driver #3 | 20500 | 20500 | 0 | 0 | 0 | 0 | 20500 | 20000 | 20499.9995 | 20499.9995 |  | Purdue | No | 75 | 2001-09-28 17:00
2.5.6.6.2 | HF Source Driver #3 Hardware | 2050 | 0 | 0 | 2050 | 2050 | -2050 | 0 | 2000 | 2050 | 2050 |  | Texas Tech | No | 0 | 2001-09-28 17:00
2.5.6.7 | HF Source Routing System #4 | 22550 | 20500 | 0 | 2050 | 2050 | -2050 | 20500 | 22000 | 22549.9995 | 22549.9995 | 0 | Barnes/Purdue | No | 38 | 2001-09-28 17:00
2.5.6.7.1 | HF Source Driver #4 | 20500 | 20500 | 0 | 0 | 0 | 0 | 20500 | 20000 | 20499.9995 |  |  | Purdue | No | 75 | 2001-09-28 17:00
2.5.6.7.2 | HF Source Driver #4 Hardware | 2050 | 0 | 0 | 2050 | 2050 | -2050 | 0 | 2000 | 2050 |  |  | Texas Tech | No | 0 | 2001-09-28 17:00
2.5.7 | Trigger/DAQ Electronics | 45641.6133 | 0 | 137838.7656 | 102865.23 | 240703.9956 | -45641.6133 | -137838.7656 | 237005 | 253522.0303 | 253522.0303 | 0 | Baden/Maryland | No | 9 | 2004-02-11 17:00
2.5.7.1 | HTR Module Production | 0 | 0 | 137838.7656 | 99710.23 | 237548.9956 | 0 | -137838.7656 | 145152 | 155854.7479 | 155854.7479 | 0 | Baden/Maryland | No | 6 | 2003-08-21 15:16
2.5.7.1.1 | HTR Module M&S (10% Spares) | 0 | 0 | 137838.7656 | 99710.23 | 237548.9956 | 0 | -137838.7656 | 142002 | 152472.4834 | 152472.4834 |  | Maryland | No | 0 | 2003-07-10 15:16
2.5.7.1.2 | HTR Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-08-07 15:16
2.5.7.1.3 | Ship HTR Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3150 | 3382.2645 | 3382.2645 |  | Maryland | No | 0 | 2003-08-21 15:16
2.5.7.2 | VME Transition Module (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Elias/FNAL | No | 100 | 1997-10-28 17:00
2.5.7.3 | Data Concentrator Module Production | 45641.6133 | 0 | 0 | 0 | 0 | -45641.6133 | 0 | 43400 | 45641.6121 | 45641.6121 | 0 | Hazen/Boston | No | 0 | 2002-10-11 17:00
2.5.7.3.1 | Data ConcentratorModule M&S (20% Spares) | 45641.6133 | 0 | 0 | 0 | 0 | -45641.6133 | 0 | 43400 | 45641.6121 | 45641.6121 |  | Boston | No | 0 | 2002-08-16 17:00
2.5.7.3.2 | Data Concentrator Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2002-09-27 17:00
2.5.7.3.3 | Ship Data Concentrator Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2002-10-11 17:00
2.5.7.3.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2002-08-16 17:00
2.5.7.4 | VME Crates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27153 | 29155.1199 | 29155.1199 | 0 | Baden/Maryland | No | 0 | 2003-07-03 17:00
2.5.7.4.1 | VME Subracks M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27153 | 29155.1199 | 29155.1199 |  | FIT | No | 0 | 2003-05-22 17:00
2.5.7.4.2 | VME Subracks Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-19 17:00
2.5.7.4.3 | Ship VME Subracks to CERN (Zero Cost-Purchase in Europe) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-03 17:00
2.5.7.5 | VME Relay Racks M&S (no Spares) | 0 | 0 | 0 | 3155 | 3155 | 0 | 0 | 9000 | 9663.6128 | 9663.6128 |  | Maryland | No | 0 | 2003-06-19 17:00
2.5.7.6 | Level 1 Trigger Cables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | 6764.529 | 6764.529 | 0 | Baden/Maryland | No | 12 | 2003-09-08 10:13
2.5.7.6.1 | Level 1 Link M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6300 | 6764.529 | 6764.529 |  | Maryland | No | 0 | 2003-07-28 10:13
2.5.7.6.2 | Level 1 Link Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-08-25 10:13
2.5.7.6.3 | Ship Level 1 Link to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-09-08 10:13
2.5.7.7 | DAQ Links | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 0 | 2003-07-11 17:00
2.5.7.7.1 | DAQ Link M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-27 17:00
2.5.7.7.2 | Ship DAQ Link to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-11 17:00
2.5.7.8 | Crate Fanout Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6442.4086 | 6442.4086 | 0 | Tully/Princeton | No | 0 | 2004-02-11 17:00
2.5.7.8.1 | Crate Fanout Production Module M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6442.4086 | 6442.4086 |  | Princeton | No | 0 | 2003-12-15 17:00
2.5.7.8.2 | Crate Fanout Production Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Princeton | No | 0 | 2004-01-28 17:00
2.5.7.8.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Princeton | No | 0 | 2004-02-11 17:00
2.5.7.8.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Princeton | No | 0 | 2003-10-13 17:00

## CPR 080202
Cost Performance Report
Prepared on: | 2002-09-23 07:53
For month ending: 8/02
Hadron Calorimeter -- Cummulative Report --
WBS | Task Name | BCWS | BCWP | ACWP | Commit. | Oblig. | SV | CV | BAC | BAC Infl. | EAC | VAC | Institution | Grant | % Compl | Finish Date | Status
2 | Hadron Calorimeter (HCAL) | [11 empty] | Green/Skuja/Freeman | No | 25 | 2006-03-14 17:00
2.1 | Barrel Hadron Calorimeter (HB) | [11 empty] | Green/Skuja/Freeman | No | 68 | 2005-11-30 08:00
2.1.5 | Front-end Electronics | [11 empty] | Elias/FNAL | No | 77 | 2004-11-30 08:00
2.1.5.14 | Teststands for Development and Maintenance | 147231 | 36807.75 | 0 | 21555 | 21555 | -110423.25 | 36807.75 | 140000 | 147231.0066 | 147231.0066 | 0 | FNAL | No | 21 | 2002-11-08 17:00
2.1.5.14.1 | Teststands for Developmen/Maintenance-FNAL | 36807.75 | 0 | 0 | 21555 | 21555 | -36807.75 | 0 | 35000 | 36807.7517 | 36807.7517 |  | FNAL | No | 80 | 2002-11-08 17:00
2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland | 36807.75 | 0 | 0 | 0 | 0 | -36807.75 | 0 | 35000 | 36807.7517 | 36807.7517 |  | Maryland | No | 0 | 2002-11-08 17:00
2.1.5.14.3 | Teststands for Developmen/Maintenance-BOSTON | 36807.75 | 36807.75 | 0 | 0 | 0 | 0 | 36807.75 | 35000 | 36807.7517 | 36807.7517 |  | Boston | No | 5 | 2002-11-08 17:00
2.1.5.14.4 | Teststands for Developmen/Maintenance-CERN | 36807.75 | 0 | 0 | 0 | 0 | -36807.75 | 0 | 35000 | 36807.7517 | 36807.7517 |  | FNAL | No | 0 | 2002-11-08 17:00
2.1.7 | Trigger/DAQ Electronics | [10 empty] | 0 | Baden/Maryland | No | 57 | 2005-01-31 08:00
2.1.7.1 | HCAL Trigger Readout (HTR) Module | [10 empty] | 0 | Baden/Maryland | No | 77 | 2003-12-19 17:00
2.1.7.1.1 | VME Readout Module Development | 240549.6694 | 203733.6724 | 129346.6172 | 415918.4 | 545265.0172 | -36815.9971 | 74387.0552 | 660023.2 | 697840.419 | 658007.6891 | 39832.7299 | Baden/Maryland | No | 73 | 2003-12-19 17:00
2.1.7.1.1.2 | HTR Module Specification Report | 6957.2163 | 6957.2163 | 4219.0898 | 0 | 4219.0898 | 0 | 2738.1265 | 6720 | 6957.2161 | 4219.0898 | 2738.1263 | Maryland | No | 100 | 1999-09-15 17:00 | Closed
2.1.7.1.1.3 | HTR Demonstrator Module (6U, N=8ch) | 58884 | 58884 | 21585.0801 | 35010.85 | 56595.9301 | 0 | 37298.9199 | 58884 | 58884 | 21585.0801 | 37298.9199 | Baden/Maryland | No | 100 | 2000-08-18 17:00 | Closed
2.1.7.1.1.3.1 | HTR Demonstrator Module Design & Testing | 40584 | 40584 | 0 | 0 | 0 | 0 | 40584 | 40584 | 40584 |  |  | Maryland | No | 100 | 2000-08-18 17:00 | Closed
2.1.7.1.1.3.2 | HTR Demonstrator Module M&S | 18300 | 18300 | 0 | 0 | 0 | 0 | 18300 | 18300 | 18300 |  |  | Maryland | No | 100 | 2000-06-23 17:00 | Closed
2.1.7.1.1.4 | HTR Prototype Module (9U, N=32ch) | 101081.1719 | 101081.1719 | 75473.7266 | 25785.27 | 101258.9966 | 0 | 25607.4453 | 98520 | 101081.1715 | 100528.0627 | 553.1088 | Baden/Maryland | No | 100 | 2001-10-16 17:00
2.1.7.1.1.4.1 | HTR Prototype Module Design & Testing | 70331.1719 | 70331.1719 | 0 | 0 | 0 | 0 | 70331.1719 | 68520 | 70331.1722 |  |  | Maryland | No | 100 | 2001-10-16 17:00
2.1.7.1.1.4.2 | HTR Prototype Module M&S | 30750 | 30750 | 0 | 0 | 0 | 0 | 30750 | 30000 | 30749.9993 |  |  | Maryland | No | 100 | 2001-02-26 11:12 | Closed
2.1.7.1.1.5 | HTR 2nd Prototype Module (9U, N=32ch) | 73627.2812 | 36811.2842 | 28068.7207 | 45558.28 | 73627.0007 | -36815.9971 | 8742.5635 | 70011.2 | 73627.2818 | 71781.9928 | 1845.289 | Baden/Maryland | No | 93 | 2002-07-18 17:00
2.1.7.1.1.5.1 | 2nd HTR Prototype Module Design & Testing | 52594.2812 | 15778.2842 | 0 | 0 | 0 | -36815.9971 | 15778.2842 | 50011.2 | 52594.2808 |  |  | Maryland | No | 80 | 2002-07-18 17:00
2.1.7.1.1.5.2 | 2nd HTR Prototype Module M&S | 21033 | 21033 | 0 | 0 | 0 | 0 | 21033 | 20000 | 21033.0009 |  |  | Maryland | No | 90 | 2002-07-18 17:00
2.1.7.1.1.6 | HTR Production Module (9U, N=48ch) | 0 | 0 | 0 | 309564 | 309564 | 0 | 0 | 425888 | 457290.7496 | 459893.4637 | -2602.7141 | Baden/Maryland | No | 0 | 2003-12-19 17:00
2.1.7.1.1.6.1 | HTR Production Module M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312686 | 335741.8273 |  |  | Maryland | No | 0 | 2003-12-19 17:00
2.1.7.1.1.6.2 | HTR Production Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110052 | 118166.6578 |  |  | Maryland | No | 0 | 2003-05-23 17:00
2.1.7.1.1.6.3 | Ship HTR Production Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3150 | 3382.2645 |  |  | Maryland | No | 0 | 2003-06-06 17:00
2.1.7.1.1.6.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Maryland | No | 0 | 2003-01-31 17:00
2.1.7.3 | Data Concentrator Card (DCC) Module | 357057.123 | 216737.2656 | 127741.8018 | 56301.61 | 184043.4118 | -140319.8574 | 88995.4639 | 383539.2 | 395894.7248 | 371962.0149 | 23932.71 | Hazen/Boston | No | 94 | 2004-02-13 12:00
2.1.7.3.1 | DCC Specification Report | 56412 | 56412 | 55301.0498 | 34588.81 | 89889.8598 | 0 | 1110.9502 | 56412 | 56412 | 55301.0498 | 1110.9502 | Boston | No | 100 | 2003-09-26 17:00
2.1.7.3.1.1 | VME Data Concentrator Requirements Report (deleted WBS) | 0 | 0 | 5179.5498 | 0 | 5179.5498 | 0 | -5179.5498 |  |  | 5179.5498 | -5179.5498 | Boston | No | 100 | 1999-09-03 17:00 | Open
2.1.7.3.1.3 | VME Data Concentrator Development (deleted WBS) | 56412 | 56412 | 50121.5 | 34588.81 | 84710.31 | 0 | 6290.5 | 56412 | 56412 | 50121.5 | 6290.5 | Hazen/Boston | No | 100 | 2000-04-06 17:00 | Closed
2.1.7.3.1.3.10 | VME Data Concentrator Development M&S | 56412 | 56412 | 0 | 0 | 0 | 0 | 56412 | 56412 | 56412 |  |  | Boston | No | 100 | 2000-04-06 17:00 | Closed
2.1.7.3.1.4 | VME Data Concentrator Prototype (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Hazen/Boston | No | 100 | 2003-09-26 17:00
2.1.7.3.2 | VME Data Concentrator Production (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Hazen/Boston | No | 100 | 1998-01-07 17:00
2.1.7.3.3 | DCC Demonstrator Module | 77837.5977 | 77837.5977 | 72440.752 | 21712.8 | 94153.552 | 0 | 5396.8457 | 113480 | 116675.1984 | 93853.4386 | 22821.7598 | Hazen/Boston | No | 100 | 2004-02-13 12:00
2.1.7.3.3.1 | DCC Demonstrator Module Design & Testing | 38837.5977 | 38837.5977 | 56262.5117 | 17947.95 | 74210.4617 | 0 | -17424.9141 | 74480 | 77675.1984 | 77675.1984 |  | Boston | No | 100 | 2004-02-13 12:00
2.1.7.3.3.2 | DCC Demonstrator Module M&S | 39000 | 39000 | 16178.2402 | 3764.85 | 19943.0902 | 0 | 22821.7598 | 39000 | 39000 | 16178.2402 | 22821.7598 | Boston | No | 100 | 2000-02-17 17:00 | Closed
2.1.7.3.4 | DCC Prototype Module (9U, N=18ch) | 75106.2227 | 61454.668 | 0 | 0 | 0 | -13651.5547 | 61454.668 | 73200 | 75106.222 | 75106.222 | 0 | Hazen/Boston | No | 75 | 2001-10-16 17:00
2.1.7.3.4.1 | DCC Prototype Module Design & Testing | 54606.2227 | 40954.668 | 0 | 0 | 0 | -13651.5547 | 40954.668 | 53200 | 54606.2224 | 54606.2224 |  | Boston | No | 80 | 2001-10-16 17:00
2.1.7.3.4.2 | DCC Prototype Module M&S | 20500 | 20500 | 0 | 0 | 0 | 0 | 20500 | 20000 | 20499.9995 | 20499.9995 |  | Boston | No | 60 | 2001-07-30 17:00
2.1.7.3.5 | DCC 2nd Prototype Module (9U, N=18ch) | 78523.7617 | 21033 | 0 | 0 | 0 | -57490.7617 | 21033 | 74667.2 | 78523.7644 | 78523.7644 | 0 | Hazen/Boston | No | 34 | 2002-08-16 17:00
2.1.7.3.5.1 | DCC Prototype Module Design & Testing | 57490.7617 | 0 | 0 | 0 | 0 | -57490.7617 | 0 | 54667.2 | 57490.7635 | 57490.7635 |  | Boston | No | 0 | 2002-08-16 17:00
2.1.7.3.5.2 | DCC Prototype Module M&S | 21033 | 21033 | 0 | 0 | 0 | 0 | 21033 | 20000 | 21033.0009 | 21033.0009 |  | Boston | No | 85 | 2002-06-21 17:00
2.1.7.3.6 | DCC Module Production | 69177.541 | 0 | 0 | 0 | 0 | -69177.541 | 0 | 65780 | 69177.5401 | 69177.5401 | 0 | Hazen/Boston | No | 0 | 2002-08-23 17:00
2.1.7.3.6.1 | DCC Module M&S (10% Spares) | 57840.7539 | 0 | 0 | 0 | 0 | -57840.7539 | 0 | 55000 | 57840.7526 | 57840.7526 |  | Boston | No | 0 | 2002-08-23 17:00
2.1.7.3.6.2 | DCC Production Module Engineering Support | 11336.7871 | 0 | 0 | 0 | 0 | -11336.7871 | 0 | 10780 | 11336.7875 | 11336.7875 |  | Boston | No | 0 | 2002-07-12 17:00
2.1.7.3.6.3 | Ship DCC Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2002-06-14 17:00
2.1.7.3.6.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2002-08-16 17:00
2.1.7.4 | VME Crates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34484 | 37026.6695 | 37026.6695 | 0 | Baden/Maryland | No | 5 | 2003-10-10 17:00
2.1.7.4.1 | VME Subrack M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | 29527.7059 | 29527.7059 |  | FIT | No | 0 | 2003-08-01 17:00
2.1.7.4.2 | VME Crates Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6984 | 7498.9636 | 7498.9636 |  | FIT | No | 0 | 2003-09-26 17:00
2.1.7.4.3 | Ship VME Crates to CERN (Zero Cost-Purchase in Europe) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-10-10 17:00
2.1.7.5 | VME Relay Racks | 0 | 0 | 0 | 20742 | 20742 | 0 | 0 | 8400 | 9083.7959 | 9083.7959 | 0 | Baden/Maryland | No | 0 | 2003-11-07 17:00
2.1.7.5.1 | VME Relay Racks M&S (no Spares) | 0 | 0 | 0 | 20742 | 20742 | 0 | 0 | 6000 | 6442.4086 | 6442.4086 |  | Maryland | No | 0 | 2003-10-10 17:00
2.1.7.5.2 | VME Relay Racks Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 2641.3874 | 2641.3874 |  | Maryland | No | 0 | 2003-10-24 17:00
2.1.7.5.3 | Ship VME Relay Racks to CERN (Zero Cost-Purchase in Europe) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-11-07 17:00
2.1.7.6 | Level 1 Trigger Links | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35568 | 38190.598 | 38190.598 | 0 | Baden/Maryland | No | 35 | 2003-08-19 10:25
2.1.7.6.1 | Level 1 Trigger Links M&S (20% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28800 | 30923.5611 | 30923.5611 |  | Maryland | No | 0 | 2003-07-08 10:25
2.1.7.6.2 | Level 1 Trigger Links Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6768 | 7267.0369 | 7267.0369 |  | Maryland | No | 0 | 2003-08-05 10:25
2.1.7.6.3 | Ship Level 1 Trigger Links to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-08-19 10:25
2.1.7.7 | DCC Input Link | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 0 | 2003-07-11 17:00
2.1.7.7.1 | DCC Input Link M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-27 17:00
2.1.7.7.2 | Ship DCC Input Link to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-11 17:00
2.1.7.8 | PCI Receiver Module (deleted WBS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 100 | 1999-01-21 17:00
2.1.7.8.1 | PCI Receiver Module Development (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Hazen/Boston | No | 100 | 1999-01-21 17:00
2.1.7.8.2 | PCI Receiver Module Production (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Hazen/Boston | No | 100 | 1998-05-06 17:00
2.1.7.9 | VME Pipeline Module | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12884.8171 | 12884.8171 | 0 | Baden/Maryland | No | 59 | 2003-05-23 17:00
2.1.7.9.1 | VME Pipeline Module Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12884.8171 | 12884.8171 |  | Maryland | No | 0 | 2003-05-23 17:00
2.1.7.9.2 | VME Pipeline Module M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-01-31 17:00
2.1.7.9.3 | Ship VME Pipeline Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-02-14 17:00
2.1.7.10 | HCAL Readout Control (Crate Fanout) Module | 156981.1787 | 112517.415 | 0 | 0 | 0 | -44463.7637 | 112517.415 | 187785 | 194183.94 | 112671.7503 | 81512.1898 | Adams/UIC | No | 68 | 2003-08-29 17:00
2.1.7.10.2 | Crate Fanout Specification Report | 4522.1904 | 4522.1904 | 0 | 0 | 0 | 0 | 4522.1904 | 4368 | 4522.1905 | 0 | 4522.1905 | UIC | No | 100 | 1999-09-03 17:00 | Closed
2.1.7.10.3 | Crate Fanout Demonstrator Module (6U VME) | 46240 | 46240 | 0 | 0 | 0 | 0 | 46240 | 46240 | 46240 | 0 | 46240 | Adams/UIC | No | 100 | 2000-08-18 17:00
2.1.7.10.3.1 | Crate Fanout Demonstrator Module Design & Testing | 21140 | 21140 | 0 | 0 | 0 | 0 | 21140 | 21140 | 21140 | 0 | 21140 | UIC | No | 100 | 2000-08-18 17:00 | Closed
2.1.7.10.3.2 | Crate Fanout Demonstrator Module M&S | 25100 | 25100 | 0 | 0 | 0 | 0 | 25100 | 25100 | 25100 | 0 | 25100 | UIC | No | 100 | 2000-06-23 17:00 | Closed
2.1.7.10.4 | Crate Fanout Prototype Module (9U VME) | 61755.2246 | 61755.2246 | 0 | 0 | 0 | 0 | 61755.2246 | 60249 | 61755.2236 | 31005.2243 | 30749.9993 | Adams/UIC | No | 100 | 2001-08-23 08:00
2.1.7.10.4.1 | Crate Fanout Prototype Module Design & Testing | 31005.2246 | 31005.2246 | 0 | 0 | 0 | 0 | 31005.2246 | 30249 | 31005.2243 | 31005.2243 |  | UIC | No | 100 | 2001-08-23 08:00 | Closing
2.1.7.10.4.2 | Crate Fanout Prototype Module M&S | 30750 | 30750 | 0 | 0 | 0 | 0 | 30750 | 30000 | 30749.9993 | 0 | 30749.9993 | UIC | No | 100 | 2001-02-20 17:00 | Closed
2.1.7.10.5 | Crate Fanout 2nd Prototype Module (9U VME) | 44463.7637 | 0 | 0 | 0 | 0 | -44463.7637 | 0 | 42280 | 44463.764 | 44463.764 | 0 | Adams/UIC | No | 95 | 2002-08-15 17:00
2.1.7.10.5.1 | Crate Fanout Prototype Module Design & Testing | 22379.1133 | 0 | 0 | 0 | 0 | -22379.1133 | 0 | 21280 | 22379.113 | 22379.113 |  | UIC | No | 95 | 2002-08-15 17:00
2.1.7.10.5.2 | Crate Fanout Prototype Module M&S | 22084.6504 | 0 | 0 | 0 | 0 | -22084.6504 | 0 | 21000 | 22084.651 | 22084.651 |  | UIC | No | 95 | 2002-06-20 17:00
2.1.7.10.6 | Crate Fanout Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34648 | 37202.762 | 37202.762 | 0 | Adams/UIC | No | 0 | 2003-08-29 17:00
2.1.7.10.6.1 | Crate Fanout Production Module M&S (20% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9663.6128 | 9663.6128 |  | UIC | No | 0 | 2003-06-20 17:00
2.1.7.10.6.2 | Crate Fanout Production Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25648 | 27539.1491 | 27539.1491 |  | UIC | No | 0 | 2003-08-15 17:00
2.1.7.10.6.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-08-29 17:00
2.1.7.10.6.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-04-18 17:00
2.1.7.11 | Tester Stations | 358946.332 | 311629.7441 | 182219.1287 | 80354.52 | 262573.6487 | -47316.5879 | 129410.6155 | 355782.32 | 362295.1085 | 290014.5893 | 72280.5193 | Baden/Maryland | No | 91 | 2004-03-26 12:00
2.1.7.11.1 | Universal Tester Module | 79559.3711 | 79559.3711 | 68922.1892 | 4962.1 | 73884.2892 | 0 | 10637.1819 | 79264.12 | 79559.3697 | 68922.1892 | 10637.1805 | Baden/Maryland | No | 100 | 2000-11-09 17:00
2.1.7.11.1.1 | Universal Tester Module Design & Testing | 63072.1211 | 63072.1211 | 57767.4492 | 2304.29 | 60071.7392 | 0 | 5304.6719 | 63072.12 | 63072.12 | 57767.4492 | 5304.6708 | Maryland | No | 100 | 2000-08-04 17:00 | Closed
2.1.7.11.1.2 | Universal Tester Module M&S | 4382 | 4382 | 3072.24 | 914.16 | 3986.4 | 0 | 1309.76 | 4382 | 4382 | 3072.24 | 1309.76 | Maryland | No | 100 | 2000-08-17 17:00 | Closed
2.1.7.11.1.3 | Universal Tester Module Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Maryland | No | 100 | 2000-09-14 17:00 | Closed
2.1.7.11.1.4 | Universal Tester Module Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Maryland | No | 100 | 2000-10-12 17:00 | Closed
2.1.7.11.1.5 | TTC and LHC Emulator Setup | 12105.25 | 12105.25 | 8082.5 | 1743.65 | 9826.15 | 0 | 4022.75 | 11810 | 12105.2497 | 8082.5 | 4022.7497 | Maryland | No | 100 | 2000-11-09 17:00 | Closed
2.1.7.11.2 | Front-End Electronic (FEE) Emulator | 64359 | 64359 | 48024.1602 | 18876.99 | 66901.1502 | 0 | 16334.8398 | 64359 | 64359 | 48024.1602 | 16334.8398 | Baden/Maryland | No | 100 | 2000-10-12 17:00
2.1.7.11.2.1 | FEE Emulator Design & Testing | 50184 | 50184 | 36745.5 | 17375.54 | 54121.04 | 0 | 13438.5 | 50184 | 50184 | 36745.5 | 13438.5 | Maryland | No | 100 | 2000-07-20 17:00 | Closed
2.1.7.11.2.2 | FEE Emulator M&S | 14175 | 14175 | 11278.6602 | 1501.45 | 12780.1102 | 0 | 2896.3398 | 14175 | 14175 | 11278.6602 | 2896.3398 | Maryland | No | 100 | 2000-08-17 17:00 | Closed
2.1.7.11.2.3 | FEE Emulator Assembly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Maryland | No | 100 | 2000-09-14 17:00 | Closed
2.1.7.11.2.4 | FEE Emulator Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Maryland | No | 100 | 2000-10-12 17:00 | Closed
2.1.7.11.3 | DCC Module Test Equipment | 47891.8789 | 43313.5059 | 28028.2393 | 4811.97 | 32840.2093 | -4578.373 | 15285.2666 | 47831.2 | 47891.8801 | 47891.8801 | 0 | Hazen/Boston | No | 82 | 2004-03-26 12:00
2.1.7.11.3.1 | DCC Module Test Equipment | 25000 | 25000 | 15909.1396 | 89.97 | 15999.1096 | 0 | 9090.8604 | 25000 | 25000 | 25000 |  | Boston | No | 90 | 2004-03-26 12:00
2.1.7.11.3.2 | DCC Module Software Development | 22891.8789 | 18313.5059 | 12119.0996 | 4722 | 16841.0996 | -4578.373 | 6194.4062 | 22831.2 | 22891.8801 | 22891.8801 |  | Boston | No | 80 | 2000-11-02 17:00
2.1.7.11.4 | Crate Fanout Demo Tester | 23640 | 23640 | 0 | 0 | 0 | 0 | 23640 | 23640 | 23640 | 0 | 23640 | Adams/UIC | No | 75 | 2000-05-25 17:00
2.1.7.11.4.1 | Crate Fanout Demo Tester Design & Testing | 21140 | 21140 | 0 | 0 | 0 | 0 | 21140 | 21140 | 21140 | 0 | 21140 | UIC | No | 100 | 2000-03-02 17:00 | Closed
2.1.7.11.4.2 | Crate Fanout Demo Tester M&S | 2500 | 2500 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 0 | 2500 | UIC | No | 100 | 2000-03-30 17:00 | Closed
2.1.7.11.4.3 | Crate Fanout Demo Tester | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2000-04-27 17:00
2.1.7.11.4.4 | FEE Emulator Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2000-05-25 17:00
2.1.7.12
2.1.7.12.1 | Demontrator Integration Tests (Maryland) | 24600 | 24600 | 24600 | 0 | 24600 | 0 | 0 | 24000 | 24599.9994 | 24600 | -0.0005722 | Maryland | No | 100 | 2000-12-08 17:00 | Closed
2.1.7.12.2 | Demontrator Integration Tests (Boston) | 18976.4062 | 18976.4062 | 12644.54 | 9023.46 | 21668 | 0 | 6331.8662 | 21140 | 22325.1831 | 22325.1831 |  | Boston | No | 100 | 2004-02-24 17:00
2.1.7.12.3 | Demontrator Integration Tests (UIC) | 21668.5 | 21668.5 | 0 | 0 | 0 | 0 | 21668.5 | 21140 | 21668.4995 | 0 | 21668.4995 | UIC | No | 100 | 2000-12-08 17:00 | Closed
2.1.7.12.4 | Prototype Integration Tests (Maryland) | 42680.1641 | 5277.6006 | 0 | 42680 | 42680 | -37402.5635 | 5277.6006 | 40584 | 42680.1655 | 42680.1655 |  | Maryland | No | 10 | 2002-04-01 17:00
2.1.7.12.5 | Prototype Integration Tests (Boston) | 17785.5059 | 12449.8545 | 0 | 0 | 0 | -5335.6514 | 12449.8545 | 16912 | 17785.5056 | 17785.5056 |  | Boston | No | 80 | 2002-02-04 17:00
2.1.7.12.6 | Prototype Integration Tests (UIC) | 17785.5059 | 17785.5059 | 0 | 0 | 0 | 0 | 17785.5059 | 16912 | 17785.5056 | 17785.5056 |  | UIC | No | 100 | 2002-02-04 17:00
2.1.7.12.7 | Installation at CERN (Maryland) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2004-09-29 17:00
2.1.7.12.8 | Installation at CERN (Boston) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2004-09-29 17:00
2.1.7.12.9 | Installation at CERN (UIC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2004-09-29 17:00
2.1.7.13 | Trigger/DAQ Coordination | 347603.4883 | 104940.5 | 125172.9922 | 166560.1 | 291733.0922 | -242662.9883 | -20232.4922 | 403200 | 419006.1338 | 419006.1338 | 0 | Baden/Maryland | No | 31 | 2004-09-28 17:00
2.1.7.13.1 | Trigger/DAQ HCAL DAQ/Trigger Integration (Maryland) | 291501.4062 | 104940.5 | 125172.9922 | 166560.1 | 291733.0922 | -186560.9062 | -20232.4922 | 283200 | 291501.3988 | 291501.3988 |  | Maryland | No | 36 | 2002-08-05 17:00
2.1.7.13.2 | Trigger/DAQ Project Engineering (Boston) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 26 | 2004-09-28 17:00
2.1.7.13.3 | Trigger/DAQ Project Engineering (Maryland) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 35 | 2004-09-28 17:00
2.1.7.13.4 | Trigger/DAQ Project Engineering (UIC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 90 | 2004-09-28 17:00
2.1.7.13.5 | Trigger/DAQ Shipping Costs (Boston) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2004-09-28 17:00
2.1.7.13.6 | Trigger/DAQ Shipping Costs (Maryland) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2004-09-28 17:00
2.1.7.13.7 | Trigger/DAQ Shipping Costs (UIC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2004-09-28 17:00
2.1.7.13.10 | DCC Module Software Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 32 | 2003-09-26 17:00
2.1.7.13.11 | TRIDAS Engineering FY02,FY03 (Maryland) | 56102.082 | 0 | 0 | 0 | 0 | -56102.082 | 0 | 120000 | 127504.735 | 127504.735 |  | Maryland | No | 0 | 2003-03-28 17:00
2.1.7.14 | HCAL DAQ Concentrator (HDC) Module (deleted) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Adams/UIC | No | 100 | 2002-11-08 17:00
2.1.7.14.1 | HDC Prototype Module (9U VME) (deleted) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Adams/UIC | No | 100 | 2002-05-23 17:00
2.1.7.14.2 | HDC 2nd Prototype Module (9U VME) (deleted) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Adams/UIC | No | 100 | 2002-02-28 17:00
2.1.7.14.3 | HDC Module Production (deleted) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Adams/UIC | No | 100 | 2002-11-08 17:00
2.1.7.15 | SLB Modules | 15774.75 | 15774.75 | 0 | 0 | 0 | 0 | 15774.75 | 160440 | 172007.2019 | 172007.2019 | 0 | Baden/Maryland | No | 8 | 2003-10-17 17:00
2.1.7.15.1 | SLB Trigger Links M&S (20% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57600 | 61847.1222 | 61847.1222 |  | Maryland | No | 0 | 2003-10-17 17:00
2.1.7.15.2 | SLB Trigger Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21840 | 23518.8348 | 23518.8348 |  | Maryland | No | 0 | 2003-10-17 17:00
2.1.7.15.3 | SLB Trigger Links Transition Boards | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66000 | 70866.4942 | 70866.4942 |  | Maryland | No | 0 | 2003-10-17 17:00
2.1.7.16 | Teststand equipment | 15774.75 | 15774.75 | 0 | 0 | 0 | 0 | 15774.75 | 15000 | 15774.7507 | 15774.7507 | 0 | Baden/Maryland | No | 93 | 2002-03-29 17:00
2.1.7.16.1 | CPUs | 5258.25 | 5258.25 | 0 | 0 | 0 | 0 | 5258.25 | 5000 | 5258.2502 | 5258.2502 |  | Boston | No | 80 | 2002-03-15 17:00
2.1.7.16.2 | Oscilloscope | 10516.5 | 10516.5 | 0 | 0 | 0 | 0 | 10516.5 | 10000 | 10516.5005 | 10516.5005 |  | Boston | No | 100 | 2002-03-29 17:00
2.1.10.11 | 2002 test beam | 141972.752 | 42066 | 87136.5078 | 0 | 87136.5078 | -99906.752 | -45070.5078 | 135000 | 141972.7564 | 141972.7564 | 0 | FNAL | No | 46 | 2002-09-17 17:00
2.1.10.11.1 | travel - FNAL | 26291.252 | 0 | 29506.6094 | 0 | 29506.6094 | -26291.252 | -29506.6094 | 25000 | 26291.2512 | 26291.2512 |  | FNAL | No | 75 | 2002-06-25 17:00
2.1.10.11.2 | installation | 21033 | 0 | 0 | 0 | 0 | -21033 | 0 | 20000 | 21033.0009 | 21033.0009 |  | FNAL | No | 95 | 2002-05-28 17:00
2.1.10.11.3 | Test Beam RBX/Electronics M&S | 42066 | 42066 | 57629.8984 | 0 | 57629.8984 | 0 | -15563.8984 | 40000 | 42066.0019 | 42066.0019 |  | FNAL | No | 95 | 2002-06-25 17:00
2.1.10.11.4 | travel - Princeton | 10516.5 | 0 | 0 | 0 | 0 | -10516.5 | 0 | 10000 | 10516.5005 | 10516.5005 |  | Princeton | No | 0 | 2002-09-17 17:00
2.1.10.11.5 | Test BeamTRIDAS M&S | 42066 | 0 | 0 | 0 | 0 | -42066 | 0 | 40000 | 42066.0019 | 42066.0019 |  | Maryland | No | 60 | 2002-06-25 17:00
2.1.11.1 | Maintenance Engineers | 0 | 0 | 0 | 0 | [6 empty] | 0 | FNAL | No | 0 | 2004-12-31 17:00
2.2 | Outer Barrel Calorimeter (HO) | [11 empty] | Mondal/TATA | No | 18 | 2005-11-30 08:00
2.2.7 | Trigger/DAQ Electronics | 0 | 0 | 0 | 252712 | 252712 | 0 | 0 | 357304 | 383810.7846 | 383810.7846 | 0 | Baden/Maryland | No | 27 | 2005-06-15 17:00
2.2.7.1 | HTR Module Production | 0 | 0 | 0 | 252712 | 252712 | 0 | 0 | 276804 | 297214.0766 | 297214.0766 | 0 | Baden/Maryland | No | 0 | 2003-06-20 17:00
2.2.7.1.1 | HTR Module M&S (10% Spares) | 0 | 0 | 0 | 252712 | 252712 | 0 | 0 | 276804 | 297214.0766 | 297214.0766 |  | Maryland | No | 0 | 2003-06-20 17:00
2.2.7.1.2 | HTR Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-01-31 17:00
2.2.7.1.3 | Ship HTR Modules to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-02-14 17:00
2.2.7.1.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-04-18 17:00
2.2.7.2 | VME Transition Module (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Baden/Maryland | No | 100 | 1998-05-20 17:00
2.2.7.3 | Data Concentrator Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 48318.0642 | 48318.0642 | 0 | Hazen/Boston | No | 0 | 2003-04-18 17:00
2.2.7.3.1 | Data Concentrator M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 48318.0642 | 48318.0642 |  | Boston | No | 0 | 2003-04-18 17:00
2.2.7.3.2 | Data Concentrator Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2003-01-31 17:00
2.2.7.3.3 | Ship Data Concentrator Modules to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2003-02-14 17:00
2.2.7.3.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2003-04-18 17:00
2.2.7.4 | VME Crates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 23622.1647 | 23622.1647 | 0 | Baden/Maryland | No | 0 | 2003-06-06 17:00
2.2.7.4.1 | VME Subracks M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 23622.1647 | 23622.1647 |  | FIT | No | 0 | 2003-04-25 17:00
2.2.7.4.2 | VME Subracks Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-05-23 17:00
2.2.7.4.3 | Ship VME Subracks to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-06 17:00
2.2.7.5 | VME Relay Racks M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6603.4684 | 6603.4684 |  | Maryland | No | 0 | 2005-06-15 17:00
2.2.7.6 | Data Link (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Baden/Maryland | No | 100 | 1997-12-09 17:00
2.2.7.7 | DAQ Links | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 0 | 2003-07-11 17:00
2.2.7.7.1 | DAQ Link M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-27 17:00
2.2.7.7.2 | Ship DAQ Links to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-11 17:00
2.2.7.7.3 | Ship PCI Receiver Modules to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2002-07-29 17:00
2.2.7.8 | DCC Input Link | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 0 | 2003-07-11 17:00
2.2.7.8.1 | DCC Input Link M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-27 17:00
2.2.7.8.2 | Ship DCC Input Link to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-11 17:00
2.2.7.10 | Crate Fanout Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8053.0107 | 8053.0107 | 0 | Adams/UIC | No | 0 | 2003-07-04 17:00
2.2.7.10.1 | Crate Fanout Production Module M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8053.0107 | 8053.0107 |  | UIC | No | 0 | 2003-05-23 17:00
2.2.7.10.2 | Crate Fanout Production Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-06-20 17:00
2.2.7.10.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-07-04 17:00
2.2.7.10.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-04-18 17:00
2.3 | Endcap Hadron Calorimeter (HE) | [11 empty] | Golutvin/RDMS | No | 22 | 2006-03-14 17:00
2.3.7 | Trigger/DAQ Electronics | 0 | 0 | 0 | 309564 | 309564 | 0 | 0 | 417936 | 448752.4108 | 448752.4108 | 0 | Baden/Maryland | No | 32 | 2003-10-09 15:11
2.3.7.1 | HTR Module Production | 0 | 0 | 0 | 303254 | 303254 | 0 | 0 | 315836 | 339124.0917 | 339124.0917 | 0 | Baden/Maryland | No | 29 | 2003-08-01 17:00
2.3.7.1.1 | HTR Module M&S (10% Spares) | 0 | 0 | 0 | 303254 | 303254 | 0 | 0 | 312686 | 335741.8273 | 335741.8273 |  | Maryland | No | 0 | 2003-06-20 17:00
2.3.7.1.2 | HTR Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-18 17:00
2.3.7.1.3 | Ship HTR Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3150 | 3382.2645 | 3382.2645 |  | Maryland | No | 0 | 2003-08-01 17:00
2.3.7.2 | VME Transition Module (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Boston | No | 100 | 1998-01-28 17:00
2.3.7.3 | Data Concentrator Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 48318.0642 | 48318.0642 | 0 | Hazen/Boston | No | 0 | 2003-05-30 17:00
2.3.7.3.1 | Data Concentrator M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 48318.0642 | 48318.0642 |  | Boston | No | 0 | 2003-04-18 17:00
2.3.7.3.2 | Data Concentrator Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2003-05-16 17:00
2.3.7.3.3 | Ship Data Concentrator Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2003-05-30 17:00
2.3.7.3.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-04-18 17:00
2.3.7.4 | VME Crates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 23622.1647 | 23622.1647 | 0 | Baden/Maryland | No | 0 | 2003-08-01 17:00
2.3.7.4.1 | VME Subracks M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 23622.1647 | 23622.1647 |  | FIT | No | 0 | 2003-06-20 17:00
2.3.7.4.2 | VME Subracks Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-18 17:00
2.3.7.4.3 | Ship VME Subracks to CERN (Zero Cost-Purchase in Europe) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-08-01 17:00
2.3.7.4.4 | Ship VME Crates to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2002-02-04 17:00
2.3.7.5 | VME Relay Racks M&S (no Spares) | 0 | 0 | 0 | 6310 | 6310 | 0 | 0 | 6000 | 6442.4086 | 6442.4086 |  | Maryland | No | 0 | 2003-09-24 12:00
2.3.7.6 | Level 1Trigger Links | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21600 | 23192.6708 | 23192.6708 | 0 | Baden/Maryland | No | 7 | 2003-10-09 15:11
2.3.7.6.1 | Level 1 Link M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21600 | 23192.6708 | 23192.6708 |  | Maryland | No | 0 | 2003-08-28 15:11
2.3.7.6.2 | Level 1 Link Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-09-25 15:11
2.3.7.6.3 | Ship Level 1 Link to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-10-09 15:11
2.3.7.7 | DAQ Links | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 0 | 2003-07-11 17:00
2.3.7.7.1 | DAQ Link M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-27 17:00
2.3.7.7.2 | Ship DAQ Link to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-11 17:00
2.3.7.8 | PCI Receiver Module (deleted WBS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8053.0107 | 8053.0107 | 0 | Hazen/Boston | No | 51 | 2003-09-19 17:00
2.3.7.10 | Crate Fanout Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8053.0107 | 8053.0107 | 0 | Adams/UIC | No | 0 | 2003-09-19 17:00
2.3.7.10.1 | Crate Fanout Production Module M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8053.0107 | 8053.0107 |  | UIC | No | 0 | 2003-07-11 17:00
2.3.7.10.2 | Crate Fanout Production Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-09-05 17:00
2.3.7.10.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-09-19 17:00
2.3.7.10.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-04-18 17:00
2.3.7.10 | Crate Fanout Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8053.0107 | 8053.0107 | 0 | Adams/UIC | No | 0 | 2003-09-19 17:00
2.3.7.10.1 | Crate Fanout Production Module M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 8053.0107 | 8053.0107 |  | UIC | No | 0 | 2003-07-11 17:00
2.3.7.10.2 | Crate Fanout Production Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-09-05 17:00
2.3.7.10.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-09-19 17:00
2.3.7.10.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-04-18 17:00
2.5 | Forward Calorimeter (HF) | [11 empty] | Akchurin/Texas Tech | No | 23 | 2005-11-30 08:00
2.5.7 | Trigger/DAQ Electronics | 36807.75 | 0 | 137838.7656 | 102865.23 | 240703.9956 | -36807.75 | -137838.7656 | 293994 | 314898.6122 | 314898.6122 | 0 | Baden/Maryland | No | 8 | 2003-09-08 10:13
2.5.7.1 | HTR Module Production | 0 | 0 | 137838.7656 | 99710.23 | 237548.9956 | 0 | -137838.7656 | 228694 | 245556.6973 | 245556.6973 | 0 | Baden/Maryland | No | 6 | 2003-08-01 17:00
2.5.7.1.1 | HTR Module M&S (10% Spares) | 0 | 0 | 137838.7656 | 99710.23 | 237548.9956 | 0 | -137838.7656 | 225544 | 242174.4328 | 242174.4328 |  | Maryland | No | 0 | 2003-06-20 17:00
2.5.7.1.2 | HTR Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-18 17:00
2.5.7.1.3 | Ship HTR Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3150 | 3382.2645 | 3382.2645 |  | Maryland | No | 0 | 2003-08-01 17:00
2.5.7.2 | VME Transition Module (deleted WBS) | 0 | 0 | 0 | 0 | [6 empty] | 0 | Elias/FNAL | No | 100 | 1997-10-28 17:00
2.5.7.3 | Data Concentrator Module Production | 36807.75 | 0 | 0 | 0 | 0 | -36807.75 | 0 | 35000 | 36807.7517 | 36807.7517 | 0 | Hazen/Boston | No | 0 | 2002-10-11 17:00
2.5.7.3.1 | Data ConcentratorModule M&S (20% Spares) | 36807.75 | 0 | 0 | 0 | 0 | -36807.75 | 0 | 35000 | 36807.7517 | 36807.7517 |  | Boston | No | 0 | 2002-08-16 17:00
2.5.7.3.2 | Data Concentrator Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2002-09-27 17:00
2.5.7.3.3 | Ship Data Concentrator Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2002-10-11 17:00
2.5.7.3.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Boston | No | 0 | 2002-08-16 17:00
2.5.7.4 | VME Crates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | 17716.6235 | 17716.6235 | 0 | Baden/Maryland | No | 0 | 2003-06-06 17:00
2.5.7.4.1 | VME Subracks M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | 17716.6235 | 17716.6235 |  | FIT | No | 0 | 2003-04-25 17:00
2.5.7.4.2 | VME Subracks Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-05-23 17:00
2.5.7.4.3 | Ship VME Subracks to CERN (Zero Cost-Purchase in Europe) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-06 17:00
2.5.7.5 | VME Relay Racks M&S (no Spares) | 0 | 0 | 0 | 3155 | 3155 | 0 | 0 | 6000 | 6442.4086 | 6442.4086 |  | Maryland | No | 0 | 2003-05-23 17:00
2.5.7.6 | Level 1 Trigger Cables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1932.7226 | 1932.7226 | 0 | Baden/Maryland | No | 12 | 2003-09-08 10:13
2.5.7.6.1 | Level 1 Link M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1932.7226 | 1932.7226 |  | Maryland | No | 0 | 2003-07-28 10:13
2.5.7.6.2 | Level 1 Link Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-08-25 10:13
2.5.7.6.3 | Ship Level 1 Link to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-09-08 10:13
2.5.7.7 | DAQ Links | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Baden/Maryland | No | 0 | 2003-07-11 17:00
2.5.7.7.1 | DAQ Link M&S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-06-27 17:00
2.5.7.7.2 | Ship DAQ Link to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Maryland | No | 0 | 2003-07-11 17:00
2.5.7.8 | Crate Fanout Module Production | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6442.4086 | 6442.4086 | 0 | Adams/UIC | No | 0 | 2003-08-01 17:00
2.5.7.8.1 | Crate Fanout Production Module M&S (10% Spares) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6442.4086 | 6442.4086 |  | UIC | No | 0 | 2003-06-20 17:00
2.5.7.8.2 | Crate Fanout Production Module Engineering Support | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-07-18 17:00
2.5.7.8.3 | Ship Crate Fanout Production Module to CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-08-01 17:00
2.5.7.8.4 | Spare Parts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | UIC | No | 0 | 2003-04-18 17:00
2.5.11.1 | Rate Monitor Electronics | 93377.5 | 0 | 0 | 0 | 0 | -93377.5 | 0 | 101660 | 104999.6022 | 104999.6022 | 0 | Snow/Nebraska | No | 0 | 2003-12-09 17:00
2.5.11.1.1 | Electronics Design | 13837.5 | 0 | 0 | 0 | 0 | -13837.5 | 0 | 13500 | 13837.4997 | 13837.4997 |  | Nebraska | No | 0 | 2000-12-01 17:00
2.5.11.1.2 | Electronics Installation and Testing (Phase 1) | 9840 | 0 | 0 | 0 | 0 | -9840 | 0 | 9600 | 9839.9998 | 9839.9998 |  | Nebraska | No | 0 | 2001-04-06 17:00
2.5.11.1.3 | EPICS IOC Luminosity | 14350 | 0 | 0 | 0 | 0 | -14350 | 0 | 14000 | 14349.9997 | 14349.9997 |  | Nebraska | No | 0 | 2001-05-04 17:00
2.5.11.1.4 | EPICS Data Handling Boards | 20500 | 0 | 0 | 0 | 0 | -20500 | 0 | 20000 | 20499.9995 | 20499.9995 |  | Nebraska | No | 0 | 2001-05-04 17:00
2.5.11.1.5 | VME Electronics | 4100 | 0 | 0 | 0 | 0 | -4100 | 0 | 4000 | 4099.9999 | 4099.9999 |  | Nebraska | No | 0 | 2001-05-04 17:00
2.5.11.1.6 | VME Crates | 30750 | 0 | 0 | 0 | 0 | -30750 | 0 | 30000 | 30749.9993 | 30749.9993 |  | Nebraska | No | 0 | 2001-06-01 17:00
2.5.11.1.7 | Electronics Installation and Testing (Phase 2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2560 | 2817.4799 | 2817.4799 |  | Nebraska | No | 0 | 2003-10-28 17:00
2.5.11.1.8 | Installation at CERN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8804.6246 | 8804.6246 |  | Nebraska | No | 0 | 2003-12-09 17:00
Note on C5: Drew Baden: work that has been schedule
Note on D5: Drew Baden: work performed
Note on E5: Drew Baden: actual costs that have come in and charged
Note on F5: Drew Baden: what has been committed
Note on G5: Drew Baden: what has already been paid (not necessarily what the budget is)
Note on H5: Drew Baden: schedule variance (difference between work scheduled and performed)
Note on I5: Drew Baden: difference between work performed and actuals
Note on J5: Drew Baden: flat budget
Note on K5: Drew Baden: includes inflation
Note on L5: Drew Baden: estimate at completion

## WBS 10_02
[7 empty] | CPR 8/02 | Increase M&S |  | ENG
WBS | Task Name | Cost3 | % Work Complete | $ Remaining | M&S ESTIMATE | BAC | BAC infl | BAC infl | BAC | Remaining
2 | Hadron Calorimeter (HCAL) | 37455592.73 | 45% | 20600576.0015
2.1 | Barrel Hadron Calorimeter (HB) | 27718930.35 | 60% | 11087572.14 |  |  | 2325528.5915
2.1.7 | Trigger/DAQ Electronics | 2241221.72 | 6% | 2106748.4168 |  |  | 2325528.5915
2.1.7.1 | HCAL Trigger Readout (HTR) Module | 660023.2 | 8% | 607221.344 |  |  | 697840.419
2.1.7.1.1 | VME Readout Module Development | 660023.2 | 8% | 607221.344 |  |  | 697840.419
2.1.7.1.1.1 | HTR Module Requirements Report | 0 | 100% | 0 |  |  | 0 |  |  | 0
2.1.7.1.1.2 | HTR Module Specification Report | 6720 | 100% | 0 |  | 6720 | 6957.2161 |  |  | 0
2.1.7.1.1.3 | HTR Demonstrator Module (6U, N=8ch) | 58884 | 100% | 0 |  |  | 58884
2.1.7.1.1.3.1 | HTR Demonstrator Module Design & Testing | 40584 | 100% | 0 |  | 40584 | 40584 |  |  | 0
2.1.7.1.1.3.2 | HTR Demonstrator Module M&S | 18300 | 100% | 0 |  | 18300 | 18300
2.1.7.1.1.4 | HTR Prototype Module (9U, N=32ch) | 98520 | 100% | 0 |  |  | 101081.1715
2.1.7.1.1.4.1 | HTR Prototype Module Design & Testing | 68520 | 100% | 0 |  |  | 70331.1722 |  |  | 0
2.1.7.1.1.4.2 | HTR Prototype Module M&S | 30000 | 100% | 0 |  | 30000 | 30749.9993
2.1.7.1.1.5 | HTR 2nd Prototype Module (9U, N=32ch) | 70011.2 | 88% | 8401.344 |  |  | 73627.2818
2.1.7.1.1.5.1 | 2nd HTR Prototype Module Design & Testing | 50011.2 | 80% | 10002.24 |  |  | 52594.2808 |  |  | 10002.24
2.1.7.1.1.5.2 | 2nd HTR Prototype Module M&S | 20000 | 90% | 2000 |  | 20000 | 21033.0009
2.1.7.1.1.6 | HTR Production Module (9U, N=48ch) | 425888 | 0% | 425888 |  |  | 457290.7496
2.1.7.1.1.6.1 | HTR Production Module M&S (10% Spares) | 312686 | 0% | 312686 | 337938 | 312686 | 335741.8273 | 2196.1727 | 25252
2.1.7.1.1.6.2 | HTR Production Module Engineering Support | 110052 | 0% | 110052 |  |  | 118166.6578 |  |  | 110052
2.1.7.1.1.6.3 | Ship HTR Production Module to CERN | 3150 | 0% | 3150 | 1620 | 3150 | 3382.2645 | -1762.2645 | -1530
2.1.7.1.1.6.4 | Spare Parts | 0 | 0% | 0 |  | 0 | 0
2.1.7.3 | Data Concentrator Card (DCC) Module | 383539.2 | 41% | 226288.128 |  |  | 395894.7248
2.1.7.3.1 | DCC Specification Report | 56412 | 100% | 0 |  |  | 56412
2.1.7.3.3 | DCC Demonstrator Module | 113480 | 100% | 0 |  |  | 116675.1984
2.1.7.3.3.1 | DCC Demonstrator Module Design & Testing | 74480 | 100% | 0 |  |  | 77675.1984 |  |  | 0
2.1.7.3.3.2 | DCC Demonstrator Module M&S | 39000 | 100% | 0 |  | 39000 | 39000
2.1.7.3.4 | DCC Prototype Module (9U, N=18ch) | 73200 | 71% | 21228 |  |  | 75106.222
2.1.7.3.4.1 | DCC Prototype Module Design & Testing | 53200 | 80% | 10640 |  |  | 54606.2224 |  |  | 10640
2.1.7.3.4.2 | DCC Prototype Module M&S | 20000 | 60% | 8000 |  | 20000 | 20499.9995
2.1.7.3.5 | DCC 2nd Prototype Module (9U, N=18ch) | 74667.2 | 46% | 40320.288 |  |  | 78523.7644
2.1.7.3.5.1 | DCC Prototype Module Design & Testing | 54667.2 | 0% | 54667.2 |  |  | 57490.7635 |  |  | 54667.2
2.1.7.3.5.2 | DCC Prototype Module M&S | 20000 | 85% | 3000 |  | 20000 | 21033.0009
2.1.7.3.6 | DCC Module Production | 65780 | 0% | 65780 |  |  | 69177.5401
2.1.7.3.6.1 | DCC Module M&S (10% Spares) | 55000 | 0% | 55000 | 68000 | 55000 | 57840.7526 | 10159.2474 | 13000
2.1.7.3.6.2 | DCC Production Module Engineering Support | 10780 | 0% | 10780 |  |  | 11336.7875 |  |  | 10780
2.1.7.3.6.3 | Ship DCC Module to CERN | 0 | 0% | 0 | 170 | 0 | 0 | 170 | 170
2.1.7.3.6.4 | Spare Parts | 0 | 0% | 0 |  | 0 | 0
2.1.7.4 | VME Crates | 34484 | 0% | 34484 |  |  | 37026.6695
2.1.7.4.1 | VME Subrack M&S | 27500 | 0% | 27500 | 45255 | 27500 | 29527.7059 | 15727.2941 | 17755
2.1.7.4.2 | VME Crates Engineering Support | 6984 | 0% | 6984 |  |  | 7498.9636 |  |  | 6984
2.1.7.4.3 | Ship VME Crates to CERN (Zero Cost-Purchase in Europe) | 0 | 0% | 0 |  | 0 | 0
2.1.7.5 | VME Relay Racks | 8400 | 0% | 8400 |  |  | 9083.7959
2.1.7.5.1 | VME Relay Racks M&S (no Spares) | 6000 | 0% | 6000 | 9000 | 6000 | 6442.4086 | 2557.5914 | 3000
2.1.7.5.2 | VME Relay Racks Engineering Support | 2400 | 0% | 2400 |  |  | 2641.3874 |  |  | 2400
2.1.7.5.3 | Ship VME Relay Racks to CERN (Zero Cost-Purchase in Europe) | 0 | 0% | 0 |  | 0 | 0
2.1.7.6 | Level 1 Trigger Links | 35568 | 0% | 35568 |  |  | 38190.598
2.1.7.6.1 | Level 1 Trigger Links M&S (20% Spares) | 28800 | 0% | 28800 | 47520 | 28800 | 30923.5611 | 16596.4389 | 18720
2.1.7.6.2 | Level 1 Trigger Links Engineering Support | 6768 | 0% | 6768 |  |  | 7267.0369 |  |  | 6768
2.1.7.10 | HCAL Readout Control (Crate Fanout) Module | 187785 | 46% | 101403.9 |  |  | 194183.94
2.1.7.10.2 | Crate Fanout Specification Report | 4368 | 100% | 0 |  |  | 4522.1905 |  |  | 0
2.1.7.10.3 | Crate Fanout Demonstrator Module (6U VME) | 46240 | 100% | 0 |  |  | 46240
2.1.7.10.3.1 | Crate Fanout Demonstrator Module Design & Testing | 21140 | 100% | 0 |  |  | 21140 |  |  | 0
2.1.7.10.3.2 | Crate Fanout Demonstrator Module M&S | 25100 | 100% | 0 |  | 25100 | 25100
2.1.7.10.4 | Crate Fanout Prototype Module (9U VME) | 60249 | 100% | 0 |  |  | 61755.2236
2.1.7.10.4.1 | Crate Fanout Prototype Module Design & Testing | 30249 | 100% | 0 |  |  | 31005.2243 |  |  | 0
2.1.7.10.4.2 | Crate Fanout Prototype Module M&S | 30000 | 100% | 0 |  | 30000 | 30749.9993
2.1.7.10.5 | Crate Fanout 2nd Prototype Module (9U VME) | 42280 | 95% | 2114 |  |  | 44463.764
2.1.7.10.5.1 | Crate Fanout Prototype Module Design & Testing | 21280 | 95% | 1064 |  |  | 22379.113 |  |  | 1064
2.1.7.10.5.2 | Crate Fanout Prototype Module M&S | 21000 | 95% | 1050 |  | 21000 | 22084.651
2.1.7.10.6 | Crate Fanout Module Production | 34648 | 0% | 34648 |  |  | 37202.762
2.1.7.10.6.1 | Crate Fanout Production Module M&S (20% Spares) | 9000 | 0% | 9000 | 16500 | 9000 | 9663.6128 | 6836.3872 | 7500
2.1.7.10.6.2 | Crate Fanout Production Module Engineering Support | 25648 | 0% | 25648 |  |  | 27539.1491 |  |  | 25648
2.1.7.10.6.3 | Ship Crate Fanout Production Module to CERN | 0 | 0% | 0 | 110 | 0 | 0 | 110 | 110
2.1.7.10.6.4 | Spare Parts | 0 | 0% | 0 |  | 0 | 0
2.1.7.11 | Tester Stations | 215094.32 | 97% | 6452.8296 |  |  | 215450.2498
2.1.7.11.1 | Universal Tester Module | 79264.12 | 100% | 0 |  |  | 79559.3697
2.1.7.11.1.1 | Universal Tester Module Design & Testing | 63072.12 | 100% | 0 |  |  | 63072.12 |  |  | 0
2.1.7.11.1.2 | Universal Tester Module M&S | 4382 | 100% | 0 |  | 4382 | 4382
2.1.7.11.1.3 | Universal Tester Module Assembly | 0 | 100% | 0 |  |  | 0 |  |  | 0
2.1.7.11.1.4 | Universal Tester Module Evaluation | 0 | 100% | 0 |  |  | 0 |  |  | 0
2.1.7.11.1.5 | TTC and LHC Emulator Setup | 11810 | 100% | 0 |  |  | 12105.2497 |  |  | 0
2.1.7.11.2 | Front-End Electronic (FEE) Emulator | 64359 | 100% | 0 |  |  | 64359
2.1.7.11.2.1 | FEE Emulator Design & Testing | 50184 | 100% | 0 |  |  | 50184 |  |  | 0
2.1.7.11.2.2 | FEE Emulator M&S | 14175 | 100% | 0 |  | 14175 | 14175
2.1.7.11.2.3 | FEE Emulator Assembly | 0 | 100% | 0 |  |  | 0 |  |  | 0
2.1.7.11.2.4 | FEE Emulator Evaluation | 0 | 100% | 0 |  |  | 0 |  |  | 0
2.1.7.11.3 | DCC Module Test Equipment | 47831.2 | 85% | 7174.68 |  |  | 47891.8801
2.1.7.11.3.1 | DCC Module Test Equipment | 25000 | 90% | 2500 |  | 25000 | 25000
2.1.7.11.3.2 | DCC Module Software Development | 22831.2 | 80% | 4566.24 |  |  | 22891.8801 |  |  | 4566.24
2.1.7.11.4 | Crate Fanout Demo Tester | 23640 | 100% | 0 |  |  | 23640
2.1.7.11.4.1 | Crate Fanout Demo Tester Design & Testing | 21140 | 100% | 0 |  |  | 21140 |  |  | 0
2.1.7.11.4.2 | Crate Fanout Demo Tester M&S | 2500 | 100% | 0 |  | 2500 | 2500
2.1.7.11.4.3 | Crate Fanout Demo Tester | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.1.7.11.4.4 | FEE Emulator Evaluation | 0 | 0% | 0 | [5 empty] | 0
2.1.7.12 | System Integration/Milestones | 140688 | 39% | 85819.68 |  |  | 146844.8587
2.1.7.12.1 | Demontrator Integration Tests (Maryland) | 24000 | 100% | 0 |  |  | 24599.9994 |  |  | 0
2.1.7.12.2 | Demontrator Integration Tests (Boston) | 21140 | 100% | 0 |  |  | 22325.1831 |  |  | 0
2.1.7.12.3 | Demontrator Integration Tests (UIC) | 21140 | 100% | 0 |  |  | 21668.4995 |  |  | 0
2.1.7.12.4 | Prototype Integration Tests (Maryland) | 40584 | 12% | 35713.92 |  |  | 42680.1655 |  |  | 35713.92
2.1.7.12.5 | Prototype Integration Tests (Boston) | 16912 | 80% | 3382.4 |  |  | 17785.5056 |  |  | 3382.4
2.1.7.12.6 | Prototype Integration Tests (UIC) | 16912 | 100% | 0 |  |  | 17785.5056 |  |  | 0
2.1.7.12.7 | Installation at CERN (Maryland) | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.1.7.12.8 | Installation at CERN (Boston) | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.1.7.12.9 | Installation at CERN (UIC) | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.1.7.13 | Trigger/DAQ Coordination | 403200 | 43% | 229824 |  |  | 419006.1338
2.1.7.13.1 | Trigger/DAQ HCAL DAQ/Trigger Integration (Maryland) | 283200 | 36% | 181248 |  |  | 291501.3988 |  |  | 181248
2.1.7.13.11 | TRIDAS Engineering FY02,FY03 (Maryland) | 120000 | 0% | 120000 |  |  | 127504.735 |  |  | 120000
2.1.7.15 | SLB Modules | 160440 | 0% | 160440 |  |  | 156232.4512
2.1.7.15.1 | SLB Trigger Links M&S (20% Spares) | 57600 | 0% | 57600 | 143750 | 57600 | 61847.1222 | 81902.8778 | 86150
2.1.7.15.2 | SLB Trigger Engineering | 21840 | 0% | 21840 |  |  | 23518.8348 |  |  | 21840
2.1.7.15.3 | SLB Trigger Links Transition Boards | 66000 | 0% | 66000 | 0 | 66000 | 70866.4942 | -70866.4942 | -66000
2.1.7.16 | Teststand equipment | 15000 | 90% | 1500 |  |  | 15774.7507
2.1.7.16.1 | CPUs | 5000 | 80% | 1000 |  | 5000 | 5258.2502
2.1.7.16.2 | Oscilloscope | 10000 | 100% | 0 |  |  | 10516.5005
2.2 | Outer Barrel Calorimeter (HO) | 1344544.72 | 14% | 1156308.4592 |  |  | 390414.2531
2.2.7 | Trigger/DAQ Electronics | 357304 | 0% | 357304 |  |  | 390414.2531
2.2.7.1 | HTR Module Production | 276804 | 0% | 276804 |  |  | 297214.0766
2.2.7.1.1 | HTR Module M&S (10% Spares) | 276804 | 0% | 276804 | 263674 | 276804 | 297214.0766 | -33540.0766 | -13130
2.2.7.1.2 | HTR Module Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.2.7.1.3 | Ship HTR Modules to CERN | 0 | 0% | 0 | 1260 | 0 | 0 | 1260 | 1260
2.2.7.1.4 | Spare Parts | 0 | 0% | 0 |  | 0 | 0
2.2.7.3 | Data Concentrator Module Production | 45000 | 0% | 45000 |  |  | 48318.0642
2.2.7.3.1 | Data Concentrator M&S (10% Spares) | 45000 | 0% | 45000 | 40000 | 45000 | 48318.0642 | -8318.0642 | -5000
2.2.7.3.2 | Data Concentrator Module Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.2.7.3.3 | Ship Data Concentrator Modules to CERN | 0 | 0% | 0 | 100 | 0 | 0 | 100 | 100
2.2.7.3.4 | Spare Parts | 0 | 0% | 0 |  | 0 | 0 | 0 | 0
2.2.7.4 | VME Crates | 22000 | 0% | 22000 |  |  | 30225.6331
2.2.7.4.1 | VME Subracks M&S | 22000 | 0% | 22000 | 36204 | 22000 | 23622.1647 | 12581.8353 | 14204
2.2.7.4.2 | VME Subracks Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.2.7.4.3 | Ship VME Subracks to CERN | 0 | 0% | 0 |  | 0 | 0 | 0 | 0
2.2.7.5 | VME Relay Racks M&S | 6000 | 0% | 6000 | 9000 | 6000 | 6603.4684 | 2396.5316 | 3000
2.2.7.8 | DCC Input Link | [5 empty] | 0
2.2.7.8.1 | DCC Input Link M&S | 0 | 0% | 0
2.2.7.8.2 | Ship DCC Input Link to CERN | 0 | 0% | 0
2.2.7.10 | Crate Fanout Module Production | 7500 | 0% | 7500 |  |  | 8053.0107
2.2.7.10.1 | Crate Fanout Production Module M&S (10% Spares) | 7500 | 0% | 7500 | 7500 | 7500 | 8053.0107 | -553.0107 | 0
2.2.7.10.2 | Crate Fanout Production Module Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.2.7.10.3 | Ship Crate Fanout Production Module to CERN | 0 | 0% | 0 | 50 | 0 | 0 | 50 | 50
2.2.7.10.4 | Spare Parts | 0 | 0% | 0 |  | 0 | 0
2.3 | Endcap Hadron Calorimeter (HE) | 3215046.56 | 49% | 1639673.7456 |  |  | 448752.4108
2.3.7 | Trigger/DAQ Electronics | 417936 | 0% | 417936 |  |  | 448752.4108
2.3.7.1 | HTR Module Production | 315836 | 0% | 315836 |  |  | 339124.0917
2.3.7.1.1 | HTR Module M&S (10% Spares) | 312686 | 0% | 312686 | 292860 | 312686 | 335741.8273 | -42881.8273 | -19826
2.3.7.1.2 | HTR Module Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.3.7.1.3 | Ship HTR Module to CERN | 3150 | 0% | 3150 | 1400 | 3150 | 3382.2645 | -1982.2645 | -1750
2.3.7.3 | Data Concentrator Module Production | 45000 | 0% | 45000 |  |  | 48318.0642
2.3.7.3.1 | Data Concentrator M&S (10% Spares) | 45000 | 0% | 45000 | 40000 | 45000 | 48318.0642 | -8318.0642 | -5000
2.3.7.3.2 | Data Concentrator Module Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.3.7.3.3 | Ship Data Concentrator Module to CERN | 0 | 0% |  | 100 | 0 | 0 | 100 | 100
2.3.7.3.4 | Spare Parts | 0 | 0% | 0 |  |  | 0
2.3.7.4 | VME Crates | 22000 | 0% | 22000 |  |  | 23622.1647
2.3.7.4.1 | VME Subracks M&S | 22000 | 0% | 22000 | 36204 | 22000 | 23622.1647 | 12581.8353 | 14204
2.3.7.4.2 | VME Subracks Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.3.7.4.3 | Ship VME Subracks to CERN (Zero Cost-Purchase in Europe) | 0 | 0% | 0 |  | 0 | 0
2.3.7.5 | VME Relay Racks M&S (no Spares) | 6000 | 0% | 6000 | 9000 | 6000 | 6442.4086 | 2557.5914 | 3000
2.3.7.6 | Level 1Trigger Links | 21600 | 0% | 21600 |  |  | 23192.6708
2.3.7.6.1 | Level 1 Link M&S (10% Spares) | 21600 | 0% | 21600 | 35640 | 21600 | 23192.6708 | 12447.3292 | 14040
2.3.7.6.2 | Level 1 Trigger Links Engineering Support | 6768 |  | 6768 |  |  | 0 |  |  | 6768
2.3.7.10 | Crate Fanout Module Production | 7500 | 0% | 7500 |  |  | 8053.0107
2.3.7.10.1 | Crate Fanout Production Module M&S (10% Spares) | 7500 | 0% | 7500 | 7500 | 7500 | 8053.0107 | -553.0107 | 0
2.3.7.10.2 | Crate Fanout Production Module Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.3.7.10.3 | Ship Crate Fanout Production Module to CERN | 0 | 0% | 0 |  |  | 0
2.3.7.10.4 | Spare Parts | 0 | 0% | 0 |  |  | 0
2.5 | Forward Calorimeter (HF) | 5177071.1 | 0% | 5177071.1 |  |  | 314898.6122
2.5.7 | Trigger/DAQ Electronics | 293994 | 0% | 293994 |  |  | 314898.6122
2.5.7.1 | HTR Module Production | 228694 | 0% | 228694 |  |  | 245556.6973
2.5.7.1.1 | HTR Module M&S (10% Spares) | 225544 | 0% | 225544 | 196606 | 225544 | 242174.4328 | -45568.4328 | -28938
2.5.7.1.2 | HTR Module Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.5.7.1.3 | Ship HTR Module to CERN | 3150 | 0% | 3150 | 940 | 3150 | 3382.2645 | -2442.2645 | -2210
2.5.7.3 | Data Concentrator Module Production | 35000 | 0% | 35000 |  |  | 36807.7517
2.5.7.3.1 | Data ConcentratorModule M&S (20% Spares) | 35000 | 0% | 35000 | 28000 | 35000 | 36807.7517 | -8807.7517 | -7000
2.5.7.3.2 | Data Concentrator Module Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.5.7.3.3 | Ship Data Concentrator Module to CERN | 0 | 0% | 0 | 70 |  | 0 | 70 | 70
2.5.7.3.4 | Spare Parts | 0 | 0% | 0 |  |  | 0
2.5.7.4 | VME Crates | 16500 | 0% | 16500 |  |  | 17716.6235
2.5.7.4.1 | VME Subracks M&S | 16500 | 0% | 16500 | 27153 | 16500 | 17716.6235 | 9436.3765 | 10653
2.5.7.4.2 | VME Subracks Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.5.7.4.3 | Ship VME Subracks to CERN (Zero Cost-Purchase in Europe) | 0 | 0% | 0 |  |  | 0
2.5.7.5 | VME Relay Racks M&S (no Spares) | 6000 | 0% | 6000 | 9000 | 6000 | 6442.4086 | 2557.5914 | 3000
2.5.7.6 | Level 1 Trigger Cables | 1800 | 0% | 1800 |  |  | 1932.7226
2.5.7.6.1 | Level 1 Link M&S (10% Spares) | 1800 | 0% | 1800 | 2970 | 1800 | 1932.7226 | 1037.2774 | 1170
2.5.7.6.2 | Level 1 Link Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.5.7.6.3 | Ship Level 1 Link to CERN | 0 | 0% | 0 |  |  | 0
2.5.7.8 | Crate Fanout Module Production | 6000 | 0% | 6000 |  |  | 6442.4086
2.5.7.8.1 | Crate Fanout Production Module M&S (10% Spares) | 6000 | 0% | 6000 | 6000 | 6000 | 6442.4086 | -442.4086 | 0
2.5.7.8.2 | Crate Fanout Production Module Engineering Support | 0 | 0% | 0 |  |  | 0 |  |  | 0
2.5.7.8.3 | Ship Crate Fanout Production Module to CERN | 0 | 0% | 0 | 40 | 0 | 0 | 40 | 40
2.5.7.8.4 | Spare Parts | 0 | 0% | 0 |  |  | 0
| TOTAL | [6 empty] | -32563.5567 | 86164 | 612524
Note on F2: Drew Baden: from Cost 10_02
Note on I2: Drew Baden: increased costs to finish (this is what needs to be added)
Note on K2: Drew Baden: remaining funds as reported in the aug 2002 cpr

## Task_Table 9_01
Parameters
| Swiss Franc exchange rate |  |  |  | 1.67
Labor rates
| Technican daily rate |  |  |  | 218.4
| Engineer3 Maryland |  |  |  | 480
| Engineer Boston |  |  |  | 422.8
| Engineer UIC |  |  |  | 422.8
| Engineer FNAL |  |  |  | 422.8
| HTR Production Module | [5 empty] | 2500 |  |  | 5126
| DCC Production Module | [5 empty] | 7800 |  |  | 6200
| HRC Production Module | [5 empty] | 6500 |  |  | 1500
| VME Crate | [5 empty] | 5500 |  |  | 5500
| VME Rack | [5 empty] | 3000 |  |  | 3000
| Level 1 Trigger Links (4 per cable) | [5 empty] | 131.2594 |  |  | 60
| SLB | [8 empty] | 100
| SLB Transition | [8 empty] | 300
Cost as of Sept 01
WBS | Name | Start Date | Finish Date | Duration (d) | Work (d) | Number | Item Cost | Cost | TSHAW | Number | Cost | Changes | Final F01
2.1.1.5.1.5 | Computing in Building 189
2.1.1.8.6.9 | Travel
2.1.5.14.2 | Teststands for Developmen/Maintenance-Maryland
2.1.10.11.5 | Test BeamTRIDAS M&S
2 | Hadron Calorimeter (HCAL) | 1995-10-02 08:00 | 2006-03-15 | 2609 | 720853.06 |  |  | 46913794.44
2.1 | Barrel Hadron Calorimeter (HB) | 1995-10-02 08:00 | 2006-03-15 | 2311 | 327458.2 |  |  | 24422100.86
2.1.7 | Trigger/DAQ Electronics | 1997-07-01 08:00 | 2004-09-29 17:00 | 1816 | 2584 |  |  | 1924411.95 | 0.078798 |  | 2148867.97 | 224456.02
2.1.7.1 | HCAL Trigger Readout (HTR) Module | 1997-07-01 08:00 | 2003-06-23 17:00 | 1496 | 389 |  |  | 710104 |  | 65 | 675244 | -34860
2.1.7.1.1.1 | HTR Module Requirements Report | 1997-07-01 08:00 | 1997-07-14 17:00 | 10 | 5 |  |  | 2114
| engineer - fermilab-FY97 | 1997-07-01 08:00 | 1997-07-14 17:00 |  | 5 |  | 422.8 | 2114 |  |  |  |  | 0
2.1.7.1.1.2 | HTR Module Specification Report | 1999-08-09 08:00 | 1999-09-03 17:00 | 20 | 10 |  |  | 4800 | 4800 |  | 4800 | 0 | 4800
| engineer3 - maryland | 1999-08-09 08:00 | 1999-09-03 17:00 |  | 10 |  | 480 | 4800 |  |  | 4800 | 0
2.1.7.1.1.3 | HTR Demonstrator Module (6U, N=8ch) | 2000-04-03 08:00 | 2000-08-18 17:00 | 100 | 90 |  |  | 55584 | 55584 |  | 55584 | 0
2.1.7.1.1.3.1 | HTR Demonstrator Module Design & Testing | 2000-04-03 08:00 | 2000-08-18 17:00 | 100 | 90 |  |  | 40584 | 40584 |  | 40584 |  | 40584
| engineer3 - maryland | 2000-04-03 08:00 | 2000-08-18 17:00 |  | 80 |  | 480 | 38400
| Layout |  |  |  | 10
| Design |  |  |  | 30
| Evaluation |  |  |  | 40
| technician - maryland - FY00 | 2000-04-03 08:00 | 2000-08-18 17:00 |  | 10 |  | 218.4 | 2184
2.1.7.1.1.3.2 | HTR Demonstrator Module M&S | 2000-04-03 08:00 | 2000-06-23 17:00 | 60 |  |  |  | 15000 | 15000 |  | 15000 |  | 15000
| UMD (3), UIC (1), BU (1) |  |  |  |  | 5 | [5 empty] | 0
| Parts (dominated by large FPGA) | [5 empty] | 2000 |  |  |  |  | 0
| Fab and Assembly (small quantity) | [5 empty] | 1000 |  |  |  |  | 0
| Total | [5 empty] | 3000 |  |  |  |  | 0
2.1.7.1.1.4 | HTR Prototype Module (9U, N=32ch) | 2001-01-10 08:00 | 2001-10-16 17:00 | 200 | 170 |  |  | 84520 | 84520 |  | 98520 | 14000
2.1.7.1.1.4.1 | HTR Prototype Module Design & Testing | 2001-01-10 08:00 | 2001-10-16 17:00 | 200 | 170 |  |  | 68520 | 68520 |  | 68520 |  | 68520
| engineer3 - maryland | 2001-01-10 08:00 | 2001-10-16 17:00 |  | 120 |  | 480 | 57600
| Layout |  |  |  | 10
| Design |  |  |  | 20
| FPGA programming |  |  |  | 90
| technician - maryland - FY00 | 2001-01-10 08:00 | 2001-10-16 17:00 |  | 50 |  | 218.4 | 10920
| Support for prototype |  |  |  | 40
| Support for integration |  |  |  | 10
2.1.7.1.1.4.2 | HTR Prototype Module M&S | 2001-01-10 08:00 | 2001-04-03 17:00 | 60 |  | 4 |  | 16000 | 16000 |  | 30000 | 14000 | 30000
| Parts | 2001-01-10 08:00 | 2001-04-03 17:00 |  |  |  | 2000
| Fab and Assembly (small quantity) and Testing | [5 empty] | 2000 |  |  |  |  | 0
| Total | [5 empty] | 4000 |  |  |  |  | 0
2.1.7.1.1.5 | HTR 2nd Prototype Module (9U, N=32ch) | 2002-02-01 08:00 | 2002-07-18 17:00 | 120 | 114 |  |  | 47024 | 47024 |  | 70000 | 22976
2.1.7.1.1.5.1 | 2nd HTR Prototype Module Design & Testing | 2002-02-01 08:00 | 2002-07-18 17:00 | 120 | 114 |  |  | 39504 | 39504 |  | 50000 |  | 50011.29
| engineer3 - maryland | 2002-02-01 08:00 | 2002-07-18 17:00 |  | 55 |  | 480 | 26400 | 26400
| Update design |  |  |  | 10
| Update layout |  |  |  | 5
| FPGA programming |  |  |  | 40
| technician - maryland - FY00 | 2002-02-01 08:00 | 2002-07-18 17:00 |  | 60 |  | 218.4 | 13104 | 13104
2.1.7.1.1.5.2 | 2nd HTR Prototype Module M&S | 2002-02-01 08:00 | 2002-07-18 17:00 | 120 |  | 2 |  | 8000 | 8000 |  | 20000 | 12000 | 20000
| Parts | 2001-01-10 08:00 | 2001-04-03 17:00 |  |  |  | 2000
| Fab and Assembly (small quantity) and Testing | [5 empty] | 2000
| Total | [5 empty] | 4000
2.1.7.1.1.6 | HTR Production Module (9U, N=32ch) | 2002-09-02 08:00 | 2003-06-23 17:00 | 200 |  |  |  | 478912 | 350392 | 65 | 446340 | -32572
2.1.7.1.1.6.1 | HTR Production Module M&S (10% Spares) | 2002-09-02 08:00 | 2003-06-23 17:00 | 200 |  | 172 | 2500 | 430000 | 264330 | 65 | 333190 |  | 333190 | 288360
| FPGA (4 per card | [5 empty] | 1000
| PC Board | [5 empty] | 200
| Fab & Assy | [5 empty] | 200
| Rx chips (16 @ $30 + Vitesse + LVDS) | [5 empty] | 500
| Connectors | [5 empty] | 200
| Misc (FIFOs, MUX, VME, etc) | [5 empty] | 400
| Total | [5 empty] | 2500
2.1.7.1.1.6.2 | HTR Production Module Engineering Support | 2002-09-02 08:00 | 2003-02-03 17:00 | 100 | 200 |  |  | 48912 | 48912 |  | 110000 |  | 110000
| engineer3 - maryland | 2002-09-02 08:00 | 2003-02-03 17:00 |  | 20 |  | 480 | 9600
| Checkout and rework |  |  |  | 20
| technician - maryland | 2002-09-02 08:00 | 2003-02-03 17:00 |  | 180 |  | 218.4 | 39312
| Run checkout assembly line |  |  |  | 180
2.1.7.1.1.6.3 | Ship HTR Production Module to CERN | 2003-02-04 08:00 | 2003-02-17 17:00 | 10 |  |  |  |  | 3150 |  | 3150 |  | 3150
| Removed from WBS? | 2003-02-04 08:00 | 2003-02-17 17:00 |  | 210
2.1.7.1.1.6.4 | Spare Parts | 2002-09-02 08:00 | 2002-09-27 17:00 | 20 | 340 |  |  |  | 34000 |  | 0 |  | 0
| Removed from WBS | 2002-09-02 08:00 | 2002-09-27 17:00 |  | 340
2.1.7.3 | Data Concentrator Card (DCC) Module | 1997-07-01 08:00 | 2002-12-13 17:00 | 1371 | 450 |  |  | 308675.2 |  | 12 | 351192 | 42516.8
2.1.7.3.1 | DCC Requirements Report | 1997-07-01 08:00 | 1997-07-14 17:00 | 10 | 10 |  |  | 4228
| engineer - fermilab-FY97 | 1997-07-01 08:00 | 1997-07-14 17:00 |  | 10 |  | 422.8 | 4228
2.1.7.3.2 | DCC Specification Report | 1999-08-09 08:00 | 1999-09-03 17:00 | 20 | 10 |  |  | 4228 | 4228 |  | 4228 | 0
| engineer - boston - FY97 | 1999-08-09 08:00 | 1999-09-03 17:00 |  | 10 |  | 422.8 | 4228
2.1.7.3.3 | DCC Demonstrator Module | 1999-10-01 08:00 | 2000-06-15 17:00 | 175 | 210 |  |  | 94480 | 113480 |  | 113480 | 19000 | 113480
2.1.7.3.3.1 | DCC Demonstrator Module Design & Testing | 1999-10-01 08:00 | 2000-06-15 17:00 | 175 | 210 |  |  | 74480 | 74480 |  | 74480 |  | 74480 | 56412
| engineer - boston - FY00 | 1999-10-01 08:00 | 2000-06-15 17:00 |  | 140 |  | 422.8 | 59192
| VME motherboard |  |  |  | 70
| Detailed spec |  |  |  | 10
| Logic design |  |  |  | 40
| Layout notes/supervision |  |  |  | 5
| Testing |  |  |  | 15
| PMC Logic Board |  |  |  | 70
| Detailed spec |  |  |  | 10
| Logic design |  |  |  | 45
| Layout notes/supervision |  |  |  | 5
| Testing |  |  |  | 10
| technician - Boston - FY00 | 1999-10-01 08:00 | 2000-06-15 17:00 |  | 70 |  | 218.4 | 15288
| VME motherboard |  |  |  | 30
| PCB Layout |  |  |  | 15
| Technical Support |  |  |  | 15
| PMC Logic Board |  |  |  | 40
| PCB Layout |  |  |  | 20
| Technical Support |  |  |  | 20
2.1.7.3.3.2 | DCC Demonstrator Module M&S | 1999-10-01 08:00 | 2000-01-06 17:00 | 60 |  |  |  | 20000 | 39000 |  | 39000 |  | 39000
| Demonstrator boards |  |  |  | 3 |  | 18000
| Motherboard | [5 empty] | 2000
| PC-MIPS card | [5 empty] | 2000
| PMC Logic Board | [5 empty] | 2000
| Total | 1999-10-01 08:00 | 2000-01-06 17:00 |  |  |  | 6000
| Fab and Assembly | [5 empty] | 2000
2.1.7.3.4 | DCC Prototype Module (9U, N=18ch) | 2001-01-10 08:00 | 2001-10-16 17:00 | 200 | 100 |  |  | 52060 | 52060 |  | 73200 | 21140 | 73200
2.1.7.3.4.1 | DCC Prototype Module Design & Testing | 2001-01-10 08:00 | 2001-10-16 17:00 | 200 | 100 |  |  | 32060 | 32060 |  | 53200 |  | 53200
| engineer - boston | 2001-01-10 08:00 | 2001-10-16 17:00 |  | 50 |  | 422.8 | 21140 | 21140 |  | 42280
| Motherboard |  |  |  | 15
| Logic design |  |  |  | 5
| Layout notes/supervision |  |  |  | 5
| Testing |  |  |  | 5
| PMC Logic Board |  |  |  | 35
| Expansion of PC-MIPS to full capacity |  |  |  | 5
| Layout notes/supervision |  |  |  | 5
| DAQ/Trig path |  |  |  | 10
| Design verification |  |  |  | 5
| Testing |  |  |  | 10
| technician - Boston - FY00 | 2001-01-10 08:00 | 2001-10-16 17:00 |  | 50 |  | 218.4 | 10920 | 10920 |  | 10920
| VME motherboard |  |  |  | 25
| PCB Layout |  |  |  | 5
| Technical Support |  |  |  | 20
| PMC Logic Board |  |  |  | 25
| PCB Layout |  |  |  | 5
| Technical Support |  |  |  | 20
2.1.7.3.4.2 | DCC Prototype Module M&S | 2001-01-10 08:00 | 2001-04-03 17:00 | 60 |  |  |  | 20000 | 20000 |  | 20000 |  | 20000
| same M&S as for Demonstrator | 2001-01-10 08:00 | 2001-04-03 17:00 |  |  |  |  | 20000
2.1.7.3.5 | DCC 2nd Prototype Module (9U, N=18ch) | 2002-02-01 08:00 | 2002-07-18 17:00 | 120 | 80 |  |  | 49736 | 49299 |  | 75104 | 25368 | 74667.2
2.1.7.3.5.1 | DCC Prototype Module Design & Testing | 2002-02-01 08:00 | 2002-07-18 17:00 | 120 | 80 |  |  | 29736 | 29299 |  | 55104 |  | 54667.2
| engineer - boston - FY00 | 2002-02-01 08:00 | 2002-07-18 17:00 |  | 60 |  | 422.8 | 25368 |  |  | 50736
| Motherboard |  |  |  | 15
| Logic design |  |  |  | 5
| Layout notes/supervision |  |  |  | 5
| Testing |  |  |  | 5
| PMC Logic Board |  |  |  | 25
| Layout notes/supervision |  |  |  | 5
| Design verification |  |  |  | 10
| Testing |  |  |  | 10
| Testing at CERN |  |  |  | 20
| technician - Boston - FY00 | 2002-02-01 08:00 | 2002-07-18 17:00 |  | 20 |  | 218.4 | 4368 |  |  | 4368
2.1.7.3.5.2 | DCC Prototype Module M&S | 2002-02-01 08:00 | 2002-05-23 17:00 | 80 |  |  |  | 20000 | 20000 |  | 20000 |  | 20000
| same M&S as for Demonstrator | 2002-02-01 08:00 | 2002-05-23 17:00 |  |  |  |  | 20000
2.1.7.3.6 | DCC Module Production | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 | 40 |  |  | 104380 | 55780 | 12 | 85180 | -19200 | 85180
2.1.7.3.6.1 | DCC Module M&S (10% Spares) | 2002-09-02 08:00 | 2002-11-22 17:00 | 60 |  | 12 | 7800 | 93600 | 45000 | 12 | 74400 |  | 74400
| Motherboard | 2002-09-02 08:00 | 2002-11-22 17:00 |  |  |  | 2300 | 93600
| PC-MIPS cards (6 per board) | [5 empty] | 3100
| PMC Logic Board | [5 empty] | 2400
| Total | [5 empty] | 7800
2.1.7.3.6.2 | DCC Production Module Engineering Support | 2002-10-04 08:00 | 2002-11-14 17:00 | 30 | 40 |  |  | 10780 | 10780 |  | 10780 |  | 10780
| engineer - boston - FY00 | 2002-10-04 08:00 | 2002-11-14 11:17 |  | 10 |  | 422.8 | 4228
| Checkout and rework |  |  |  | 10
| technician - Boston - FY00 | 2002-10-04 08:00 | 2002-11-14 17:00 |  | 30 |  | 218.4 | 6552
| Checkout |  |  |  | 30
2.1.7.3.6.4 | Spare Parts | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 | 0 |  |  | 0
Removed from WBS
2.1.7.4 | VME Crates | 2002-09-02 08:00 | 2003-02-17 17:00 | 110 | 40 |  |  | 61984 | 28984 | 5 | 34484 | -27500 | 34484
2.1.7.4.1 | VME Subrack M&S | 2002-09-02 08:00 | 2002-11-22 17:00 | 60 |  |  |  | 55000 | 22000 | 5 | 27500 |  | 27500
| VME Subracks Acquisition | 2002-09-02 08:00 | 2002-11-22 17:00 |  |  |  |  | 55000 | 22000 |  | 27500
| 9U VIPA crate with J1, J2, and power |  |  |  |  | 10 | 5500 | 55000 |  | 5 | 27500
2.1.7.4.2 | VME Crates Engineering Support | 2002-11-25 08:00 | 2003-02-03 17:00 | 40 | 20 |  |  | 6984 | 6984 |  | 6984 |  | 6984
| engineer3 - maryland | 2002-11-25 08:00 | 2003-02-03 17:00 |  | 10 |  | 480 | 4800 |  |  |  | -4800
| Specification (interlocking, current, voltages, etc.) | [10 empty] | 0
| technician - maryland - FY00 | 2002-11-25 08:00 | 2003-02-03 17:00 |  | 10 |  | 218.4 | 2184 |  |  |  | -2184
| support | [10 empty] | 0
2.1.7.4.3 | Ship VME Crates to CERN (Zero Cost-Purchase in Europe) | 2003-02-04 08:00 | 2003-02-17 17:00 | 10 | 0 |  |  | 0
2.1.7.5 | VME Relay Racks | 2002-09-02 08:00 | 2003-03-03 17:00 | 120 | 5 |  |  | 14400 | 8400 | 2 | 8400 | -6000 | 8400
2.1.7.5.1 | VME Relay Racks M&S (no Spares) | 2002-09-02 08:00 | 2003-02-03 17:00 | 100 |  |  |  | 12000 | 6000 | 2 | 6000 | -6000 | 6000
| Rack, monitoring, cooling, etc. | 2002-09-02 08:00 | 2003-02-03 17:00 |  |  | 4 | 3000 | 12000 |  | 2 | 6000
2.1.7.5.2 | VME Relay Racks Engineering Support | 2003-02-04 08:00 | 2003-02-17 17:00 | 10 | 5 |  |  | 2400 | 2400 |  | 2400 | 0 | 2400
| engineer3 - maryland | 2003-02-04 08:00 | 2003-02-17 17:00 |  | 5 |  | 480 | 2400 |  |  |  | -2400
| Specification (interlocking, current, voltages, etc.) | [10 empty] | 0
2.1.7.5.3 | Ship VME Relay Racks to CERN (Zero Cost-Purchase in Europe) | 2003-02-18 08:00 | 2003-03-03 17:00 | 10 | 0 |  |  | 0
2.1.7.6 | Level 1 Trigger Links | 2003-06-02 08:00 | 2003-08-15 17:00 | 55 | 25 |  |  | 46460.8525 | 25251 | 288 | 24048 | -22412.8525 | 24048
2.1.7.6.1 | Level 1 Trigger Links M&S (5% Spares) | 2003-06-02 08:00 | 2003-07-04 17:00 | 25 |  | 302.4 | 131.2594 | 39692.8525 | 18483 | 288 | 17280 | -22412.8525 | 17280
| Belden 9182 PVC (cost per 1000 ft) |  |  |  |  | 1000 | 472.11
| Cost for 20m cable |  |  |  |  | 1 | 30.9799
| D-sub metal backshells |  |  |  |  | 1 | 2.61
| Connector |  |  |  |  | 1 | 1.06
| Total cost per connector: |  |  |  |  | 1 | 3.67
| Total cost per cable quad cable with connector |  |  |  |  | 4 | 131.2594
| Number of L1 trigger channels |  |  |  |  | 2304
| Number of cables (2 channels per cable, 5% spares) |  |  |  |  | 302.4
2.1.7.6.2 | Level 1 Trigger Links Engineering Support | 2003-07-07 08:00 | 2003-08-01 17:00 | 20 | 25 |  |  | 6768 | 6768 |  | 6768 |  | 6768
| technician - maryland - FY00 | 2003-07-07 08:00 | 2003-08-01 17:00 |  | 20 |  | 218.4 | 4368
Support for cable making
| engineer3 - maryland | 2003-07-07 08:00 | 2003-08-01 17:00 |  | 5 |  | 480 | 2400
Specs and verification on cabling scheme
2.1.7.6.3 | Ship Level 1 Trigger Links to CERN | 2003-08-04 08:00 | 2003-08-15 17:00 | 10 | 0 |  |  | 0
2.1.7.7 | DCC Input Link | 2003-06-02 08:00 | 2003-07-11 17:00 | 30 | 0 |  |  | 0
2.1.7.7.1 | DCC Input Link M&S | 2003-06-02 08:00 | 2003-06-27 17:00 | 20 |  |  |  | 0
| Obsolete WBS item | 2003-06-02 08:00 | 2003-06-27 17:00 |  | 3020 |  |  | 0
2.1.7.7.2 | Ship DCC Input Link to CERN | 2003-06-30 08:00 | 2003-07-11 17:00 | 10 | 0 |  |  | 0
2.1.7.9 | VME Pipeline Module | 2002-12-02 08:00 | 2003-05-05 17:00 | 100 | 25 |  |  | 12000 | 12000 |  | 12000 | 0
2.1.7.9.1 | VME Pipeline Module Integration | 2002-12-02 08:00 | 2003-05-05 17:00 | 100 | 25 |  |  | 12000 | 12000 |  | 12000 |  | 12000
| engineer3 - maryland | 2002-12-02 08:00 | 2003-05-05 17:00 |  | 25 |  | 480 | 12000
| integrage using HTR production modules |  |  |  | 25
2.1.7.9.2 | VME Pipeline Module M&S | 2002-12-02 08:00 | 2003-01-13 17:00 | 20 |  |  |  | 0
| Use HTR and DCC production modules | 2002-12-02 08:00 | 2003-01-13 17:00 |  |  |  |  | 0
2.1.7.9.3 | Ship VME Pipeline Module to CERN | 2003-01-14 08:00 | 2003-01-27 17:00 | 10 | 0 |  |  | 0
2.1.7.10 | HCAL Readout Control (HRC) Module | 1997-07-01 08:00 | 2003-02-03 17:00 | 1396 | 280 |  |  | 260012.97 |  | 6 | 187784.97 | -72228
2.1.7.10.1 | HRC Requirements Report | 1997-07-01 08:00 | 1997-07-14 17:00 | 10 | 10 |  |  | 4228 |  |  | 4228 |  | 0
| engineer - fermilab-FY97 | 1997-07-01 08:00 | 1997-07-14 17:00 |  | 10 |  | 422.8 | 4228 |  |  | 4228
2.1.7.10.2 | HRC Specification Report | 1999-08-09 08:00 | 1999-09-03 17:00 | 20 | 20 |  |  | 4368 | 4368 |  | 4368 |  | 4368
| technician2 - uic - FY97 | 1999-08-09 08:00 | 1999-09-03 17:00 |  | 20 |  | 218.4 | 4368 |  |  | 4368
2.1.7.10.3 | HRC Demonstrator Module (6U VME) | 2000-04-03 08:00 | 2000-08-18 17:00 | 100 | 50 |  |  | 46240 | 46240 |  | 46240
2.1.7.10.3.1 | HRC Demonstrator Module Design & Testing | 2000-04-03 08:00 | 2000-08-18 17:00 | 100 | 50 |  | 422.8 | 21140 |  |  | 21140 |  | 21140
| engineer - uic | 2000-04-03 08:00 | 2000-08-18 17:00 |  | 50 |  |  | 21140 |  |  | 21140
| TTC Fanout |  |  |  | 20 | [5 empty] | 0
| Detailed Spec and Logic Design |  |  |  | 10 | [5 empty] | 0
| Layout notes/supervision |  |  |  | 5 | [5 empty] | 0
| Testing |  |  |  | 5 | [5 empty] | 0
| In-crate DAQ |  |  |  | 30 | [5 empty] | 0
| Detailed Spec |  |  |  | 10 | [5 empty] | 0
| Software |  |  |  | 10 | [5 empty] | 0
| Testing/Debugging |  |  |  | 10 | [5 empty] | 0
2.1.7.10.3.2 | HRC Demonstrator Module M&S | 2000-04-03 08:00 | 2000-06-23 17:00 | 60 |  |  |  | 25100 |  |  | 25100 |  | 25100
| TTC Fanout board | 2000-04-03 08:00 | 2000-06-23 17:00 |  |  | 5 |  | 7500 |  |  | 7500
| PC Board and electrical test | [5 empty] | 500 |  |  |  | 0
| FPGA | [5 empty] | 300 |  |  |  | 0
| Fab and Assembly | [5 empty] | 400 |  |  |  | 0
| Misc (FIFOs, MUX, VME, etc) | [5 empty] | 300 |  |  |  | 0
| Total | [5 empty] | 1500 |  |  |  | 0
| CPU board |  |  |  |  | 3 |  | 12600 |  |  | 12600
| Motherboard | [5 empty] | 2000 |  |  |  | 0
| CPU board | [5 empty] | 2200 |  |  |  | 0
| Total | [5 empty] | 4200 |  |  |  | 0
| VxWorks licence for UIC |  |  |  |  | 1 |  | 5000 |  |  | 5000
2.1.7.10.4 | HRC Prototype Module (9U VME) | 2001-01-10 08:00 | 2001-08-21 17:00 | 160 | 60 |  |  | 60248.97 | 60248.97 |  | 60248.97
2.1.7.10.4.1 | HRC Prototype Module Design & Testing | 2001-01-10 08:00 | 2001-08-21 17:00 | 160 | 60 |  |  | 29736 |  |  | 29736 |  | 30248.98
| post doc-illinois-Rob Martin | 2001-01-10 08:00 | 2001-08-21 17:00 |  | 80 |  |  | 0 |  |  | 0
| engineer - uic | 2001-01-10 08:00 | 2001-08-21 17:00 |  | 60 |  | 422.8 | 25368 |  |  | 25368
| 9U Main HRC board |  |  |  | 40 | [5 empty] | 0
| Detailed spec |  |  |  | 5 | [5 empty] | 0
| TTC fanout circuit design |  |  |  | 10 | [5 empty] | 0
| Motherboard design |  |  |  | 10 | [5 empty] | 0
| Layout notes/supervision |  |  |  | 5 | [5 empty] | 0
| Testing |  |  |  | 10 | [5 empty] | 0
| FMU PMC card |  |  |  | 20 | [5 empty] | 0
| Detailed spec |  |  |  | 5 | [5 empty] | 0
| I/O and logic design |  |  |  | 5 | [5 empty] | 0
| Layout notes/supervision |  |  |  | 5 | [5 empty] | 0
| Testing |  |  |  | 5 | [5 empty] | 0
| technician2 - uic | 2001-01-10 08:00 | 2001-08-21 17:00 |  | 20 |  | 218.4 | 4368 |  |  | 4368
| Support |  |  |  | 20 | [5 empty] | 0
2.1.7.10.4.2 | HRC Prototype Module M&S | 2001-01-10 08:00 | 2001-02-26 10:40 | 33.33 |  |  |  | 30000 |  |  | 30000 |  | 30000
| Motherboard |  |  |  | 5 |  | 2500 | 12500 |  |  | 12500
| CPU board | 2001-01-10 08:00 | 2001-02-26 10:40 |  | 3 |  | 2500 | 7500 |  |  | 7500
| FMU PMC card |  |  |  | 5 |  | 2000 | 10000 |  |  | 10000
2.1.7.10.5 | HRC 2nd Prototype Module (9U VME) | 2002-03-01 08:00 | 2002-08-15 17:00 | 120 | 40 |  |  | 42280 | 42280 |  | 42280
2.1.7.10.5.1 | HRC Prototype Module Design & Testing | 2002-03-01 08:00 | 2002-08-15 17:00 | 80 | 40 |  |  | 21280 |  |  | 21280 |  | 21280
| post doc-illinois-Rob Martin | 2002-03-01 08:00 | 2002-08-15 17:00 |  | 40 |  |  | 0 |  |  | 0
| engineer - uic | 2002-03-01 08:00 | 2002-08-15 17:00 |  | 40 |  | 422.8 | 16912 |  |  | 16912
| 9U Main HRC board |  |  |  | 20 | [5 empty] | 0
| TTC fanout circuit design |  |  |  | 5 | [5 empty] | 0
| Motherboard design |  |  |  | 5 | [5 empty] | 0
| Layout notes/supervision |  |  |  | 5 | [5 empty] | 0
| Testing |  |  |  | 5 | [5 empty] | 0
| FMU PMC card |  |  |  | 20 | [5 empty] | 0
| I/O and logic design |  |  |  | 5 | [5 empty] | 0
| Layout notes/supervision |  |  |  | 5 | [5 empty] | 0
| Testing |  |  |  | 10 | [5 empty] | 0
| technician2 - uic - FY00 | 2002-03-01 08:00 | 2002-06-20 17:00 |  | 20 |  | 218.4 | 4368 |  |  | 4368
| Support |  |  |  | 20 | [5 empty] | 0
2.1.7.10.5.2 | HRC Prototype Module M&S | 2002-03-01 08:00 | 2002-04-11 17:00 | 30 |  |  |  | 21000 |  |  | 21000 |  | 21000
| Motherboard |  |  |  | 3 |  | 2500 | 7500 |  |  | 7500
| CPU board | 2001-01-10 08:00 | 2001-02-26 10:40 |  | 3 |  | 2500 | 7500 |  |  | 7500
| FMU PMC card |  |  |  | 3 |  | 2000 | 6000 |  |  | 6000
2.1.7.10.6 | HRC Module Production | 2002-09-02 08:00 | 2003-02-03 17:00 | 100 | 100 |  |  | 103648 | 50648 | 6 | 34648
2.1.7.10.6.1 | HRC Production Module M&S (10% Spares) | 2002-09-02 08:00 | 2002-11-08 17:00 | 50 |  | 12 | 6500 | 78000 | 25000 | 6 | 9000 |  | 9000
| Motherboard | [5 empty] | 2000 |  |  |  | 0
| CPU board | 2001-01-10 08:00 | 2001-02-26 10:40 |  |  |  | 2500 |  |  |  | 0
| FMU PMC card | [5 empty] | 2000 |  |  |  | 0
| Total | 2002-09-02 08:00 | 2002-11-08 17:00 |  |  |  | 6500 |  |  |  | 0
2.1.7.10.6.2 | HRC Production Module Engineering Support | 2002-11-11 08:00 | 2003-01-20 17:00 | 40 | 100 |  |  | 25648 | 25648 |  | 25648 |  | 25648
| post doc-illinois-Rob Martin | 2002-11-11 08:00 | 2003-01-20 17:00 |  | 20 |  |  | 0 |  |  | 0
| engineer - uic | 2002-11-11 08:00 | 2003-01-20 17:00 |  | 40 |  | 422.8 | 16912 |  |  | 16912
| Checkout and rework |  |  |  | 40 | [5 empty] | 0
| technician2 - uic | 2002-11-11 08:00 | 2003-01-20 17:00 |  | 40 |  | 218.4 | 8736 |  |  | 8736
| Checkout | [9 empty] | 0
2.1.7.10.6.3 | Ship HRC Production Module to CERN | 2003-01-21 08:00 | 2003-02-03 17:00 | 10 | 0 |  |  | 0 |  |  | 0
2.1.7.10.6.4 | Spare Parts | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 | 0 |  |  | 0 |  |  | 0
2.1.7.11 | Tester Stations | 1999-10-01 08:00 | 2000-11-09 17:00 | 280 | 400 |  |  | 192020 |  |  | 206939 | 14919
2.1.7.11.1 | Universal Tester Module | 1999-10-01 08:00 | 2000-11-09 17:00 | 280 | 130 |  |  | 72278.6287 | 72784 |  | 72784 |  | 72784
2.1.7.11.1.1 | Universal Tester Module Design & Testing | 1999-10-01 08:00 | 2000-07-20 17:00 | 200 | 130 |  |  | 59784 | 59784 |  | 59784 |  | 59784
| engineer3 - maryland | 1999-10-01 08:00 | 2000-07-20 17:00 |  | 120 |  | 480 | 57600 |  |  | 0
| Parts Evaluation |  |  |  | 40 | [5 empty] | 0
| Layout |  |  |  | 10 | [5 empty] | 0
| Design |  |  |  | 20 | [5 empty] | 0
| Testing |  |  |  | 50 | [5 empty] | 0
| technician - maryland - FY00 | 1999-10-01 08:00 | 2000-07-20 17:00 |  | 10 |  | 218.4 | 2184 |  |  | 0
2.1.7.11.1.2 | Universal Tester Module M&S | 2000-07-21 08:00 | 2000-08-17 17:00 | 20 |  |  |  | 4000 | 4000 |  | 4000 |  | 4000
| 1 board, maybe 6U or handheld | 2000-07-21 08:00 | 2000-08-17 17:00 |  |  | 1 |  |  |  |  | 0
| Parts (all I/O plus FPGA for control and VME) | [5 empty] | 2000 |  |  |  | 0
| Fab and Assembly (small quantity) | [5 empty] | 2000 |  |  |  | 0
| Total | [5 empty] | 4000 |  |  |  | 0
2.1.7.11.1.5 | TTC and LHC Emulator Setup | 2000-10-13 08:00 | 2000-11-09 17:00 | 20 |  |  |  | 8494.6287 | 9000 |  | 9000 |  | 9000
| TTC-VI (VME interface module) | [5 empty] | 1497.006 |  |  |  | 0
| TTC-VX (electro-optical converter) | [5 empty] | 538.9222 |  |  |  | 0
| TTC-RX | [5 empty] | 149.7006 |  |  |  | 0
| 6U VME crate w/750W power supply | 2000-10-13 08:00 | 2000-11-09 17:00 |  |  |  | 3809 |  |  |  | 0
| LHC emulator | [5 empty] | 0 |  |  |  | 0
| PC | [5 empty] | 2500 |  |  |  | 0
| Total | [5 empty] | 8494.6287 |  |  |  | 0
2.1.7.11.2 | Front-End Electronic (FEE) Emulator | 1999-10-01 08:00 | 2000-10-12 17:00 | 260 | 110 |  |  | 62684 | 62684 |  | 62684 |  | 62684
2.1.7.11.2.1 | FEE Emulator Design & Testing | 1999-10-01 08:00 | 2000-07-20 17:00 | 200 | 110 |  |  | 50184 | 50184 |  | 50184 |  | 50184
| engineer3 - maryland | 1999-10-01 08:00 | 2000-07-20 17:00 |  | 100 |  | 480 | 48000 |  |  | 48000
| Layout |  |  |  | 10 | [5 empty] | 0
| Parts Evaluation |  |  |  | 20 | [5 empty] | 0
| Design |  |  |  | 20 | [5 empty] | 0
| Testing |  |  |  | 50 | [5 empty] | 0
| technician - maryland - FY00 | 1999-10-01 08:00 | 2000-07-20 17:00 |  | 10 |  | 218.4 | 2184 |  |  | 2184
2.1.7.11.2.2 | FEE Emulator M&S | 2000-07-21 08:00 | 2000-08-17 17:00 | 20 |  |  |  | 12500 | 12500 |  | 12500 |  | 12500
| UMD (3), UIC (1), BU (1) | 2000-07-21 08:00 | 2000-08-17 17:00 |  |  | 5
| Connectors | [5 empty] | 600 |  |  |  | 0
| $150 each for 4 SC optical connectors plus chips | [9 empty] | 0
| FPGA | [5 empty] | 500 |  |  |  | 0
| FIFOs | [5 empty] | 200 |  |  |  | 0
| PC board | [5 empty] | 500 |  |  |  | 0
| Fab and Assembly (small quantity) and Testing | [5 empty] | 400 |  |  |  | 0
| Misc | [5 empty] | 300 |  |  |  | 0
| Total | [5 empty] | 2500 |  |  |  | 0
2.1.7.11.3 | DCC Module Test Equipment | 2000-01-06 08:00 | 2000-09-07 17:00 | 176 | 40 |  |  | 25406.6287 | 47831 |  | 47831 |  | 47831
2.1.7.11.3.1 | DCC Module Test Equipment | 2000-06-16 08:00 | 2000-09-07 17:00 | 60 |  |  |  | 8494.6287 | 25000 |  | 25000 |  | 25000
| 6U VME crate and TTC setup (see above) | 2000-06-16 08:00 | 2000-09-07 17:00 |  |  |  |  | 8494.6287 |  |  | 0
2.1.7.11.3.2 | DCC Module Software Development | 2000-01-06 08:00 | 2000-08-16 17:00 | 160 | 40 |  |  | 16912 | 22831 |  | 22831 |  | 22831
| engineer - boston | 2000-01-06 08:00 | 2000-08-16 17:00 |  | 40 |  | 422.8 | 16912 |  |  | 16912
| Mostly FPGA coding, VME interface, DAQ, etc |  |  |  | 40 | [5 empty] | 0
2.1.7.11.4 | HRC Demo Tester | 1999-10-01 08:00 | 2000-05-25 17:00 | 160 | 120 |  |  | 23640 | 23640 |  | 23640 |  | 23640
2.1.7.11.4.1 | HRC Demo Tester Design & Testing | 1999-10-01 08:00 | 2000-03-02 17:00 | 100 | 50 |  | 422.8 | 21140 | 21140 |  | 21140 |  | 21140
| engineer - uic | 1999-10-01 08:00 | 2000-03-02 17:00 |  | 50 |  |  | 21140 |  |  | 21140
| TTC and LHC Emulator Setup |  |  |  | 40 | [5 empty] | 0
| TTC fanout |  |  |  | 10 | [5 empty] | 0
2.1.7.11.4.2 | HRC Demo Tester M&S | 2000-03-03 08:00 | 2000-03-30 17:00 | 20 | 20 |  |  | 2500 | 2500 |  | 2500 |  | 2500
| FEE Emulator | 2000-03-03 08:00 | 2000-03-30 17:00 |  | 20 |  |  | 2500 |  |  | 2500
2.1.7.11.4.3 | HRC Demo Tester | 2000-03-31 08:00 | 2000-04-27 17:00 | 20 | 0 |  |  | 0 |  |  | 0
2.1.7.11.4.4 | FEE Emulator Evaluation | 2000-04-28 08:00 | 2000-05-25 17:00 | 20 | 0 |  |  | 0 |  |  | 0
2.1.7.12 | System Integration/Milestones | 2000-10-01 08:00 | 2004-09-29 17:00 | 999 | 605 |  |  | 140688 | 140688 |  | 140688 | 0
2.1.7.12.1 | Demontrator Integration Tests (Maryland) | 2000-10-01 08:00 | 2000-12-08 17:00 | 50 | 50 |  |  | 24000 | 24000 |  | 24000 |  | 24000
| engineer3 - maryland | 2000-10-02 08:00 | 2000-12-08 17:00 |  | 50 |  | 480 | 24000
| Integrate DCC, HTR, HRC, TTC, etc. |  |  |  | 50
2.1.7.12.2 | Demontrator Integration Tests (Boston) | 2000-10-01 08:00 | 2000-12-08 17:00 | 50 | 50 |  |  | 21140 | 21140 |  | 21140 |  | 21140
| engineer - boston - FY00 | 2000-10-02 08:00 | 2000-12-08 17:00 |  | 50 |  | 422.8 | 21140
Integrate DCC, HTR, HRC, TTC, etc.
2.1.7.12.3 | Demontrator Integration Tests (UIC) | 2000-10-01 08:00 | 2000-12-08 17:00 | 50 | 50 |  |  | 21140 | 21140 |  | 21140 |  | 21140
| engineer - uic | 2000-10-02 08:00 | 2000-12-08 17:00 |  | 50 |  | 422.8 | 21140
Integrate DCC, HTR, HRC, TTC, etc.
2.1.7.12.4 | Prototype Integration Tests (Maryland) | 2001-10-01 08:00 | 2002-04-01 17:00 | 100 | 90 |  |  | 40584 | 40584 |  | 40584 |  | 40584
| engineer3 - maryland | 2001-10-01 08:00 | 2002-02-04 17:00 |  | 80 |  | 480 | 38400
| Integrate DCC, HTR, HRC, TTC, etc. |  |  |  | 80
| technician - maryland - FY00 | 2001-10-01 08:00 | 2002-04-01 17:00 |  | 10 |  | 218.4 | 2184
2.1.7.12.5 | Prototype Integration Tests (Boston) | 2001-10-01 08:00 | 2002-02-04 17:00 | 80 | 40 |  |  | 16912 | 16912 |  | 16912 |  | 16912
| engineer - boston - FY00 | 2001-10-01 08:00 | 2002-02-04 17:00 |  | 40 |  | 422.8 | 16912
Integrate DCC, HTR, HRC, TTC, etc.
2.1.7.12.6 | Prototype Integration Tests (UIC) | 2001-10-01 08:00 | 2002-02-04 17:00 | 80 | 40 |  |  | 16912 | 16912 |  | 16912 |  | 16912
| engineer - uic | 2001-10-01 08:00 | 2002-02-04 17:00 |  | 40 |  | 422.8 | 16912
| Integrate DCC, HTR, HRC, TTC, etc. |  |  |  | 40
2.1.7.12.7 | Installation at CERN (Maryland) | 2004-01-08 08:00 | 2004-09-29 17:00 | 190 | 95 |  |  | 0
| postdoc-maryland-Archana Sharma | 2004-01-08 08:00 | 2004-09-29 17:00 |  | 95 |  |  | 0
2.1.7.12.8 | Installation at CERN (Boston) | 2004-01-08 08:00 | 2004-09-29 17:00 | 190 | 95 |  |  | 0
| postdoc-Boston-TBN | 2004-01-08 08:00 | 2004-09-29 17:00 |  | 95 |  |  | 0
2.1.7.12.9 | Installation at CERN (UIC) | 2004-01-08 08:00 | 2004-09-29 17:00 | 190 | 95 |  |  | 0
| post doc-illinois-Rob Martin | 2004-01-08 08:00 | 2004-09-29 17:00 |  | 95 |  |  | 0
Milestones
HCAL-HB-M43 | Start Fully-Functional Prototype Design | 2001-01-10 08:00 | 2001-01-10 08:00 | 0 | 0 |  |  | 0
HCAL-HB-M44 | Start 2nd Submission of Fully-Functional Prototype Design | 2002-02-01 08:00 | 2002-02-01 08:00 | 0 | 0 |  |  | 0
HCAL-HB-M45 | Start Full Production of T/DAQ Readout Cards (24 Crates) | 2002-09-01 08:00 | 2002-09-01 08:00 | 0 | 0 |  |  | 0
HCAL-HB-M46 | Trigger/DAQ Production (HB,HO, HE, & HF) Complete | 2003-03-15 08:00 | 2003-03-15 08:00 | 0 | 0 |  |  | 0
HCAL-HB-M47 | Trigger/DAQ Installation (HB,HO, HE, & HF) Complete | 2004-02-01 08:00 | 2004-02-01 08:00 | 0 | 0 |  |  | 0
2.1.7.13 | Trigger/DAQ Coordination | 1999-10-01 08:00 | 2004-09-29 17:00 | 1250 | 310 |  |  | 148800 | 148800 |  | 343800 | 195000 | 283785.61
2.1.7.13.1 | Trigger/DAQ HCAL DAQ/Trigger Integration (Maryland) | 2000-05-01 08:00 | 2002-10-14 17:00 | 620 | 310 |  |  | 163800 | 148800 |  | 343800 |  | 283785.61
| engineer3 - maryland | 2000-05-01 08:00 | 2002-10-14 17:00 |  | 310 |  |  | 148800
| Overall integration at engineering level, 5/00 to 12/04 |  |  |  | 310 |  | 480 | 148800
| DaSilva consulting July 2000 | [6 empty] | 15000
2.1.7.13.2 | Trigger/DAQ Project Engineering (Boston) | 1999-10-01 08:00 | 2004-09-29 17:00 | 1250 |  |  |  | 0
| postdoc-Boston-TBN | 1999-10-01 08:00 | 2004-09-29 17:00 |  |  |  |  | 0
2.1.7.13.3 | Trigger/DAQ Project Engineering (Maryland) | 1999-10-01 08:00 | 2004-09-29 17:00 | 1250 |  |  |  | 0
| postdoc-maryland-Archana Sharma | 1999-10-01 08:00 | 2004-09-29 17:00 |  |  |  |  | 0
2.1.7.13.4 | Trigger/DAQ Project Engineering (UIC) | 1999-10-01 08:00 | 2004-09-29 17:00 | 1250 |  |  |  | 0
| post doc-illinois-Rob Martin | 1999-10-01 08:00 | 2004-09-29 17:00 |  | 125 |  |  | 0
2.1.7.13.5 | Trigger/DAQ Shipping Costs (Boston) | 1999-10-01 08:00 | 2004-09-29 17:00 | 1250 |  |  |  | 0
2.1.7.13.6 | Trigger/DAQ Shipping Costs (Maryland) | 1999-10-01 08:00 | 2004-09-29 17:00 | 1250 |  |  |  | 0
2.1.7.13.7 | Trigger/DAQ Shipping Costs (UIC) | 1999-10-01 08:00 | 2004-09-29 17:00 | 1250 |  |  |  | 0
2.1.7.13.8 | Trigger/DAQ Electronics Evaluation & Testing | 1999-10-01 08:00 | 2003-09-29 17:00 | 1000 |  |  |  | 0
| postdoc-maryland-Archana Sharma | 1999-10-01 08:00 | 2003-09-29 17:00 |  |  |  |  | 0
2.1.7.13.9 | Level II Trigger Simulation and Algorithm Development | 1999-10-01 08:00 | 2003-09-29 17:00 | 1000 |  |  |  | 0
| postdoc-maryland-S. Kunori | 1999-10-01 08:00 | 2003-09-29 17:00 |  |  |  |  | 0
| physicist-maryland-S. Eno | 1999-10-01 08:00 | 2003-09-29 17:00 |  |  |  |  | 0
2.1.7.13.10 | DCC Module Software Development | 1999-10-01 08:00 | 2003-09-29 17:00 | 1000 |  |  |  | 0
| postdoc-Boston-TBN | 1999-10-01 08:00 | 2003-09-29 17:00 |  |  |  |  | 0
2.1.7.14 | HCAL DAQ Concentrator (HDC) Module | 2002-02-01 08:00 | 2002-10-14 17:00 | 182 | 55 |  |  | 29188 | 29188 |  | 29188 | 0
2.1.7.14.1 | HDC Prototype Module (9U VME) | 2002-03-01 08:00 | 2002-05-23 17:00 | 60 | 20 |  |  | 10640 | 10640 |  | 10640 |  | 10640
2.1.7.14.1.1 | HDC Prototype Module Design & Testing | 2002-03-01 08:00 | 2002-04-25 17:00 | 40 | 20 |  |  | 10640
| post doc-illinois-Rob Martin | 2002-03-01 08:00 | 2002-04-25 17:00 |  | 20 |  |  | 0
| engineer - uic | 2002-03-01 08:00 | 2002-04-25 17:00 |  | 20 |  | 422.8 | 8456
| I/O and logic design |  |  |  | 20
| technician2 - uic - FY00 | 2002-03-01 08:00 | 2002-04-25 17:00 |  | 10 |  | 218.4 | 2184
| Support |  |  |  | 10
2.1.7.14.1.2 | HDC Prototype Module M&S | 2002-03-01 08:00 | 2002-05-23 17:00 | 60 | 0 |  |  | 0
2.1.7.14.2 | HDC 2nd Prototype Module (9U VME) | 2002-02-01 08:00 | 2002-02-28 17:00 | 20 | 0 |  |  | 0
2.1.7.14.2.1 | HDC Prototype Module Design & Testing | 2002-02-01 08:00 | 2002-02-28 17:00 | 20 | 0 |  |  | 0
2.1.7.14.2.2 | HDC Prototype Module M&S | 2002-02-01 08:00 | 2002-02-28 17:00 | 20 | 0 |  |  | 0
2.1.7.14.3 | HDC Module Production | 2002-07-02 08:00 | 2002-10-14 17:00 | 75 | 35 |  |  | 18548 | 18548 |  | 18548 |  | 18548
2.1.7.14.3.1 | HDC Production Module M&S (0 Spares) | 2002-07-02 08:00 | 2002-08-30 17:00 | 44 |  |  |  | 9000
| HDC Modules | 2002-07-02 08:00 | 2002-08-30 17:00 |  |  |  |  | 9000
| 6U, majority logic plus I/O, small quantity produced |  |  |  |  | 3 | 3000 | 9000
2.1.7.14.3.2 | HDC Production Module Engineering Support | 2002-07-08 08:00 | 2002-09-27 17:00 | 40 | 35 |  |  | 9548
| post doc-illinois-Rob Martin | 2002-07-08 08:00 | 2002-08-30 17:00 |  | 10 |  |  | 0
| engineer - uic | 2002-07-08 08:00 | 2002-09-27 17:00 |  | 20 |  | 422.8 | 8456
| Design and checkout |  |  |  | 20
| technician2 - uic | 2002-07-08 08:00 | 2002-08-30 17:00 |  | 5 |  | 218.4 | 1092
| checkout |  |  |  | 5
2.1.7.14.3.3 | Ship HDC Production Module to CERN | 2002-09-30 08:00 | 2002-10-11 17:00 | 10 | 0 |  |  | 0
2.1.7.14.3.4 | Spare Parts | 2002-07-02 08:00 | 2002-10-14 17:00 | 75 | 0 |  |  | 0
2.1.7.15 | SLB Boards | [8 empty] | 626 | 135100 | 135100
2.1.7.15.1 | SLB Trigger Link M&S (20% Spares) | [7 empty] | 52600 | 626 | 62600 |  | 62600
2.1.7.15.2 | SLB ENG | [7 empty] | 20000 |  | 20000 |  | 21840
2.1.7.15.2 | SLB Transition | [8 empty] | 175 | 52500 |  | 66000
2.2 | Outer Barrel Calorimeter (HO) | 1997-10-01 08:00 | 2005-04-30 08:00 | 1891 | 123234 |  |  | 3050838.54
2.2.7 | Trigger/DAQ Electronics | 2002-09-02 08:00 | 2005-02-24 17:00 | 615 |  |  |  | 339100 | 0.11115 |  | 394808 | 55708
2.2.7.1 | HTR Module Production | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 200000 |  | 58 | 297308 | 97308
2.2.7.1.1 | HTR Module M&S (10% Spares) | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 200000 |  | 58 | 297308 |  | 297308
| HTR Production Module M&S (10% Spares) | 2002-09-02 08:00 | 2002-12-13 17:00 |  |  | 80 | 2500 | 200000 | 254718 | 58 | 297308
2.2.7.1.2 | HTR Module Engineering Support | 2002-09-02 08:00 | 2002-09-27 17:00 | 20 |  |  |  | 0
2.2.7.1.3 | Ship HTR Modules to CERN | 2002-09-30 08:00 | 2002-10-11 17:00 | 10 |  |  |  | 0
2.2.7.1.4 | Spare Parts | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 0
2.2.7.3 | Data Concentrator Module Production | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 54600 |  | 10 | 62000 | 7400
2.2.7.3.1 | Data Concentrator M&S (10% Spares) | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 54600 | 35000 | 10 | 62000 |  | 62000
| DCC Production Module | 2002-09-02 08:00 | 2002-12-13 17:00 |  |  | 7 | 7800 | 54600
2.2.7.3.2 | Data Concentrator Module Engineering Support | 2002-09-02 08:00 | 2002-09-27 17:00 | 20 |  |  |  | 0
2.2.7.3.3 | Ship Data Concentrator Modules to CERN | 2002-09-30 08:00 | 2002-10-11 17:00 | 10 |  |  |  | 0
2.2.7.3.4 | Spare Parts | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 0
2.2.7.4 | VME Crates | 2002-09-02 08:00 | 2002-12-06 17:00 | 70 |  |  |  | 33000 |  | 4 | 22000 | -11000
2.2.7.4.1 | VME Subracks M&S | 2002-09-02 08:00 | 2002-10-25 17:00 | 40 |  |  |  | 33000 | 16500 | 4 | 22000 |  | 22000
| VME Crates | 2002-09-02 08:00 | 2002-10-25 17:00 |  |  | 6 | 5500 | 33000
2.2.7.4.2 | VME Subracks Engineering Support | 2002-10-28 08:00 | 2002-11-22 17:00 | 20 |  |  |  | 0
2.2.7.4.3 | Ship VME Subracks to CERN | 2002-11-25 08:00 | 2002-12-06 17:00 | 10 |  |  |  | 0
2.2.7.5 | VME Relay Racks M&S | 2003-02-04 08:00 | 2005-02-24 17:00 | 200 |  |  |  | 6000 | 3000 | 2 | 6000 | 0 | 6000
| Trigger/DAQ Relay Racks | 2003-02-04 08:00 | 2005-02-24 17:00 |  |  | 2 | 3000 | 6000
2.2.7.7 | DAQ Links | 2003-06-02 08:00 | 2003-07-11 17:00 | 30 |  |  |  | 0
2.2.7.7.1 | DAQ Link M&S | 2003-06-02 08:00 | 2003-06-27 17:00 | 20 |  |  |  | 0
2.2.7.7.2 | Ship DAQ Links to CERN | 2003-06-30 08:00 | 2003-07-11 17:00 | 10 |  |  |  | 0
2.2.7.8 | DCC Input Link | 2003-06-02 08:00 | 2003-07-11 17:00 | 30 |  |  |  | 0
2.2.7.8.1 | DCC Input Link M&S | 2003-06-02 08:00 | 2003-06-27 17:00 | 20 |  |  |  | 0
2.2.7.8.2 | Ship DCC Input Link to CERN | 2003-06-30 08:00 | 2003-07-11 17:00 | 10 |  |  |  | 0
2.2.7.10 | HRC Module Production | 2002-09-02 08:00 | 2003-02-10 17:00 | 105 |  |  |  | 45500 |  | 5 | 7500 | -38000
2.2.7.10.1 | HRC Production Module M&S (10% Spares) | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 45500 | 15000 | 5 | 7500 |  | 7500
| HRC Production Module | 2002-09-02 08:00 | 2002-12-13 17:00 |  |  | 7 | 6500 | 45500
2.2.7.10.2 | HRC Production Module Engineering Support | 2002-12-16 08:00 | 2003-01-27 17:00 | 20 |  |  |  | 0
2.2.7.10.3 | Ship HRC Production Module to CERN | 2003-01-28 08:00 | 2003-02-10 17:00 | 10 |  |  |  | 0
2.2.7.10.4 | Spare Parts | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 0
2.3 | Endcap Hadron Calorimeter (HE) | 1997-10-01 08:00 | 2006-03-15 17:00 | 2109 |  |  |  | 10636471.81
2.3.7 | Trigger/DAQ Electronics | 2002-09-02 08:00 | 2003-10-06 14:27 | 274.68 |  |  |  | 532145.8912 | 0.05003 |  | 446800 | -85345.8912
2.3.7.1 | HTR Module Production | 2002-09-02 08:00 | 2003-02-10 17:00 | 105 |  |  |  | 320650 | 267480 | 65 | 336340 | 15690
2.3.7.1.1 | HTR Module M&S (10% Spares) | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 317500 | 264330 | 65 | 333190 |  | 333190
| HTR Production Module | 2002-09-02 08:00 | 2002-12-13 17:00 |  |  | 127 | 2500 | 317500
2.3.7.1.2 | HTR Module Engineering Support | 2002-12-16 08:00 | 2003-01-27 17:00 | 20 |  |  |  | 0
2.3.7.1.3 | Ship HTR Module to CERN | 2003-01-28 08:00 | 2003-02-10 17:00 | 10 |  |  |  | 3150 | 3150 |  | 3150 |  | 3150
| Maryland-CERN Shipping Costs | 2003-01-28 08:00 | 2003-02-10 17:00 |  |  |  |  | 3150
2.3.7.3 | Data Concentrator Module Production | 2002-09-02 08:00 | 2003-02-10 17:00 | 105 |  |  |  | 70200 | 35000 |  | 62000 | -8200
2.3.7.3.1 | Data Concentrator M&S (10% Spares) | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 70200 | 35000 | 10 | 62000 |  | 62000
| DCC Production Module | 2002-09-02 08:00 | 2002-12-13 17:00 |  |  | 9 | 7800 | 70200
2.3.7.3.2 | Data Concentrator Module Engineering Support | 2002-12-16 08:00 | 2003-01-27 17:00 | 20 |  |  |  | 0
2.3.7.3.3 | Ship Data Concentrator Module to CERN | 2003-01-28 08:00 | 2003-02-10 17:00 | 10 |  |  |  | 0
2.3.7.3.4 | Spare Parts | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 0
2.3.7.4 | VME Crates | 2002-09-02 08:00 | 2003-01-20 17:00 | 90 |  |  |  | 44000 | 16500 | 4 | 22000 | -22000
2.3.7.4.1 | VME Subracks M&S | 2002-09-02 08:00 | 2002-11-22 17:00 | 60 |  |  |  | 44000 | 16500 | 4 | 22000 |  | 22000
| VME Crates | 2002-09-02 08:00 | 2002-11-22 17:00 |  |  | 8 | 5500 | 44000
2.3.7.4.2 | VME Subracks Engineering Support | 2002-11-25 08:00 | 2003-01-06 17:00 | 20 |  |  |  | 0
2.3.7.4.3 | Ship VME Subracks to CERN (Zero Cost-Purchase in Europe) | 2003-01-07 08:00 | 2003-01-20 17:00 | 10 |  |  |  | 0
2.3.7.5 | VME Relay Racks M&S (no Spares) | 2002-09-02 08:00 | 2003-03-10 17:00 | 125 |  |  |  | 9000 | 3000 | 2 | 6000 | -3000 | 6000
| VME Racks | 2002-09-02 08:00 | 2003-03-10 17:00 |  |  | 3 | 3000 | 9000
2.3.7.6 | Level 1Trigger Links | 2003-06-02 08:00 | 2003-10-06 14:27 | 90.68 |  |  |  | 29795.8912 | 13847 | 216 | 12960 | -16835.8912
2.3.7.6.1 | Level 1 Link M&S (5% Spares) | 2003-06-02 08:00 | 2003-08-25 14:27 | 60.68 |  |  |  | 29795.8912 | 13847 | 216 | 12960 |  | 12960
| Trigger Link Acquisition | 2003-06-02 08:00 | 2003-08-25 14:27 |  |  | 227 | 131.2594 | 29795.8912
2.3.7.6.2 | Level 1 Link Engineering Support | 2003-08-25 14:27 | 2003-09-22 14:27 | 20 |  |  |  | 0
2.3.7.6.3 | Ship Level 1 Link to CERN | 2003-09-22 14:27 | 2003-10-06 14:27 | 10 |  |  |  | 0
2.3.7.7 | DAQ Links | 2003-06-02 08:00 | 2003-07-11 17:00 | 30 |  |  |  | 0
2.3.7.7.1 | DAQ Link M&S | 2003-06-02 08:00 | 2003-06-27 17:00 | 20 |  |  |  | 0
2.3.7.7.2 | Ship DAQ Link to CERN | 2003-06-30 08:00 | 2003-07-11 17:00 | 10 |  |  |  | 0
2.3.7.10 | HRC Module Production | 2002-09-02 08:00 | 2003-03-10 17:00 | 125 |  |  |  | 58500 | 20000 | 5 | 7500 | -51000
2.3.7.10.1 | HRC Production Module M&S (10% Spares) | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 58500 | 20000 | 5 | 7500 |  | 7500
| HRC Production Module | 2002-09-02 08:00 | 2002-12-13 17:00 |  |  | 9 | 6500 | 58500
2.3.7.10.2 | HRC Production Module Engineering Support | 2002-12-16 08:00 | 2003-02-24 17:00 | 40 |  |  |  | 0
2.3.7.10.3 | Ship HRC Production Module to CERN | 2003-02-25 08:00 | 2003-03-10 17:00 | 10 |  |  |  | 0
2.3.7.10.4 | Spare Parts | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 0
| technician - fermilab - FY97 | 1998-10-01 08:00 | 1998-10-14 17:00 |  |  |  |  | 2184
2.5 | Forward Hadron Calorimeter (HF) | 1997-10-01 08:00 | 2005-07-18 08:00 | 1946 |  |  |  | 7998117.56
2.5.7 | Trigger/DAQ Electronics | 2002-09-02 08:00 | 2003-08-15 17:00 | 239 |  |  |  | 356056.5236 | 0.044518 |  | 311926 | -44130.5236
2.5.7.1 | HTR Module Production | 2002-09-02 08:00 | 2003-02-10 17:00 | 105 |  |  |  | 213150 |  | 46 | 238946 | 25796
2.5.7.1.1 | HTR Module M&S (10% Spares) | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 210000 | 249912 | 46 | 235796 |  | 235796
| HTR Production Module | 2002-09-02 08:00 | 2002-12-13 17:00 |  |  | 84 | 2500 | 210000
2.5.7.1.2 | HTR Module Engineering Support | 2002-12-16 08:00 | 2003-01-27 17:00 | 20 |  |  |  | 0 |  |  | 0
2.5.7.1.3 | Ship HTR Module to CERN | 2003-01-28 08:00 | 2003-02-10 17:00 | 10 |  |  |  | 3150 | 3150 |  | 3150 |  | 3150
| Maryland-CERN Shipping Costs | 2003-01-28 08:00 | 2003-02-10 17:00 |  |  |  |  | 3150
2.5.7.3 | Data Concentrator Module Production | 2002-09-02 08:00 | 2003-02-24 17:00 | 115 |  |  |  | 54600 |  | 7 | 43400 | -11200
2.5.7.3.1 | Data ConcentratorModule M&S (20% Spares) | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 54600 | 30000 | 7 | 43400 |  | 43400
| DCC Production Module | 2002-09-02 08:00 | 2002-12-13 17:00 |  |  | 7 | 7800 | 54600
2.5.7.3.2 | Data Concentrator Module Engineering Support | 2003-01-14 08:00 | 2003-02-10 17:00 | 20 |  |  |  | 0
2.5.7.3.3 | Ship Data Concentrator Module to CERN | 2003-02-11 08:00 | 2003-02-24 17:00 | 10 |  |  |  | 0
2.5.7.3.4 | Spare Parts | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 0
2.5.7.4 | VME Crates | 2002-09-02 08:00 | 2002-12-06 17:00 | 70 |  |  |  | 33000 |  | 3 | 16500 | -16500
2.5.7.4.1 | VME Subracks M&S | 2002-09-02 08:00 | 2002-10-25 17:00 | 40 |  |  |  | 33000 | 16500 | 3 | 16500 |  | 16500
| VME Crates | 2002-09-02 08:00 | 2002-10-25 17:00 |  |  | 6 | 5500 | 33000
2.5.7.4.2 | VME Subracks Engineering Support | 2002-10-28 08:00 | 2002-11-22 17:00 | 20 |  |  |  | 0
2.5.7.4.3 | Ship VME Subracks to CERN (Zero Cost-Purchase in Europe) | 2002-11-25 08:00 | 2002-12-06 17:00 | 10 |  |  |  | 0
2.5.7.5 | VME Relay Racks M&S (no Spares) | 2002-09-02 08:00 | 2003-02-03 17:00 | 100 |  |  |  | 6000 | 3000 | 2 | 6000 | 0 | 6000
| Trigger/DAQ Relay Racks | 2002-09-02 08:00 | 2003-02-03 17:00 |  |  | 2 | 3000 | 6000
2.5.7.6 | Level 1 Trigger Cables | 2003-06-02 08:00 | 2003-08-15 17:00 | 55 |  |  |  | 3806.5236 |  | 18 | 1080 | -2726.5236
2.5.7.6.1 | Level 1 Link M&S (5% Spares) | 2003-06-02 08:00 | 2003-07-04 17:00 | 25 |  |  |  | 3806.5236 | 1769 | 18 | 1080 |  | 1080
| Trigger Link Acquisition | 2003-06-02 08:00 | 2003-07-04 17:00 |  |  | 29 | 131.2594 | 3806.5236
2.5.7.6.2 | Level 1 Link Engineering Support | 2003-07-07 08:00 | 2003-08-01 17:00 | 20 |  |  |  | 0
2.5.7.6.3 | Ship Level 1 Link to CERN | 2003-08-04 08:00 | 2003-08-15 17:00 | 10 |  |  |  | 0
2.5.7.7 | DAQ Links | 2003-06-02 08:00 | 2003-07-11 17:00 | 30 |  |  |  | 0
2.5.7.7.1 | DAQ Link M&S | 2003-06-02 08:00 | 2003-06-27 17:00 | 20 |  |  |  | 0
2.5.7.7.2 | Ship DAQ Link to CERN | 2003-06-30 08:00 | 2003-07-11 17:00 | 10 |  |  |  | 0
2.5.7.8 | HRC Module Production | 2002-09-02 08:00 | 2003-02-10 17:00 | 105 |  |  |  | 45500 |  | 4 | 6000 | -39500
2.5.7.8.1 | HRC Production Module M&S (10% Spares) | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 45500 | 15000 | 4 | 6000 |  | 6000
| HRC Production Module | 2002-09-02 08:00 | 2002-12-13 17:00 |  |  | 7 | 6500 | 45500
2.5.7.8.2 | HRC Production Module Engineering Support | 2002-12-16 08:00 | 2003-01-27 17:00 | 20 |  |  |  | 0
2.5.7.8.3 | Ship HRC Production Module to CERN | 2003-01-28 08:00 | 2003-02-10 17:00 | 10 |  |  |  | 0
2.5.7.8.4 | Spare Parts | 2002-09-02 08:00 | 2002-12-13 17:00 | 75 |  |  |  | 0
| Changes | [10 empty] | 150687.6052
Note on L76: Drew Baden: increases deal with production assembly-line considerations
Note on L83: Drew Baden: spares accounted for in M&S directly
Note on J110: Drew Baden: From Terry Sep 01
Note on K428: Drew Baden: same as number of HTR including spares
Note on L381: Drew Baden: add 180k engineering
Note on F4: Drew Baden: daily rate
Note on F5: Drew Baden: daily rate
Note on F6: Drew Baden: daily rate
Note on F7: Drew Baden: daily rate
Note on F8: Drew Baden: daily rate

## FNAL Accounting
Drew's Amt Billed prior to Oct, Nov, Dec invoices.
P.O. Date | Line # | Description | Total Price | QTY_CANCELLED | PO TOTAL | Amt Billed |  |  | Balance
27-NOV-01 | 15 | 2.1.1.5.1.5 - WORKSTATIONS | 50000 | 0 | 50000 | 11816.54 | x |  | 38183.46
27-NOV-01 | 16 | 2.1.7.11.1.1 - UNIVERSAL TESTER MODULE DESIGN & TESTING | 58900 | 0 | 58900 | 56595.71 | x |  | 2304.29
27-NOV-01 | 17 | 2.1.7.11.1.2 - UNIVERSAL TESTER MODULE DESIGN M&S | 3941 | 0 | 3941 | 3026.84 | x |  | 914.16
27-NOV-01 | 18 | 2.1.7.11.2.1 - FEE EMULATOR DESIGN & TESTING | 49442 | 0 | 49442 | 32808.46 | x |  | 16633.54
10-DEC-01 | 18 | 2.1.7.11.2.1 - FEE EMULATOR DESIGN & TESTING | 742 | 0 | 742 | 0 |  |  | 742
27-NOV-01 | 19 | 2.1.7.11.2.2 - FEE EMULATOR M&S | 12315 | 0 | 12315 | 10998.55 | x |  | 1316.45
10-DEC-01 | 19 | 2.1.7.11.2.2 - FEE EMULATOR M&S | 185 | 0 | 185 | 0 |  |  | 185
27-NOV-01 | 20 | 2.1.7.13.1 - TRIGGER/DAQ HCAL INTEGRATION | 24805 | 0 | 24805 | 24805 | x |  | 0
| 25 | 2.1.7.13.1 - TRIGGER/DAQ HCAL DAQ/TRIGGER INTEGRATION (MARYLAND) | 61935 | 0 | 61935 | 61935 | x |  | 0
10-DEC-01 | 25 | 2.1.7.13.1 - TRIGGER/DAQ HCAL DAQ/TRIGGER INTEGRATION (MARYLAND) | 97008 | 0 | 97008 | 29303.86 | x |  | 67704.14
01-FEB-02 | 25 | 2.1.7.13.1 - TRIGGER/DAQ HCAL DAQ/TRIGGER INTEGRATION (MARYLAND) | 107613 | 0 | 107613 | 0 |  |  | 107613
08-FEB-99 | 7 | WBS 2.1.1.5.1.3 - BLDG PREP & INFRASTRUCTURE | 46285 | 46285 | 0 | 0 |  |  | 0
27-NOV-01 | 13 | 2.1.1.5.1.3 - BLDG. PREP. & INFRASTRUCTURE | 45000 | 0 | 45000 | 15635.64 | not mine |  | 29364.36
08-FEB-99 | 8 | WBS 2.1.1.5.1.4 - INSTALLATION FIXTURES | 20571 | 20571 | 0 | 0 |  |  | 0
30-AUG-01 | 14 | 2.1.1.5.1.4 - INSTALLATION FIXTURES | 20571 | 20571 | 0 | 0 |  |  | 0
08-FEB-99 | 9 | WBS 2.1.1.5.1.5 - WORKSTATIONS | 51429 | 51429 | 0 | 0 |  |  | 0
27-NOV-01 | 12 | 2.1.7.1.1.2 - HTR MODULE SPECIFICATION - ADD LINE 12 | 4899 | 0 | 4899 | 4899 | x |  | 0
27-NOV-01 | 10 | WBS 2.1.1.8.6.9 - MARYLAND MGMT TRAVEL | 10286 | 0 | 10286 | 10286 | x |  | 0
|  |  | 44831 | 0 | 44831 | 44621.09 | x |  | 209.91
10-DEC-01 | 10 | WBS 2.1.1.8.6.9 - MARYLAND MGMT TRAVEL | 21495 | 0 | 21495 | 12488.07 | x |  | 9006.93
27-NOV-01 | 11 | WBS 2.1.10.1.6.4 - MOUNT ACCELEROMETERS | 2057 | 0 | 2057 | 0 |  |  | 2057
27-NOV-01 | 4 | WBS 2.1.1.8.5 HCAL INSTALLATION INTEGRATION-FY97 | 12808 | 0 | 12808 | 12808 | not mine |  | 0
|  |  | 78814 | 0 | 78814 | 28330.06 | not mine |  | 50483.94
21-AUG-98 | 5 | 2.1.10.4.3 - ACCELEROMETERS (PPPA SHIPPING) EDIA | 4926 | 568.94 | 4357.06 | 0 |  |  | 4357.06
30-APR-98 | 1 | WBS2.1.1.1 - BARREL EDIA. | 13000 | 13000 | 0 | 0 |  |  | 0
| 2 | WBS2.1.10.4.3 - ACCELEROMETER (PPPI SHIPPING) EDIA AND M&S. | 5000 | 5000 | 0 | 0 |  |  | 0
| 3 | WBS2.1.7 - TRIGGER/DAQ. | 48000 | 48000 | 0 | 0 |  |  | 0
21-AUG-98 | 6 | 2.1.7 - TRIGGER/DAQ | 47290 | 16551.26 | 30738.74 | 0 |  |  | 30738.74
13-APR-00 | 6 | 2.1.7 - TRIGGER/DAQ | 9444 | 9444 | 0 | 0 |  |  | 0
27-NOV-01 | 21 | 2.1.7.1.1.4.1 - PROTOTYPE MODULE DESIGN & TESTING | 66033 | 0 | 66033 | 19970.74 | x |  | 46062.26
| 22 | 2.1.7.1.1.4.2 - HTR PROTOTYPE MODULE M&S | 16400 | 0 | 16400 | 16400 | x |  | 0
10-DEC-01 | 21 | 2.1.7.1.1.4.1 - PROTOTYPE MODULE DESIGN & TESTING | 424 | 0 | 424 | 0 |  |  | 424
| 22 | 2.1.7.1.1.4.2 - HTR PROTOTYPE MODULE M&S | 14350 | 0 | 14350 | 14350 | x |  | 0
01-FEB-02 | 21 | 2.1.7.1.1.4.1 - PROTOTYPE MODULE DESIGN & TESTING | 4052 | 0 | 4052 | 0 |  |  | 4052
27-NOV-01 | 23 | 2.1.7.11.1.5 - TTC AND LHC EMULATOR SETUP | 9225 | 0 | 9225 | 7481.35 | x |  | 1743.65
27-NOV-01 | 24 | 2.1.7.12.1 - DEMONSTRATOR INTEGRATION TESTS (MARYLAND) | 24600 | 0 | 24600 | 24600 | x |  | 0
01-FEB-02 | 29 | 2.1.7.1.1.5.1 - HTR PROTOTYPE MODULE DESIGN & TESTING | 52594 | 0 | 52594 | 0 |  |  | 52594
| 30 | 2.1.7.1.1.5.2 - HTR PROTOTYPE MODULE M&S | 21033 | 0 | 21033 | 0 |  |  | 21033
01-FEB-02 | 31 | 2.1.7.1.1.6.1 - HTR PRODUCTION MODULE M&S (10% SPARES) | 303254 | 0 | 303254 | 0 |  |  | 303254
| 32 | 2.1.7.5.1 - VME RELAY RACKS M&S (NO SPARES) | 6310 | 0 | 6310 | 0 |  |  | 6310
01-FEB-02 | 33 | 2.1.7.1.1.6.2 - HTR PRODUCTION MODULE ENGINEERING SUPPORT | 20742 | 0 | 20742 | 0 |  |  | 20742
01-FEB-02 | 34 | 2.1.7.12.4 - PROTOTYPE INTEGRATION TESTS (MARYLAND) | 42680 | 0 | 42680 | 0 |  |  | 42680
01-FEB-02 | 35 | 2.2.7.1.1 - HTR MODULE M&S (10% SPARES) | 252712 | 0 | 252712 | 0 |  |  | 252712
01-FEB-02 | 36 | 2.3.7.1.1 - HTR MODULE M&S (10% SPARES) | 303254 | 0 | 303254 | 0 |  |  | 303254
01-FEB-02 | 37 | 2.3.7.5 - VME RELAY RACKS M&S (NO SPARES) | 6310 | 0 | 6310 | 0 |  |  | 6310
01-FEB-02 | 38 | 2.5.7.1.1 - HTR MODULE M&S (10% SPARES) | 237549 | 0 | 237549 | 0 |  |  | 237549
01-FEB-02 | 39 | 2.5.7.5 - VME RELAY RACKS M&S (NO SPARES) | 3155 | 0 | 3155 | 0 |  |  | 3155
27-NOV-01 | 26 | 2.1.10.1.5.4 - MOUNT HB PPP1 ACCELEROMETERS | 5182 | 0 | 5182 | 0 |  |  | 5182
27-NOV-01 | 27 | 2.1.7.1.1.3.1 - HTR DEMONSTRATOR MODULE DESIGN & TESTING | 40584 | 0 | 40584 | 7695.39 | x |  | 32888.61
| 28 | 2.1.7.1.1.3.2 - HTR DEMONSTRATOR MODULE M&S | 15000 | 0 | 15000 | 12877.76 | x |  | 2122.24
|  |  | 2399035 | 231420.2 | 2167614.8 | 463733.06 |  |  | 1703881.74
463733.06

## Engineering Data
| UMD | BU | UIC
1999 | 75 | 60 | 30
2000 | 370 | 185 | 120
2001 | 300 | 155 | 105
2002 | 200 | 90 | 120
2003 | 40 | 10 | 10